Progress Report and Implementation Plan
Semester 1- 2024

| Accessible Word Document | This report follows accessible and inclusive design principles. The report is published in Word format for easy navigation. |
| --- | --- |

CONTENT

Purpose of this Report	4

Audience	4

Reporting Period	4

Executive Summary	17

1.1.	Introduction	17

1.2.	PRISMA progress	18

1.3.	Focus on sustainability	24

Chapter 2.	About the Program	36

2.1.	PRISMA’s Approach	36

2.2.	Governance Structure	37

2.3.	Relevance to the Government of Australia	37

2.4.	Relevance to the Government of Indonesia	38

2.5.	Relevance to Sustainable Development Goals	39

Chapter 3.	Portfolio Overview and Progress	41

3.1.	PRISMA progress	41

3.2.	Other Key Performance Indicators	45

3.3.	Value for Money	46

3.4.	Collaborations	49

3.5.	Challenges, Responses, and Learnings	50

3.6.	Risk Matrix	52

Chapter 4.	Final Year Focus	53

4.1.	Systemic Change and Sustainability	53

3.3.1 High-priority policy initiatives	56

Chapter 5.	Cross-cutting Area Progress	62

5.1.	Climate-smart Agriculture	62

5.2.	Gender Equality, Disability, and Social Inclusion	63

5.3.	Strategic Communications	75

Chapter 6.	Operations	79

6.1.	Human Resources	79

6.2.	Operations	79

Chapter 7.	Annexures	81

7.1.	Annex 1: Sectors Progress	81

7.2.	Annex 2: High-Priority Policy Initiatives	148

7.3.	Annex 3: Detailed Key Performance Indicators	162

Purpose of this Report

This report outlines the semester progress of the Australia-Indonesia Partnership for Promoting Rural Incomes through the Support for Markets in Agriculture (PRISMA) against the previous annual plan. The report follows the Australian Department of Foreign Affairs and Trade (DFAT) guidelines on progress reporting.

Audience

This report has been written for DFAT employees, the Indonesian National Development Planning Agency (Bappenas), and other program stakeholders.

The Progress Report and Implementation Plan (PRIP) is the primary coordination document between the governments of Australia and Indonesia.

Reporting Period

This PRIP covers PRISMA’s performance between 1 January and 30 June 2024. This period is referred to as ‘semester 1’, ‘S1’ or the ‘reporting period’ in this report.

List of abbreviations

| Agrosid | PT Agrosid Manunggal Sentosa |
| --- | --- |
| AI | Artificial Insemination |
| ASF | African Swine Fever |
| ATS | PT Agrotama Tunas Sarana |
| AUD | Australian Dollar |
| Bappeda | Badan Perencanaan dan Pembangunan Daerah (Regional Development Planning Agency) |
| Bappenas | Badan Perencanaan dan Pembangunan Nasional (National Development Planning Agency) |
| Bapperida | Badan Perencanaan Pembangunan Riset dan Inovasi Daerah (Regional Development Planning, Research and Innovation Agency) |
| BBPP | Balai Besar Pelatihan Pertanian (Animal Husbandry Training Center) |
| BITPRO | Direktorat Perbibitan dan Produksi Ternak (Directorate of Livestock Breeding and Production) |
| BNPL | Buy-Now-Pay-Later |
| BOSI | PT Botani Seed Indonesia |
| BPPSDMP | Badan Penyuluhan dan Pengembangan Sumber Daya Manusia Pertanian (Agricultural Human Resources Extension and Development Agency) |
| BPSIP | Balai Penerapan Standar Instrumen Pertanian (Standardisation Agency for Application of Agricultural Instruments) |
| BRIN | Badan Riset dan Inovasi Nasional (The National Research and Innovation Agency) |
| BSN | Badan Standardisasi Nasional (National Standards Agency) |
| B2B | Business-to-Business |
| CEO | Chief Executive Officer |
| CIPS | Center for Indonesian Policy Studies |
| COO | Chief Operations Officer |
| CO2 | Carbon Dioxide |
| CO2e | Carbon Dioxide Equivalent |
| CP | Crop Protection |
| CPPB | Cara Pembuatan Pakan yang Baik (Good Feed Manufacturing Practice) |
| CSL | Climate-smart Livestock |
| CTSI | PT Cipta Ternak Sehat Indonesia (company) |
| CV | Commanditaire Vennootschap (Limited Partnership) |
| DFAT | Department of Foreign Affairs and Trade, Australia |
| DKPP | Dinas Ketahanan Pangan dan Pertanian (Food Security and Agriculture Agency) |
| DPMK | Dinas Pemberdayaan Masyarakat dan Kampung (Community and Village Empowerment Agency) |
| ECB | Emission Control Blocks |
| EWINDO | East West Indonesia (seed company) |
| FGD | Focus Group Discussion |
| FMD | Foot and Mouth Disease |
| Fintech | Financial Technology |
| GAP | Good Agricultural Practices |
| GBV | Gender-Based Violence |
| GEDSI | Gender Equality, Disability and Social Inclusion |
| GFMP | Good Feed Manufacturing Practices |
| GFP | Good Fertiliser Practices |
| GHG | Greenhouse Gases |
| GKSI | Gabungan Koperasi Susu Indonesia (Indonesian Dairy Cooperative Association) |
| GOA | Government of Australia |
| GOI | Government of Indonesia |
| GCP | Good Crop Protection Practices |
| Ha | Hectare |
| HH | Household |
| HPPI | High Priority Policy Initiatives |
| HYV | High-yielding Rice Seed Variety |
| ICN | Intervention Concept Note |
| ICT | Information and Communications Technology |
| IDR | Indonesian Rupiah |
| INDEF | Institute for Development and Economics and Finance |
| IP | Intervention Plan |
| IPB University | Institut Pertanian Bogor |
| ISP | Intermediary Service Providers |
| Jamkrindo | PT Jaminan Kredit Indonesia (a guarantee company) |
| KJUB Puspetasari | Koperasi Jasa Usaha Bersama (Joint Business Services Cooperative) |
| KPI | Key Performance Indicator |
| LAMP | Loop-mediated Isothermal Amplification |
| LSD | Lumpy Skin Disease |
| MoA | Indonesian Ministry of Agriculture |
| MoU | Memorandum of Understanding |
| MPR | Majelis Permusyawaratan Rakyat (People’s Consultative Assembly) |
| MSD | Market Systems Development |
| MSME | Micro, Small, Medium-sized Enterprise |
| MSS | Market System Strategy |
| NAIC | Net Attributable Income Change |
| NPN | Non-Protein Nitrogen |
| NPP | Nomor Pendaftaran Pakan (Feed Registration Number) |
| NTB | Nusa Tenggara Barat (West Nusa Tenggara Province) |
| NTT | Nusa Tenggara Timur (East Nusa Tenggara Province) |
| OJK | Otoritas Jasa Keuangan (Financial Service Authority) |
| OPD | Organisation of People with Disabilities |
| OPV | Open-pollinated Variety (a hybrid seed) |
| PCC | Project Coordination Committee |
| PISAgro | Partnership for Indonesia’s Sustainable Agriculture |
| PPP | Purchasing Power Parity |
| PR YAKKUM | Pusat Rehabilitasi YAKKUM (YAKKUM Rehabilitation Center) |
| PROSPERA | Australia Indonesia Partnership for Economic Development |
| PRISMA | Promoting Rural Income through Support for Markets in Agriculture |
| PRIP | Progress Report and Implementation Plan |
| PSIPKH | Pusat Standar Instrumen Peternakan dan Kesehatan Hewan (Livestock and Animal Health Instrument Certification Agency) |
| PSP | Private Sector Partners |
| PYCH | Papua Youth Creative Hub |
| RENSTRA | Rencana Strategis (Strategic Plan) |
| RML | Results, Measurement and Learning |
| RPJMD | Rencana Pembangunan Jangka Menengah Daerah (Regional Medium-Term Development Planning) |
| RPJMN | Rencana Pembangunan Jangka Menengah Nasional (National Medium-Term Development Planning) |
| RPJPN | Rencana Pembangunan Jangka Panjang Nasional (National Long-Term Development Planning) |
| SDG | Sustainable Development Goals |
| SGM-Danone | PT Sarihusada Generasi Mahardika |
| SME | Small and Medium-sized Enterprise |
| SNI | Standar Nasional Indonesia (National Standards) |
| SOP | Standard Operational Procedures |
| SROI | Social Return on Investment |
| UD | Universal Design |
| UNW | University of Nadhlatul Wathan |
| UPJA | Government Mechanisation Service Unit |
| USD | American Dollar |
| VFM | Value for Money |
| WSAs | Women Sales Agents |
| WEE | Women's Economic Empowerment |
| YBTS | Yayasan Bina Tani Sejahtera (a foundation under PT East West Seed Indonesia) |

Definitions of key terms

| Direct Intervention Cost | PRISMA’s contributions to the intervention-related budget, as described in the partnership agreement or memorandum of understanding |
| --- | --- |
| Existing Intervention | Intervention that is currently running and/or commenced this semester |
| Intervention Concept Note (ICN) | An intervention concept note is an initial document outlining the main features and context of a planned intervention. |
| Indirect Intervention Cost | PRISMA’s contribution to implementation staff costs (and travel costs), result, management, and learning costs (including studies) connected to the intervention, capacity building, and communication costs |
| Investment Leverage (partners) | The ratio of the value of additional investments by partners to PRISMA’s total intervention costs |
| Investment Leverage (private sector) | The ratio of the value of additional investments by the private sector to PRISMA’s total intervention costs |
| Investment Per Farm Household | Amount of money invested by PRISMA for each farming household beneficiary |
| Intervention Plan (IP) | An intervention plan is a detailed document containing all information and data relevant to the decision to start the intervention. |
| Intermediary Service Providers | Intermediary service providers are small or medium-sized enterprises in the up- or down-stream value chain of a partner enterprise of PRISMA (i.e., either buying from farmers and selling to partners or buying from partners and selling to farmers); they can also have important functions, such as information providers or lenders. |
| KPI 1 | Number of smallholder farming households with increased net income attributable to PRISMA’s interventions |
| KPI 1a (new) | Number of smallholder farming households under the American dollar (USD) 2.50 purchasing power parity poverty line with increased net income |
| KPI 1a (old) | Number of smallholder farming households under the USD2.00 purchasing power parity poverty line with increased net income |
| KPI 1b (new) | Number of smallholder farming households under the USD5.50 purchasing power parity poverty line with increased net income |
| KPI 1b (old) | Number of smallholder farming households under the USD2.50 purchasing power parity poverty line with increased net income |
| KPI 2 | Net attributable additional income for benefitted farming households in Indonesian rupiah (IDR) |
| KPI 2a | Net attributable additional income for benefitted farming households under the USD1.90 purchasing power parity poverty line (extreme poverty) in IDR |
| KPI 2b | Net attributable additional income for benefitted farming households under the USD2.50 purchasing power parity poverty line in IDR |
| KPI 3 | Number of intermediary service providers providing farmers additional/improved access to innovation |
| KPI 4 | Women’s economic empowerment effectiveness within PRISMA innovations |
| KPI 5 | Value of additional turnover of intermediary service providers in IDR |
| KPI 6 | Number of intervention partners (private and public sector) |
| KPI 7 | Number of intervention partners (private and public sector) |
| KPI 8 | Value of attributable additional and/or more inclusive investment by the public and private sector in IDR |
| KPI 8a | Value of attributable additional and/or more inclusive investment by public and private partners in IDR |
| KPI 9 | Number of crowding-in businesses/institutions induced by PRISMA |
| KPI 10 | Number of responding businesses/institutions induced by PRISMA |
| KPI 11 | Number of policy engagements |
| MSMB | Mitra Sejahtera Membangun Bangsa (an agricultural startup) |
| NAIC | Net attributable income change is an additional income generated from a specific technology or input PRISMA promotes during one production cycle. For livestock, the measurement period is 6 months. |
| New Intervention | An intervention that started this semester |
| Outreach | Number of smallholder farming households with increased incomes |
| Partnership Outreach | Outreach that comes directly from PRISMA’s partner in the targeted area |
| Pipeline | Projection value from potential new interventions which are still at the idea/ICN/IP stage |
| Projection | Projection value from existing and new interventions |
| Quality Management Tool | A tool to assess intervention quality over time, from ICN to IP and implementation |
| Social Return on Investment | The ratio of the value of farming household’s net income increase compared to PRISMA’s total intervention costs |
| Total Intervention Cost | Total of direct and indirect intervention costs |
| Total Outreach | Partnership and wider market outreach |
| Wider Market Outreach or Households | Outreach that comes from PRISMA’s partners in other areas, other market actors in the targeted areas, and other market actors in other areas that are attributable to PRISMA’s interventions |

Glossary

| Copying | This is when several market players (competitors) adopt comparable changes instigated by PRISMA partners – either direct copies or variants of the original innovation – that are upheld without PRISMA support. This is also a key indicator of systemic change. |
| --- | --- |
| Crowding-in | Crowding-in is the process of stimulating several market players to react to the system-level changes instigated through the intervention activities. It results in greater breadth and depth within the core market functions and is a key indicator of systemic change. |
| Market Systems Development (MSD) | In poorly performing markets, such as agriculture, critical functions, such as information, technology, infrastructure, finance, skills, standards, regulations, etc., are either absent or not working as they should. Instead of supporting sector performance, they tend to inhibit it. Changes in these functions and rules are therefore needed if a sector is to perform better. In practical terms, it is these ‘supporting functions’ of the market that PRISMA seeks to influence, to make them more supportive of sector competitiveness and inclusivity. |
| Market System Strategy (MSS) | PRISMA uses an MSS framework for each sector to link its activities with partners to what it hopes to achieve in the ‘market system’ and towards achieving the program objectives. PRISMA uses a three-tiered system as a basis for the MSS – intervention area; market function; and market system change, which contribute to the sector vision. |
| Results Chain | A model showing the chain of causality through which PRISMA’s activities lead to poverty-reducing benefits. Results chains are tailored to specific interventions and are consequently more detailed than a MSS. |
| Systemic Change | When PRISMA refers to systemic change, it describes the improvements in how a market’s supporting functions are performed and how they contribute to improved sector performance and inclusivity. This is achieved by addressing the root causes of market failures and promoting inclusion and resilience at the same time. |
| Resilience | The ability of the market actors to withstand shocks, respond to unexpected threats, and continue business operations under stress. |

Executive Summary

Introduction

This report presents the final half-year progress of the Australia-Indonesia Partnership for Promoting Rural Incomes through Support for Markets in Agriculture (PRISMA). A transformative program, PRISMA has increased incomes for over 1.48 million farming households.

Massive system change has driven this result. This change is not static but a process that will continue to unfold beyond the program’s life. Farmers, agro retailers and traders have adopted higher productivity practices that generate higher incomes throughout the supply chain. Higher incomes increase investment back into agriculture, generating more resilient markets. For PRISMA, commerciality is sustainability.

The evidence PRISMA generates has been transferred to the government of Indonesia's planning and policy processes and academic institutions. Significant policy initiatives have made transformational changes (new processes, practices, regulations) and improved capacity within key partner institutions, supporting productivity increases and inbuilt resilience for farmers and the ecosystem surrounding them.

PRISMA has seen groundbreaking results in climate-smart agriculture. The program has pioneered interventions that build incomes in farming zones adapting to climate change, from catalysing climate-smart rice seeds to kick-starting mineral-based organic fertiliser usage. There continue to be opportunities to scale climate-smart innovations and influence government approaches in this fast evolving area.

Building on its success, PRISMA’s focus on its final year is to influence the market with its know-how and expertise. The eleventh year was an extension granted by DFAT in recognition of the opportunity to share the PRISMA experience more widely. The program for the final year split sustainability targets into sector-level activities (market resilience) and policy- and academic-institution-focused activities (high-priority policy initiatives).

Resilience activities spanned 12 sectors, bolstering market actors' ability to navigate market stress and uncertainties. These included activities and events for building private and public sector capacities, enhancing market functions critical for sector performance, and institutionalizing essential functions like research and marketing. Twenty-seven events were held, reaching more than 2.5 million people and influencing more than 2,500 people face-to-face.

The high-priority policy initiatives targeted policy and institutional behaviour changes to foster a more conducive environment for private sector-led agricultural growth. These initiatives build on PRISMA efforts to foster a more enabling business environment in key sectors and national and regional agricultural planning. In total, PRISMA has supported 170 GoI policy initiatives, including a few major initiatives, such as revamping Indonesia’s cattle feed standard (SNI), creating the dairy sector roadmap and contributing to the national 5-year planning. In the process, PRISMA has been recognised and appreciated by national government bodies, including Bappenas and the Ministry of Agriculture (MoA).one of our wAs a result, Bappenas and MoA continue to request PRISMA’s support in 2024 and beyond, particularly in the areas of national food security, policy and regulatory reforms, and institutional capacity development.

PRISMA is the only agriculture program that collaborates with over 238 private entities and has proven its value to the private and public sectors. Creating opportunities for overlooked market segments has been one of PRISMA’s success stories. Supporting companies to adapt their outreach to target women farmers, who make up more than one-quarter of the farming population, has resulted in income increases and greater agency for women. A similar story could be told on disability inclusive practices and work with indigenous farmers in Tanah Papua.

PRISMA’s credibility and depth of knowledge has influenced businesses to change their approach. This knowledge was harvested and shared in the final year, with increased knowledge in the market triggered by national events on gender equality and disability inclusion. Read on for more on the impact of PRISMA, this semester, and over its remarkable last decade.

PRISMA progress

The EOPO outcome data is derived from impact assessments of interventions in semester 2, 2023, and previous interventions that continued into semester 1, 2024. The majority of PRISMA’s interventions ceased in December 2023 to concentrate on market resilience. The outreach and income continue to increase, as documented below.

End-of-program outcome: 1,000,000 farming households increase their income by 30 percent due to PRISMA Interventions

PRISMA's end-of-program outcome is to increase the income of one million smallholder farming households by 30 per cent by December 2023. This is a cumulative outcome spanning both phases of the program. PRISMA exceeded the program outcome by the end of 2023 and is projected to reach over 1.48 million smallholder farmers by the end of 2024.

Outreach

Projected cumulative end of 2nd Phase (Semester 2, 2024)

1,487,364

Cumulative
1st Phase

345,001

Actual cumulative 2nd Phase (Semester 1, 2024)

1,482,778

Note that in the updated figure for the end-of-program outreach, the projected end-of-program outreach is 1,487,634 farming households, down from 1,582,147 the previous semester. There are 2 major contributing factors for this reduction: (i) High level of overlaps: during semester Y23S2, outreach overlap was 51%, and during semester Y24S1, the overlap shot up to 61.1%, and (ii) As partnerships ended with the private sector, conducting impact assessments, which are dependent on partners’ confidential data like sales information are increasingly difficult.

In this reporting period, PRISMA's interventions reached an additional 26,993 smallholder farming households. Over 66.4% of these households are living below the USD5.50 purchasing power parity poverty line, and more than 39.9% live under the USD2.50 purchasing power parity poverty line.

The increase in outreach this semester is largely attributed to PRISMA's interventions in the mechanisation and beef sectors, which account for 6,699 and 6,089 households, respectively. The remaining households impacted by PRISMA's interventions have been in 6 active sectors (mungbean, soil treatment, dairy, vegetable, rice, and pig).

To attribute the results in this semester, PRISMA conducted 7 impact assessments and 12 extrapolations. The number of beneficiaries decreased compared to last semester due to a staggering 61.1% overlap in beneficiaries this semester, indicating that more farming households access and benefit from multiple innovations from PRISMA’s partners.

This semester, 19.6% of overall outreach came from the wider market as PRISMA’s partners in the beef, mechanisation, vegetable, rice, and dairy sectors independently expanded their businesses beyond PRISMA’s intervention areas.

The overall proportion of wider outreach reached 48.7%, indicating that PRISMA’s interventions have led to sustainable and scalable outcomes.

Income

A high net attributable income increase continues to demonstrate the effectiveness of PRISMA's interventions.

This semester's average net attributable income change percentage was 33.3%, contributing to a cumulative percentage of net attributable income of 123%, a change from 149% in the previous semester. As outreach grows, a slight decrease in net attributable income change percentage is expected as the innovations reach more households further along the spectrum of innovation diffusion, as these households tend to have less capital and skill than early adopters of innovations.

Meanwhile, this semester’s net attributable income increased by 4.65% per household, from IDR3.49 million the previous semester to IDR3.65 million per household. This semester’s total net attributable income change from all PRISMA beneficiary farming households amounted to IDR253 billion, bringing the cumulative net attributable income change to IDR9.27 trillion or approximately AUD927 million. These figures demonstrate the continuous positive impact and progress generated by PRISMA’s interventions.

Focus on sustainability

PRISMA’s focus on its final year is to influence the market with its know-how and expertise. The program for the final year split sustainability targets into sector-level activities (market resilience) and policy- and academic-institution-focused activities (high-priority policy initiatives). Interventions stopped, and knowledge from cross-cutting areas and sectors was shared with the market.

PRISMA is an insightful, tangible, impactful, and sustainable program. Its legacy in the field is real and sustainable.

Uthamy Sary, MSc, Coordinator of the Bilateral Funding Directorate, Bappenas reflecting on PRISMA’s impact during a field visit in July.

Climate-Smart Agriculture, Policy, GEDSI, Communications

The progress data is derived from impact assessments of interventions in semester 2, 2023, and previous interventions that continued into semester 1, 2024. Most of PRISMA’s interventions ceased in December 2023 to concentrate on market resilience and ensure the sustainability of climate, GEDSI, and policy outcomes supported by strategic communications.

Climate-smart agriculture

PRISMA's interventions support private investment in climate-smart technologies, practices, and business models. These interventions have reduced emissions and enabled adaptation. PRISMA has supported climate initiatives through its market resilience activities, including the launch of a pioneering climate-smart seed from its partner and rice seed producer, PT Botani. For more information, please refer to Chapter 3 and ANNEX 1 for progress against the Progress. PRISMA gathered and shared its key learnings in climate-smart agriculture through three case studies and co-supported a national event for the Ministry of Agriculture and Bappenas in collaboration with the World Bank.

|  | 137,132 tonnes of carbon dioxide emissions reduced |
| --- | --- |
|  | 2,027,180 smallholder farmers contributed to emission reductions |
|  | 3 case studies On climate-smart agriculture |
|  | 2 events 1 National event and 1 climate smart seed launch |

A feed supplement with potential 
Smallholder beef and dairy farmers have had a tumultuous few years, battling foot and mouth and lumpy skin disease. Hard-fought wins in productivity have been lost in the battle with these animal diseases. PRISMA recognised the potential of Australian technology company AgCoTech’s feed innovation, the emission control blocks and backed further trials this semester. The trials demonstrated how the innovative feed supplement can reduce greenhouse gas emissions by up to 18% and boost productivity and income for smallholder farmers. AgCoTech will use the data from the trials to further develop the business model in Indonesia.

One of our cows was slow to recover from a Foot and Mouth Disease (FMD) infection from last year. After using the blocks, she’s much healthier.

Policy engagement

PRISMA supports policy initiatives to inform and influence key decision-makers and stakeholders using evidence from PRISMA’s interventions. PRISMA focused on 8 high priority policy initiatives (HPPI) this semester to ensure better sustainability. These initiatives cover sector-specific policies (beef, dairy, maize, and pig), national and regional government policy planning processes, and embedding the MSD approach in government institutions and universities’ academic programs.

|  | 48 policy initiatives in total with 8 high priority areas to support sustainability |
| --- | --- |
|  | 170 policy initiatives (cumulative) |

An opportunity to shape policy

The remarkable success story of PRISMA has not only attracted Bappenas’s interest in the MSD approach but also instilled confidence that the approach can help the government more effectively achieve its development goals and objectives. As a consequence, one of PRISMA’s 8 high-priority policy initiatives is supporting the government in adopting MSD principles. To do this, PRISMA held a one-week training that translated the concepts into practical and applicable guidance for government and university participants. The training was well received, with strong testimonials from the participants on the insights gained (shared below and in Chapter 2).

The market system development (MSD) approach that we learnt from the training can enrich the analysis of our main responsibilities and functions at the policy-making level

Agung Saras Sri Raharjo, Center for Social Economics and Agricultural Policy,

Gender equality, disability and social inclusion

PRISMA supports inclusive business models that promote gender equality and increase the inclusion of people with disabilities, youth, and Indigenous peoples. This semester, PRISMA partners continued to positively impact women, people with disabilities, and Indigenous people in Papua. PRISMA documented and shared its experience at events to influence further change.

|  | 31% of 2,257 women respondents experienced improved knowledge and skills in farming practices this semester |
| --- | --- |
|  | 59% of 2,422 women respondents experienced economic advancement |
|  | 28% of 2,306 women respondents experienced increased decision-making in agriculture |

## Women farmers share their story

Commemorating International Women’s Day, PRISMA hosted a business seminar titled “Empowering Women in Agriculture – Opportunities for Business” in Jakarta on 7 March. The event attracted 87 participants from the private sector, development organizations, and women farmers. In collaboration with the Partnership for Indonesia’s Sustainable Agriculture (PISAgro), the seminar focused on the pivotal role of women in agriculture, both as customers and as staff.

## Ibu Lasmi traveled from her fertile farm in the foothills of Mount Merbabu to Jakarta to share her story at the PRISMA-PISAgro event. As a vegetable farmer and leader of an all-women’s farmers' group, she was eager to highlight the importance of access to finance and training opportunities provided through PRISMA's partnership.

## PRISMA worked with the finance company PNM to offer loans paired with training for women’s farmer groups. The training focused on enhancing business knowledge and fostering effective collaboration within the groups, with the goal of improving productivity. For PNM, this initiative also supports customer acquisition and retention. As a result of this partnership, Ibu Lasmi’s group has transitioned to growing higher-value, organic vegetables and significantly boosted their productivity.

“What I found helpful was the support from PNM to strengthen communication in the group and define the roles, our business knowledge and ways to improve our farming, like making our own organic fertiliser.” explains Ibu Lasmi.

Photo: Lasmi, a farmer from Mekaar Abadi Women’s Farmer Group at an International Women’s Day business seminar in Jakarta, organized by PRISMA and PISAgro.

Disability inclusion

PRISMA supports widespread awareness and understanding of disability in the private sector and governments to support inclusion in agriculture.

|  | 17 farmers with disabilities benefitted through PRISMA’s interventions this semester |
| --- | --- |
|  | 3 partners adopted universal design principles to improve accessibility to their products |
|  | 3 partners demonstrated commitment to developing more inclusive farmer outreach activities |
|  | 1 National disability inclusion event to share PRISMA experience and influence agribusinesses |

Influencing agribusinesses to adopt disability-inclusive practices

Farmers in Indonesia are ageing. This means the prevalence of disabilities, especially those related to mobility and sensory functions, is increasing. Routine tasks for farmers, such as gathering green fodder to feed their dairy cows in a backyard pen or reading the label on the back of a fertiliser bottle at their local agri-kiosks, become difficult. This highlights the need for agribusinesses to consider how farmers engage with their products to ensure that farmers with disabilities can continue contributing effectively and maintaining their livelihoods.  PRISMA hosted a Petani Maju (Future Farmer) event called "Disability Inclusion in Agribusiness: From Awareness to Action" in Jakarta. The full day of activities allowed agribusinesses to learn from farmers with disabilities and share best practices for reaching farmers with a disability with products, services, and innovations that can increase their incomes.

When we did this project, we talked with our friends with disabilities about what they need and how it matches our needs

Totok Setyarto, Director of PT NuFeed International Indonesia on developing NuFeed’s disability inclusive strategy.

Youth inclusion

|  | 115,111 young farmers (individuals between 18 and 35 years) have cumulatively benefited from PRISMA’s interventions |
| --- | --- |

Indigenous inclusion

|  | 2 partners have business models targeting indigenous farmers in Tanah Papua |
| --- | --- |
|  | 2 Events sharing indigenous business models |

Strategic Communication

Strategic communication supports market resilience and policy initiatives which in turn supports a strong program legacy. This semester, PRISMA launched a final-year campaign called Petani Maju / Future Farmer. As a result, there was a significant increase in PRISMA’s reach from 806,000 last semester to 2.6 million this semester.

|  | 2.68 m audience through digital channels this semester |
| --- | --- |
|  | 7.98 m cumulative audience since measurement started in January 2022 |
|  | 197 cumulative media mentions for phase 2 |

Locally-led development

|  | To support locally-led development, PRISMA has co-created and co-financed 396 interventions with 273 organisations, 93% of which are local. |
| --- | --- |
|  | PRISMA has provided technical and financial support to these local entities (private companies, local governments, associations, universities, etc.) to implement interventions. |

This semester, PRISMA launched a final-year, public facing campaign called Petani Maju / Future Farmer. The campaign provides a platform for PRISMA’s market resilience and high priority policy initiatives in its final year and uses its private and public sector partner network to reach a larger audience. The goal was to reach 2 million people, and so far, the campaign has reached 2.68 million people. In addition to the metrics on digital reach, event attendees and media mentions (shared in the Executive Summary), PRISMA gathered qualitative data to gauge the level of influence of PRISMA’s events and activities. Quotes from event participants can be found throughout this report.

I will schedule some time for us to connect.

Campaign rationale

Petani Maju / Future Farmer, aims to share its insights, unearth ideas, and facilitate collaboration among private and public sector market actors. The goal is to equip farmers, businesses and agriculture market actors with the information they need to unlock productivity.

In the past decade, PRISMA has positively impacted over 1.4 million smallholder farming households. PRISMA has supported productivity gains and increased incomes by an average of 123% and leveraged AUD 33m in private sector investment in business models targeting smallholder farming households. However, achieving sustainable agricultural development requires ongoing collaboration and effort.

So, how can we catalyse change?

Petani Maju / Future Farmer is working towards the Government of Indonesia's vision of modernising agriculture.

We know, there are products, services, and technologies available today that can significantly increase smallholder farmers' productivity. But what are they, and how can they reach more farmers? And what is the role of the agribusinesses in encouraging behaviour change? PRISMA holds answers to some of these questions, drawing from its experience gained through collaborations with 273 private and public sector partners spanning 6 provinces and 12 agricultural commodities.

What is a Petani Maju / Future Farmer?

A farmer equipped with innovative products, services, and technologies can significantly enhance productivity, increase incomes, and build resilience to climate change. These innovations include high-yielding, climate-smart rice seeds that require less water and fertilizer, affordable, high-quality animal feed that reduces rearing time and alleviates the workload for women, and finance and technology apps designed to boost the productivity of agri-kiosks and the farmers they serve.

Improved productivity not only benefits smallholder farming households but also strengthens the communities they inhabit. Research conducted by PRISMA demonstrates that as farmers' incomes rise, they reinvest in agriculture, small business ventures, and their children's education, leading to more resilient and prosperous communities.

A survey by PRISMA involving 166 farmers from Central and East Java explored the social impact of income growth. Notably, 31% of respondents prioritized reinvesting in economic activities, while 22.5% focused on daily sustenance and 8.55% on education for their children. These findings highlight the pivotal role that increased income plays in expanding economic opportunities and enhancing the overall well-being of households and communities.

Supporting climate-resilient farmers

Climate-resilient agricultural inputs and practices can improve productivity, mitigate emissions and bolster farmers' ability to withstand extreme weather events. For instance, organic mineral-based fertilisers curb emissions and regenerate soils, while drought-tolerant, high-yielding maize seeds offer resilience against drier weather conditions.

The campaign aims to uncover and disseminate climate-smart technologies and agribusiness experiences, while also introducing products and innovations to smallholder farmers.

Building inclusive markets

Marginalised groups are often involved in agriculture yet miss out as consumers on products and services that could improve productivity. Agribusinesses can bridge this gap by researching and targeting different customer segments.

The campaign shares information to support marketing teams, company field staff, and government extension workers in reaching farmers more effectively. For example, this guidebook for marketing teams, agronomists, and field staff shares practical tips for agribusinesses on improving access to information for women farmers.

Through effective behaviour change

PRISMA has observed and supported companies in adapting their outreach and better supporting farmer behaviour change through this process. For example, supporting businesses to shift from short-term hard-selling strategies for fertilisers and pesticides to education-based marketing that builds trust with customers, increases their success rate and productivity and results in repeat customers.

In the fertiliser sector especially PRISMA found that fertiliser companies and distributors must engage in good product promotional and marketing strategies and provide regular information on good agricultural practices and proper fertiliser application. Only by doing this would farmers understand the benefits of judicious use of fertiliser and experience improved productivity.

The campaign shares behaviour change strategies specific to critical agricultural commodities for productivity and growth.

About the Program

PRISMA is a market systems development (MSD) program currently engaged in 12 agricultural sectors across 6 provinces: Central Java, East Java, East Nusa Tenggara (NTT), West Nusa Tenggara (NTB), Papua and West Papua. The Australian Government (GOA) funds PRISMA through the Department of Foreign Affairs and Trade (DFAT) in cooperation with the Government of Indonesia (GOI) through the National Development Planning Agency (Bappenas).

PRISMA’s Approach

PRISMA’s interventions from 2013 to 2023 have sought to change how the private sector does business in rural Indonesia to improve the productivity and income of smallholder farming households. Improving agricultural productivity closely aligns with the GOA and GOI’s goals to support poverty alleviation, climate change adaptation and mitigation, and contribute to smallholder farming household food security.

PRISMA achieved this by:

PRISMA’s approach has resulted in the program exceeding its end-of-program outcomes (to increase the income of one million smallholder farming households by 30%).

In addition to income increases, PRISMA has brought about significant development outcomes such as:

- Transforming economic systems and industries through systemic change,

- Initiating change to make markets more financially rewarding through business and small and medium-sized enterprise (SME) growth,

- Increasing private sector investment in climate-smart technologies, practices, and business models, supporting emission reductions and adaptation,

- Encouraging more inclusive markets through support for gender and disability-equitable business practices,

- Addressing the rules and regulations that constrain sector growth and competitiveness through policy support,

- Supporting crowding-in by other market actors (for example, other firms replicating the new, more inclusive business models) through policy support to amend legislation or streamlined procedures,

- Supporting market resilience by harvesting and sharing the PRISMA experience.

More on PRISMA’s impact can be found in the key performance indicator (KPI) table in Chapter 3.

Governance Structure

PRISMA’s governance structure includes the Project Coordination Committee (PCC), with representatives from Bappenas (from the Directorate for Food and Agriculture) and DFAT. The PCC meets at least once a year to review program updates, provide recommendations, and approve the Progress. PRISMA and DFAT also hold regular meetings to discuss program progress and challenges. PRISMA shares a monthly update report based on these discussions, which DFAT uses to communicate with Bappenas. Meanwhile, the internal governance structure includes a management team with members from all portfolios, a chief operations officer, chief technical officers, and a chief executive officer. The management team meets weekly to discuss the program’s progress, implementation plans, challenges, and risks.

Relevance to the Government of Australia

Australia’s development program aims to advance a peaceful, stable, prosperous Indo-Pacific region. Australia’s International Development Policy outlines how this will be achieved through sustainable development, lifting people out of poverty, the climate agenda, gender equality, disability and social inclusion, locally-led development, and community resilience.

PRISMA aligns strongly with many aspects of DFAT’s International Development Policy.

| DFAT policy aim | How PRISMA aligns with DFAT policy aims |
| --- | --- |
| Sustainable development and poverty reduction | PRISMA aims to increase the productivity and incomes of smallholder farmers, the majority of whom live below the poverty line. As of June 2024, 61.9% % of smallholder farming households reached by PRISMA were under the USD5.50 PPP poverty line, and 36.7% were facing extreme poverty with less than USD2.50 PPP per day. |
| Climate change | PRISMA supports private investment in climate-smart technologies, practices, and business models, supporting emission reductions and adaptation. |
| Gender equality, disability and social inclusion | PRISMA supports sustainable and inclusive businesses that increase the productivity of marginalised smallholder farmers by improving agricultural productivity. PRISMA’s partners target marginalised farmers in marketing, outreach, and training and hold inclusive training for staff to increase incomes and well-being. |
| Locally-led development | To support locally-led development, PRISMA has co-created and co-financed 396 interventions with 273 organisations, 93 % of which are local. PRISMA has provided technical and financial support to these local entities (private companies, local governments, associations, universities, etc.) to implement interventions. |
| Community resilience | PRISMA works with the private sector to build smallholder farmers’ resilience to market shocks by tackling the underlying causes of market failures, such as limited access to agricultural products and information. |

Relevance to the Government of Indonesia

Indonesia's National Long-Term Development Plan (RPJPN) from 2005 to 2025 places rural development at the centre of addressing the interconnected issues of food security, fairness, and economic growth.

PRISMA’s aim to improve agricultural productivity closely aligns with these interconnected issues and the RPJPN’s goals. Transforming agriculture is central to economic growth. Furthermore, PRISMA’s focus on eastern Indonesia aligns with the RPJPN’s focus on reducing regional disparities by growing the economy in rural regions.

PRISMA intervention aligns with the incoming RPJPN 2025-2045 transformation goal, which focuses on strengthening food system resilience. This transformation is derived from Indonesia's focus on building social, cultural, and ecological resilience. This approach advances food, water, and energy interdependence, as well as resilience to disasters and climate change.

Relevance to Sustainable Development Goals

Australia and Indonesia are committed to the United Nations 2030 Agenda for Sustainable Development and the Sustainable Development Goals (SDGs) as the globally agreed framework for international development.

PRISMA’s KPIs are aligned with SDGs 1 and 2: ending poverty and hunger. PRISMA also captures data on women’s economic empowerment (WEE), which contributes to SDG 5: gender equality.

Portfolio Overview and Progress

PRISMA progress

The EOPO outcome data is derived from impact assessments of interventions in semester 2, 2023, and previous interventions that continued into semester 1, 2024. The majority of PRISMA’s interventions ceased in December 2023 to concentrate on market resilience. The outreach and income continue to increase, as documented below.

End-of-program outcome: 1,000,000 farming households increase their income by 30 percent due to PRISMA Interventions

PRISMA's end-of-program outcome is to increase the income of one million smallholder farming households by 30 per cent by December 2023. This is a cumulative outcome spanning both phases of the program. PRISMA exceeded the program outcome by the end of 2023 and is projected to reach over 1.48 million smallholder farmers by the end of 2024.

Outreach

Projected cumulative end of 2nd Phase (Semester 2, 2024)

1,487,364

Cumulative
1st Phase

345,001

Actual cumulative 2nd Phase (Semester 1, 2024)

1,482,778

Note that in the updated figure for the end-of-program outreach, the projected end-of-program outreach is 1,487,634 farming households, down from 1,582,147 the previous semester. There are 2 major contributing factors for this reduction: (i) High level of overlaps: during semester Y23S2, outreach overlap reached 51%, and during semester Y24S1, the overlap shot up to over 61.1%, and (ii) As partnerships ended with the private sector, it is increasingly difficulty to conduct impact assessments, which are dependent on partners’ confidential data like sales information.

In this reporting period, PRISMA's interventions reached an additional 26,993 smallholder farming households. Over 66.4% of these households are currently living below the USD5.50 PPP poverty line, and more than 39.9% live under the USD2.50 PPP poverty line.

The increase in outreach this semester was largely attributed to PRISMA's interventions in the mechanisation and beef sectors, which account for 6,699 and 6,089 households, respectively. The remaining households impacted by PRISMA's interventions were in 6 active sectors (mungbean, soil treatment, dairy, vegetable, rice, and pig).

To attribute the results in this semester, PRISMA conducted 7 impact assessments and 12 extrapolations. The number of beneficiaries decreased compared to last semester due to a staggering 61.1% overlap in beneficiaries this semester, indicating that more farming households access and benefit from multiple innovations from PRISMA’s partners.

This semester, 19.6% of overall outreach came from the wider market as PRISMA’s partners in the beef, mechanisation, vegetable, rice, and dairy sectors independently expanded their businesses beyond PRISMA’s intervention areas.

The overall proportion of wider outreach reached 48.7%, indicating that PRISMA’s interventions have led to sustainable and scalable outcomes.

Income

This semester's average NAIC percentage was 33.3%, contributing to a cumulative percentage of net attributable income of 123%, a change from 149% in the previous semester. As outreach grows, a slight decrease in NAIC percentage is expected as the innovations reach more households further along the spectrum of innovation diffusion, as these households tend to have less capital and skill than early adopters of innovations.

Meanwhile,  the net attributable income increased by 4.65% per household this semester, from IDR3.49 million the previous semester to IDR3.65 million per household. The total NAIC for this semester from all PRISMA beneficiary farming households amounted to IDR253 billion, bringing the cumulative NAIC to IDR9.27 trillion or approximately AUD927 million. These figures demonstrate the continuous positive impact and progress generated by PRISMA’s interventions.

Intermediary Outcomes

PRISMA has 3 intermediary outcomes. The intermediary outcomes do not have individual targets but collectively contribute to the program achievement of the end-of-program outcomes.

Progress towards intermediate outcome 1: Targeted farming households achieve greater access to and improved use of new services, inputs, and technologies supplied by private sector partners and their intermediate agents or service providers, such as retailers, traders, and brokers.

Greater access and improved use refer to the number of farming households that received and used new services, inputs, and technologies attributed to a PRISMA intervention (for example, high-quality rice or maize seeds, fertilisers, pig breeding or cattle health services).

This semester, 72,912 farming households accessed and used new products and services, bringing the cumulative total to 2,741,236 smallholder farming households. The new services, inputs and technologies have been provided by 273 private and public sector partners and 15,107 intermediary service providers, including agri-kiosks and traders.

Around 18,467 smallholder farming households involved in the rice and maize sectors have reduced their production costs by using combine harvester machinery services offered by PRISMA’s partners and service providers. This was achieved through partners scaling up their online and offline marketing activities and offering machinery services in new areas. To date, partnerships with 11 machinery service providers have benefitted 69,960 rice and maize smallholder farmers in East Java, Central Java, NTT, NTB and 4 other provinces beyond PRISMA’s working areas.

Progress towards intermediate outcome 2: An expanded pool of private sector actors systematically target smallholder farming households in their business growth strategies and increase their profit.

During the reporting semester, PRISMA identified 95 intermediary service providers serving smallholder farmers, including agri-kiosks and traders, new services, inputs, and technologies, bringing the cumulative number of intermediary service providers to 15,107. As a strong indication of systemic change, 2 competing agribusinesses started copying innovations introduced by PRISMA’s partners in the rice and vegetables sectors. In addition, 6 other businesses responded to the growing opportunities in the soil treatment sector.

Overall, 273 partners (including 91 government and public agencies) invested nearly AUD35.1 million, resulting in a turnover of AUD146 million. This signifies high demand from smallholder farmers and a willingness of agribusinesses to tap into this potential market.

In the dairy sector, CV Sinar Mentari Indonesia (SMG), a cattle feed producer, continued to collaborate with other stakeholders, including pharmaceutical and dairy processing companies. The collaboration aims to conduct farmers' meetings to promote and educate cattle farmers on the benefits of quality cattle feed and animal health products. During this semester, the company organised farmers’ meetings in Boyolali, Malang, Ponorogo, and Pasuruan districts in Central and East Java. Due to PRISMA’s intervention, SMG is also aware of behavioural differences between men and women farmers and has adjusted its training schedules and message delivery to effectively reach both men and women farmers with its product information.

Progress towards intermediate outcome 3: Selected decision makers and policy influencers are equipped with evidence to influence changes in the Indonesian business-enabling environment at national and local levels.

During the reporting period, PRISMA was involved in 48 policy initiatives that used evidence from its interventions to inform and influence key decision-makers and stakeholders.

At the national level, PRISMA made notable progress in supporting the development of the 2025-2029 National Medium-Term Development Plan (RPJMN). PRISMA has handed over the background paper on agriculture modernisation and resilience in Indonesia. It also conducted a focus group discussion (FGD) with related directorates in Bappenas and the Ministry of Agriculture (MoA) to develop and hand over the final indicators for the background document. PRISMA also conducted an MSD training for participants from Bappenas, the MoA, Bappeda in Central Java, NTT, and NTB provinces, the Sumenep District Food Security and Agriculture Service, the Manokwari District Village Community Empowerment Service, the Bogor Agricultural Institute, Gadjah Mada University, Brawijaya University, and Nahdlatul Wathan University.

At the sub-national level, PRISMA engaged in initiatives across various sectors, including beef, maize, mechanisation, information and communications technology (ICT), dairy, mungbean, soil treatment, vegetable, and pig, to enhance local rules, regulations, and practices. Additionally, PRISMA continued to influence key stakeholders, informing them on inclusive business practices and contributing to the development of national guidelines. The engagement with Bappenas remained strong, as evidenced by regular meetings, showcasing PRISMA's achievements and garnering support for its activities.

Artificial insemination (AI) technology has become crucial to ensure pig restocking and recovery of smallholder farming households in NTT. PRISMA has collaborated with the Kupang Animal Husbandry Training Center (BBPP) under the MoA, the Agricultural Human Resources Extension and Development Agency under the MoA (BPPSDMP), associations, universities, and experts, and developed a curriculum for pig inseminator training and competency standards for the inseminators. The curriculum was approved and signed by the head of the BPPSDMP on 30 May 2024.

More detailed information is available in Section 2.3.1.

Other Key Performance Indicators

Other key performance indicators demonstrate progress in achieving scale, sustainability, and inclusion in PRISMA's commodity and livestock sectors. Details of the progress against the KPIs can be found in Annex 2 and are summarised in the following table:

| KPI Indicators |  | Actual Y24S1 |  | Actual up to June 2024 |
| --- | --- | --- | --- | --- |
| KPI1 | Number of farming households (HHs) that increase their income due to PRISMA Interventions |  | 26,993 | 1,482,778 |
| KPI1a | Number of farming HHs in extreme poverty (under USD2.50 PPP poverty line) with increased net incomes |  | 10,774 | 544,273 |
| KPI1b | Number of farm HHs under the USD5.50 PPP poverty line with increased net incomes |  | 17,921 | 917,317 |
| KPI2 | Net attributable additional income for all targeted farming HHs in IDR |  | 253,311,724,783 (AUD25,331,172) | 9,272,502,348,907 (AUD927,250,234) |
| KPI2a | Net attributable additional incomes of farming HHs in extreme poverty (USD2.50 PPP poverty line) in IDR |  | 96,562,163,086 (AUD9,656,216) | 3,606,938,014,397 (AUD360,693,801) |
| KPI2b | Net attributable additional incomes of farming HHs under the USD5.50PPP poverty line in IDR |  | 154,773,067,954 (AUD15,477,306) | 5,909,706,773,692 (AUD590,970,677) |
| KPI3 | Number of intermediary service providers (ISPs) providing farmers with additional/improved access to innovation |  | 95 | 15,107 |
| KPI4 | WEE effectiveness within PRISMA innovations |  | 1.59 | 0.79 |
| KPI5 | Value of additional turnover of ISPs in IDR |  | 193,729,701,837 (AUD19,372,970) | 2,456,760,896,778 (AUD245,676,089) |
| KPI6 | Number of intervention partners (private and public sectors) |  | 0 | 273 |
| KPI7 | Value of additional turnover of private sector partners (PSPs) in IDR |  | 144,440,470,786 (AUD14,444,047) | 1,456,329,937,487 (AUD145,632,993) |
| KPI8 | Value of attributable additional and/or more inclusive investment by public and private sector partners, ISPs, and farmers in IDR |  | 245,802,293,640 (AUD24,580,229) | 3,055,437,706,949 (AUD305,543,770) |
| KPI8x | Value of attributable additional and/or more inclusive investment by public and private partners in IDR |  | 21,246,258,063 (AUD2,124,625) | 351,117,659,084 (AUD35,111,765) |
| KPI8y | Value of attributable additional and/or more inclusive investment by ISPs in IDR |  | 141,188,240,747 (AUD14,118,824) | 802,128,192,516 (AUD80,212,819) |
| KPI9 | Number of crowding-in businesses/institutions induced by PRISMA-2 |  | 2 | 105 |
| KPI10 | Number of responding businesses/institutions induced by PRISMA-2 |  | 6 | 108 |
| KPI11 | Number of policy engagements |  | 48 | 170 |
| Access | Number of farming HHs that gain access to or information on the innovations from AIP-Rural |  | 72,977 | 4,002,090 |
| User | Number of farming HHs that adopt/use information from the innovations introduced by AIP-Rural | 72,912 |  | 2,741,236 |

Value for Money

PRISMA continues to deliver good value for money (VFM), with all 3 VFM indicators remaining strong.  Two indicators remained relatively constant compared to previous semesters, and a third continued to grow steadily. At this late stage of implementation, changes in most sector-level VFM indicators also tend to be modest, especially for sectors with high outreach.

The following VFM indicators are used to show the program's effectiveness in terms of delivery and its return on investment:

Reflects buy-in from the private sector to adopt and fund the innovations introduced through PRISMA

Reflects how effective PRISMA is in generating net-income increases for households

Reflects how efficient PRISMA is in scaling innovations

- Figure 1 Value for Money Indicators

Investment leverage (private partners, ISPs, and farmers): PRISMA’s investment leverage is 3.13, which has grown at a compound annual growth rate of 11% since 2019. This means the private sector invests 3.13 dollars for every dollar invested by PRISMA.  As of June 2024, PRISMA had generated AUD306 million in private-sector investment.

This semester’s increase in investment leverage was mainly driven by higher investments, primarily in the beef sector (AUD8.72 million) and the pig sector (AUD3.5 million). Both sectors provided exciting opportunities, with KJUB Puspetasari in Java and Sierad Produce in NTT. Both sectors gained additional farmers' investments from continuing partner business after the partnership with PRISMA ended.

Figure 2. Investment leverage (private partners, ISPs, and farmers)

Social return on investment (SROI): There was a minor decrease in SROI, bringing it to 9.49 this semester, lower than the last 3 semesters. PRISMA’s SROI appears to have plateaued with an average of 9.58 over the past 4 semesters. This is 68% higher than the next highest SROI (5.69 in semester 1 of 2022). The SROI is the ratio of the actual value of additional money farming households are getting against PRISMA’s total intervention costs. In other words, for every dollar PRISMA spends on an intervention, farmers will have a 9.58 dollar increase in net income.

This semester’s slight decrease was driven by the lower increase in net income (AUD25.3 million) compared to the previous semester (AUD 68.9 million in semester 3 of 2023) because PRISMA has ended its implementations since December 2023. However, we can see that the mechanization and mung bean sectors can provide higher SROI than last semester. The mechanization made a 27% higher SROI of 4.35 compared to 3.43 in the last semester (semester 2 of 2023). Meanwhile, the mung bean sector gained a slightly higher SROI of 31% (SROI 9.81) compared to 7.51 in the last semester (semester 2 of 2023).

From the mechanization sector, we get additional beneficiaries from partnerships with PT Rutan, Pilar Agri, and Galaxy, increasing the overall net income. In the mung bean sector, the partnership with CV Bunga Tani Sejahtera netting additional income increase from its beneficiaries.

Figure 3. Social return on investment

Investment per farming household: This indicator also remained relatively constant, with investment per farming household at AUD65.91 this semester and an average of AUD65.2 over the past four semesters. This is 35% lower than the next lowest (AUD101.1 in semester 1 of 2022). A lower figure indicates that PRISMA’s interventions are becoming more efficient in delivering returns to farmers.

In Phase 1, PRISMA needed to invest an average of AUD690 to benefit one farming household, with a peak reaching AUD1,300 in S2 of 2014. Initially, when companies were unfamiliar with PRISMA and its approach, PRISMA had to invest more funds to convince partners to work with the program. At that time, PRISMA mainly conducted small-scale pilot activities with limited outreach. As PRISMA began demonstrating positive results from its interventions and gained experience in the most efficient ways to reach farmers (for example, what promotional channels to use and what types of messaging work best), it became easier to attract new partners and scale up proven innovations. This led to a reduction of PRISMA’s contributions to partnership costs and exponential growth in outreach as partners began scaling up business models and copying innovations in new areas. As a result, PRISMA has significantly lowered its investment per farming household over time, achieving greater outreach for every dollar it spends.

Figure 4. Investment per farming household

- The direct intervention costs can be found in Annex 2: Detailed key performance indicators.

Collaborations

Collaboration facilitates the efficient allocation of resources, enabling the seizure of opportunities that may be beyond the reach of any single organisation. This semester, PRISMA collaborated with a DFAT program, the World Bank, and the Partnership for Indonesia's Sustainable Agriculture (PISAgro).

Australia Indonesia Partnership for Economic Development (Prospera)

Since 2023, PRISMA has collaborated with Prospera to engage the Indonesian Financial Service Authority (OJK) and share insights from PRISMA’s agri-kiosk survey. Leveraging Prospera's experience with OJK, the 2 programs worked together to establish a pathway for promoting flexible loans to agri-SMEs. Prospera analysed the data shared by PRISMA from the agri-kiosk survey to generate insights for OJK and offer recommendations for financial inclusion and related policies.

This semester, PRISMA has built on this collaboration by sharing data and insights on agri-SMEs' access to financing, covering both current access to finance and behaviours in obtaining financial services. PRISMA is currently developing an agri-SMEs policy brief and market brief, which will be shared through Prospera’s network, including the Coordinating Ministry for Economic Affairs and OJK, upon approval from DFAT.

The World Bank

PRISMA collaborated with the World Bank to host a national workshop, “Climate-Smart Agriculture: Increasing the Productivity, Resilience, and Sustainability of Indonesian Agriculture,” with the MoA and Bappenas. Held on 19-20 June 2024, this event gathered insights from various stakeholders and showcased climate mitigation efforts from PRISMA's private sector partners. Combining resources, networks, and logistical support with the World Bank helped PRISMA reach a broader audience in a cost-effective way, World Bank covered the venue and organised the agenda and international participants and PRISMA supported the promotion of the event, the media and an exhibition. See Chapter 3 for more information about the event.

Partnership for Indonesia's Sustainable Agriculture (PISAgro) 
PRISMA continued collaborating with PISAgro to promote women-inclusive business practices within the agricultural sector. PRISMA led initiatives within the beef and dairy sector working groups and participated in broader efforts. This semester, a seminar with the theme “Empowering Women in the Agriculture Sector – Opportunities for Business” was held to showcase practical strategies for businesses to adjust their promotional approaches to enhance accessibility for women farmers.  Post-event, PRISMA disseminated female sales agents' research findings as well as an agribusiness guideline for establishing inclusive sales, marketing, and outreach strategies.

Challenges, Responses, and Learnings

Working in dynamic and evolving agriculture markets presents a unique set of challenges. PRISMA remains proactive in its response, and its learnings help the program evolve and improve.

| Challenge | Response | Learning |
| --- | --- | --- |
| Sector (for more sector challenges and learnings, see updates in Annex 1) |  |  |
| Overcoming data collection delays and sharing learning |  |  |
| The maize and cattle sectors experienced a setback in deriving and sharing learning. The data collection and analysis of the maize smart subsidy initiative were delayed due to overlapping national holidays and religious events in April and May 2024. The leadership transition in the Sumenep Food Security and Agriculture Agency (DKPP) in March 2024 further complicated the data collection process. In the cattle sector, data collection for a policy brief to support the NTT government in developing an enabling environment for private sector investment was hampered by the limited field data collection time and the complexity of coordinating with multiple stakeholders. | PRISMA responded by working closely with a think tank, the Center for Indonesian Policy Studies (CIPS) and ensuring the timely completion of data analysis by June 2024. This allowed PRISMA to present the study results and the smart subsidy good practice outline at an FGD event, followed by the publication and dissemination of the smart subsidy policy brief. PRISMA triangulated data and enriched findings through multi-stakeholder FGDs and conducted intensive coordination with the NTT Regional Development Planning, Research, and Innovation Agency (Bapperida), local government technical offices, and other private actors to optimise data processing and insight analysis in the cattle sector. | Systematic data management and proactive stakeholder engagement are key to deriving meaningful learning. Flexibility in adjusting schedules to the local context is crucial for accommodating unforeseen challenges such as leadership transition. |
| Across the program |  |  |
| Managing staff transition and retention |  |  |
| With the program scheduled to end in 2024, several experienced staff members have begun pursuing more secure employment opportunities. The relocation of some staff from Surabaya to the Jakarta office has posed challenges and required considerable time to adjust to new practices and workflows. | PRISMA implemented a calibrated and transparent performance appraisal system correlated with salary increments and has engaged several short-term advisors for specialised activities to replace natural turnover as the program concludes. PRISMA also established regular check-ins and support mechanisms to maintain staff well-being and productivity during the transition period. | With careful planning, effective transition management, and a robust support system, logistical and staff transition challenges can be significantly eased, even within tight timeframes. |

Risk Matrix

PRISMA’s risk matrix is provided as a separate document.

Final Year Focus

Systemic Change and Sustainability

An enduring commitment to sustainability

PRISMA is committed to promoting systemic change and sustainability through its MSD approach to development. This approach focuses on understanding how key actors perform functions in a market system and how these functions can be improved and sustained after development assistance ends.

To achieve this goal, PRISMA identifies barriers to growth and works with both the private and public sectors to modify their behaviour, address these barriers, and encourage investment in business models that benefit smallholder farmers. By smoothing the way for businesses to operate and grow, PRISMA ensures the sustainability of its interventions.

This approach to sustainability operates at 3 levels:

Level 1: The program aims to ensure that innovations and investments are sustainable. Partners adopt or adapt the innovations or business models at the intervention level. Sustainability is achieved when the innovation brings tangible benefits to farming households and generates a commercial return for private sector partners.

Level 2: The program also aims to build on initial innovations to strengthen sector adaptability and resilience. At the sector level, partners focusing on different market functions (agricultural products and services) should be able to respond to opportunities or threats. New competitors may start adopting PRISMA's business models or taking advantage of the growing opportunities in the sector.

Level 3: The program seeks to influence policy and institutional behaviour, either directly or through influencing the influencers. At the policy level and in academia, PRISMA's initiatives are expected to bring about positive and tangible changes in the way the public sector operates and strengthens university content and teaching. This will create a more enabling environment for private sector-led agricultural growth.

Final year focus

Building on its success, PRISMA, in its final year, aims to influence the market with its know-how and expertise. The eleventh year was an extension granted by DFAT in recognition of the opportunity to share the PRISMA experience more widely. The program for the final year split sustainability targets into sector-level activities (market resilience) and policy- and academic-institution-focused activities (high-priority policy initiatives).

Resilience activities spanned 12 sectors, bolstering market actors' ability to navigate market stress and uncertainties. These included activities and events for building private and public sector capacities, enhancing market functions critical for sector performance, and institutionalizing essential functions like research and marketing. Twenty-seven events were held, reaching more than 2.5 million people and influencing more than 2,500 people face-to-face.

The high-priority policy initiatives targeted policy and institutional behaviour changes to foster a more conducive environment for private sector-led agricultural growth. These initiatives build on PRISMA efforts to foster a more enabling business environment in key sectors and national and regional agricultural planning.

Market resilience activities

Resilience means that PRISMA's innovations continue to thrive despite market stress and uncertainty. Each activity aims to address a gap or opportunity that, when strengthened, will ensure the sustainability of PRISMA’s interventions.

During this reporting period, resilience activities occurred across 12 active sectors to enhance market actors’ ability to withstand shocks, respond to unexpected threats, and maintain business operations under stressful conditions.

These activities can be broadly categorized as:

Exit Strategies

| Strategies towards ensuring greater sustainability |  | - Improving the private and public sectors' institutional capacity to sustain the changed behaviour without PRISMA's support. - Improving selected market functions that are critical to improving sector performance. - Institutionalising critical functions, such as research and marketing activities in untapped areas. |
| --- | --- | --- |
| Example: | Strategic focus | Enhancing a critical market function to improve sector performance. |
| Spurring production and promotion of pioneering climate-smart seeds | Challenge | Climate change poses a significant threat to rice production, rendering the sector vulnerable. As the impacts of climate change intensify, it becomes increasingly vital to enhance farmers' adoption and supply of high-yielding seed varieties (HYV). |
|  | Opportunity | Promoting the production and adoption of HYV will contribute to an improvement in sector performance. |
|  | Activity | PRISMA supported the promotion of the Institut Pertanian Bogor’s (IPB University) agribusiness and rice seed producer PT Botani's pioneering, HYV and climate-smart seed. The IPB 9G variety is specifically designed to withstand varying climate conditions, providing farmers with a dependable solution to enhance crop yields and ensure food security. The IPB 9G was officially launched at an event in Lamongan, Central Java, with endorsement from the Minister of Agriculture and the IPB Rector. The Minister actively promoted the seeds, advocated for their widespread adoption, and called for increased production. |
|  | Outreach | The event was well-attended by hundreds of farmers, agribusinesses, universities, and government officials and garnered media coverage. |
| Knowledge harvesting and dissemination |  | - Harvesting knowledge and best practices to inform non-partners and policymakers. - Promoting best practices among market actors to induce replication of behaviour changes. |
| Example: | Market resilience activity | To endorse and promote successful indigenous-inclusive approaches and learnings to stakeholders that will foster replication across Tanah Papua. |
| Catalysing off-taker business models that benefit young indigenous entrepreneurs and farmers | Challenge | The quantity of vegetables produced in Tanah Papua is less than half of the 180,000 tonnes total demand. The large supply-demand gap can be attributed to several factors, including farmers’ suboptimal yields from using low-quality inputs and a lack of off-takers. These challenges are particularly pronounced in indigenous communities. |
|  | Opportunity | PRISMA has experience working with the indigenous off-taker Anggi Mart in developing its business, with some early signs of impact. This semester, PRISMA collaborated with the Papua Youth Creative Hub (PYCH), an organization of young indigenous Papuan entrepreneurs, to hold the Youthpreneur Summit in Manokwari. The event provided a platform for participants from 4 provinces in Tanah Papua to exchange ideas on how to manage vegetable businesses effectively. |
|  | Result | Following the event, 5 out of 6 participants promptly adopted the inclusive business model. Among them, 3 individuals from Biak, Jayawijaya, and Teluk Wondama initiated their vegetable businesses. Challenges: As the event participants are still in the early stages of their business, providing continuous mentorship would be beneficial to ensure sustainable replication and scalability. |
| Policy initiatives |  | - Capturing and sharing field evidence with policymakers to improve the business-enabling environment. - Supporting selected government agencies to improve their capacity, rules, and regulations. |

More details about each sector’s market resilience activities can be found in ANNEX 1: Progress Against the Annual Workplan.

3.3.1 High-priority policy initiatives

Building on the success of its 10-year MSD program in Indonesia, PRISMA is focusing on 8 high priority policy initiatives (HPPI) in its final year to ensure better sustainability. These initiatives cover sector-specific policies (beef, dairy, maize, and pig), national and regional government policy planning processes, and embedding the MSD approach in government institutions and universities’ academic programs.

These initiatives build on existing PRISMA efforts to foster a more enabling business environment in key sectors and national and regional agricultural planning. They also involve new initiatives to influence governments and universities to incorporate PRISMA's proven approach into their policies and programs. Each initiative aims to make transformational changes (new processes, practices, regulations) or improve capacity within key partner institutions.

Significant progress has been made in implementing the 8 HPPIs. The HPPIs deliverables summary graph shows that 64% of deliverables have been completed, 24% are currently in progress, and 12% will start in S2 2024.

Completed   Ongoing   Starting in S2 2024

The initiative to embed MSD through training government officials and university lecturers has been completed, and the beef national standard (SNI) initiative is 90% complete. All other HPPIs, except for the NTT Regional Medium-Term Development Planning (RPJMD) initiative and the initiative to incorporate PRISMA’s experience into university programs and create an online repository of PRISMA’s knowledge and lessons, are at least 60%

complete.  All remaining initiatives are anticipated to be completed by October 2024. Ongoing deliverables mainly involve the completion of guidelines, studies, or policy briefs (for example, the maize subsidy guidelines for Sumenep, the maize smart subsidy study and policy briefs, thematic studies and policy briefs for the RPJMN, and the final report with the RPJMD-NTT recommendations). In terms of university initiatives, Feed University is currently harvesting lessons from climate-smart trials to finalise its climate-smart protocols. The University of Nahdlatul Wathan Mataram is finalising the new agri-tech business curriculum and plans to launch the program in August 2024. Deliverables that have yet to be started mainly involve socialisation or launch events,   which can only happen once the ongoing deliverables have been completed.

More details about each HPPI can be found in Annex 2: High Priority Policy Initiatives.

Semester highlight

Market Systems Development Training in Surabaya, 3 – 7 June 2024
Bappenas and MoA representatives came to Surabaya for a one-week course on PRISMA’s approach to problem-solving and systemic change. The course left participants with a greater understanding of the principles that underpin PRISMA’s work and helped to ensure that the progress made to date will continue to be supported.

With PRISMA's support, we are currently developing a curriculum and learning materials based on the market systems development approach that we will launch in the upcoming semester.

Alimuddin, Nadhlatul Wathan University

Following the training, we plan to hold discussions with the Regional Development Planning Agency and relevant technical offices on how to implement the market systems development approach in a regional context.

Jeffry Jacob Sahuburua, Office for Community Development of Manokwari, West Papua

The market systems development approach that we learnt about in the training will enrich the analysis of our main responsibilities and functions at the policy-making level.

Agung Saras Sri Raharjo, Center for Social Economics and Agricultural Policy, Indonesian Ministry of Agriculture

Semester Highlight

2025 – 2029 NTT RPJMD discussions, Kupang, 16 May 2024

PRISMA is supporting the NTT government to develop a background study on the agricultural sector to inform its upcoming RPJMD policy planning process. PRISMA is supporting an evidence-based approach to policymaking with FGDs and other evidence and data gathering activities.

PRISMA’s support in creating the digital map to identify production centres will undoubtedly assist the NTT provincial government in formulating future policies.

Theresia Maria Florence, Head of Economy and Natural Resources, NTT Regional Development Planning, Research, and Innovation Agency (Bapperida)

Private sector view of PRISMA policy support to the MoA on good animal feed practices

PRISMA collaborated with the MoA to enhance smallholder farmers' access to quality animal feed. Feed Directorate MoA, with support from PRISMA,  held an event providing technical guidance to micro, small, medium-sized enterprise (MSME) feed producers on good feed manufacturing practices, national feed standards with a grading system, and the feed registry numbering.

We are very appreciative of this knowledge-sharing event on implementing good feed processing practices in our business.

Juani (right), Head of Agribusiness Cooperative (KAN) in Jabung, Malang

MoA recognition for better feed, brighter futures

PRISMA’s game-changing support to MoA to revise the animal feed standards was recognised at an event this semester. The Director of Feed at MoA presented PRISMA with a plaque to thank the program for its impactful support. The event was part of an MoA/PRISMA training assisting MSME feed producers, that often struggle to access information about regulations leading to regulatory violations and unsafe feed on the market. To bridge this gap, PRISMA and MoA provide technical guidance to MSME feed producers to ensure MSMEs can meet industry requirements and supply quality and affordable animal feed to smallholder farmers.

The training covered feed registration, identifying critical points in testing for feed registration, good feed manufacturing practices, and the CPPB business licensing system. From the feedback survey, 83.3% of the participants found that the Bimtek training was helpful for their work, and 70.2% felt more confident in facilitating their company's feed registration process after the training. As many as 40.5% of the participating MSMEs planned to register for CPPB, SNI, and NPP using the knowledge from the training.

This work, and the policy support that came before it, were appreciated by the MoA

“

.

We created the SNI grading system to enhance MSMEs’ competitiveness. Now, MSMEs have a better opportunity to compete fairly, even with large companies.

drh. Nur Saptahidhayat, Director of Feed at the Ministry of Agriculture.

Cross-cutting Area Progress

The progress data is derived from impact assessments of interventions in semester 2, 2023, and previous interventions that continued into semester 1, 2024. Most of PRISMA’s interventions ceased in December 2023 to concentrate on market resilience and ensure the sustainability of climate, GEDSI, and policy outcomes supported by strategic communications.

Climate-smart Agriculture

Achieving increased incomes for smallholder farmers while adapting to climate change and reducing greenhouse gas (GHG) emissions has become increasingly critical. PRISMA has demonstrated how the private sector can successfully invest in and contribute to a climate-resilient agriculture system by offering climate-resilient inputs and educating farmers on climate-smart agriculture practices.

During this semester, 24,715 smallholder farmers contributed to reducing 2,424 tonnes of carbon dioxide equivalent (CO2e) by adopting concentrated feed for beef cattle, hybrid rice seed, and mineral fertiliser. To date, PRISMA has contributed to a total emission reduction of 137,132 tonnes of CO2e attributed to 2,027,180 individual farmers.

This total reduction is equivalent to the consumption of 1,353,384 motorcycles running on gasoline for a month or the combined electricity and fuel consumption of 1,920 households for a month.

| Sector | Attributable emission reduction (kg of CO2e per household per cycle) | Total attributable emission reduction (tonnes of CO2e) |
| --- | --- | --- |
| Beef | East and Central Java: 101 West Nusa Tenggara: 85.5 | 64,045 |
| Rice | Hybrid: 95.2 New inbreed: 32.8 | 10,786 |
| Maize | Hybrid: 73.6 | 26,050 |
| Other crops | 47.6 | 31,921 |

These figures were derived from 2 sources. The first source was the reduced and efficient use of nitrogen-based fertiliser in rice, maize, and other crops. The second source came from the cattle sector, where increased uptake of concentrated feed in cattle feeding practices has led to shorter cattle rearing cycles, reducing methane equivalent carbon dioxide emissions.

The reduction in emissions from farming activities is attributed to farmers who have adopted innovations introduced by PRISMA’s partners, compared to emissions emitted by farmers who have not adopted climate-smart agriculture practices. The total emission reduction is a conservative estimate as it captures emissions reduced by farmers for one agriculture season or cycle only.

Market resilience activity

Together with the World Bank, PRISMA supported a MoA and Bappenas event, "Climate-Smart Agriculture for Productivity, Resilience, and Sustainability of Indonesian Agriculture," in Jakarta on 19-20 June 2024. The workshop included expert presentations, panel sessions, and interactive discussions focused on scaling up climate-smart agricultural practices, facilitating an exchange of knowledge and innovation to inform agricultural planning and policymaking in Indonesia.

PRISMA's business partners involved in critical agricultural commodities, such as rice, maize, cattle, and fertilizer, shared their latest innovations and ideas at the event. PRISMA also held a press conference to support its partners in sharing innovations with journalists, resulting in 31 media articles.

This workshop addressed various important aspects of climate-smart agriculture that could be integrated into the RPJMN, the MoA’s strategic plan, and the RPJMD. This will require synergy and contributions from all those involved.

Dr. Vivi Yulaswati, MSc. Deputy for Maritime Affairs and Natural Resources, BAPPENAS

Gender Equality, Disability, and Social Inclusion

# PRISMA works with its partners to adopt inclusive business models to create opportunities to support gender equality, people with disabilities, youth, and Indigenous people.

3.2.1 Gender equality

## Impact on women’s economic empowerment dimensions

Women continue to experience positive changes across all 6 dimensions due to the agricultural inputs and services offered by PRISMA’s partners. During this semester, PRISMA conducted WEE impact assessments with 104 women respondents from the dairy, beef, and mechanisation sectors, cumulatively reaching 2,422 women respondents across 12 sectors since 2020. All 3 sectors assessed during this semester showed low involvement of women in agricultural activities (for example, beef and dairy feed and combine harvester services) targeted by PRISMA’s partners. Considering the relatively low number of respondents in these assessments, there was no significant change to the WEE score from the last reporting period.

PRISMA measures impact on women across 6 WEE dimensions: (1) access to products and services, (2) access to knowledge and skills, (3) economic advancement, (4) manageable workload, (5) decision-making, and (6) greater agency in leadership and social networks. The section below provides the cumulative score from the WEE assessments conducted since the beginning of the reporting period (second semester of 2020).

As such, 43% of the women respondents experienced better access to agricultural inputs and services offered by PRISMA’s partners.

‘Now it's getting easier to use the combine harvester service, which is really helpful, especially with the current labour shortage.’ - A woman rice farmer who uses a combine harvester service in Lamongan, East Java.

Meanwhile, 31% of the women respondents confirmed their improved knowledge and skills in farming practices after participating in promotional and educational activities conducted by PRISMA’s partners.

‘I learned about correct feeding practices and proper feeding measurements and experimented on my own to find the most suitable measurements.’ - A woman dairy farmer in Kediri, East Java.

Additionally, 59% of the women enjoyed economic advancement either as farmers or as members of farming households that adopted innovations promoted by PRISMA's partners.

By cutting down on harvesting expenses, we have boosted our income. And our income increases further if selling prices are high. We use this extra money for farming investments and household needs.’ – A woman rice farmer in Blora, Central Java.

Around 28% of women experienced increased decision-making in agriculture after gaining knowledge through farmers' meetings and other engagements from the agribusinesses.

I actively participate in the decision-making process for feed selection because I manage the finances and want to increase milk production, even if it means using slightly more expensive feed products.’ - A woman dairy farmer in Kediri, East Java

Women respondents (32%) also experienced a more manageable workload as a result of adopting innovations induced by PRISMA. While 11% reported increased workload because of increased farm productivity, they found it manageable as it only occurred during specific periods, such as the harvesting season.

‘[Since using concentrated feed], I now have more time to focus on other tasks, including household chores, as I spend less time searching for feed [foraging].’ - A woman beef cattle farmer in Central Lombok, NTB.

Finally, 24% of women respondents experienced better social connection and networking within their communities through participating in knowledge-enhancing activities offered by PRISMA’s partners and sharing their own experiences with other community members.

‘I share my experience using this feed [promoted by a PRISMA partner] with my neighbours who haven't tried it yet, hoping that it will also help improve their cattle milk production.’ - A woman dairy farmer in Kediri, East Java.

The table below shows the cumulative findings.

Table: Cumulative WEE impact assessment findings

| WEE dimension | Remarks |
| --- | --- |
| Access to products and services | 43% Women respondents adopted the innovation more easily due to the increased availability and accessibility of products or services in the neighbourhood. |
| Access to skills and knowledge | 31% Women respondents found the knowledge gained from participating in gender-inclusive and women-targeted activities was beneficial for improving their agricultural skills. |
| Economic advancement | 59% Due to higher yields and better-quality crops, women respondents had more opportunities to increase their savings and investments or fulfil family needs. |
| Manageable workload | 32% Women respondents experienced a more manageable workload as a result of adopting innovations induced by PRISMA. |
| Decision making | 28% Women respondents were more involved in agriculture decision-making as they gained better access to information on better-quality inputs, services, and good agricultural practices. |
| Leadership and social networks | 24% Women respondents were able to expand their social network within their communities. |

Knowledge harvesting and dissemination

#### Guideline for understanding and mitigating gender-based violence (GBV) risks

PRISMA has revised the GBV guidelines draft by incorporating feedback from DFAT. A GBV expert developed the guideline following a field assessment and in-depth discussions with women and men farmers, kiosk owners, field staff and management of 2 partner companies in 4 districts in Central and East Java during the last semester. After discussions with DFAT, PRISMA will conduct a workshop for interested private sector partners to orient them on the basics of gender-based violence in agriculture, mitigation and response strategies.

#### Report on understanding gender dynamics in kiosk management

#### PRISMA has finalised the report on understanding gender dynamics within kiosks and the potential commercial implications. Through a gender lens, this research demystified the roles and responsibilities of the agricultural kiosk as indispensable parts in farming communities. The research also identified overlooked business opportunities to help agri-businesses design cost-effective outreach, marketing, and extension activities. PRISMA will share the Indonesian version of the document with its private sector partners via email and during relevant workshops organised by different sector teams.

#### Research on return on investment in women-inclusive business practices

#### PRISMA has commissioned Daya Makara - University of Indonesia (DM-UI) to conduct research on women-inclusive return on investment (WI-ROI). The research aims to determine if private sector partners experience a positive return on their investment by trialling or adopting women-inclusive business practices, such as holding women farmers’ meetings. The research will survey 2 companies from the maize and dairy sectors and cover in-depth interviews, FGDs, and surveys with representatives from the companies, farmers, and company field agents. The research findings will be finalised in August and published on the website upon DFAT's approval.

#### National seminar on women-inclusive business practices in agriculture

#### Commemorating International Women’s Day, PRISMA conducted a business seminar, “Empowering women in agriculture – opportunities for business”, in Jakarta on 7 March. Eighty-seven participants from the private sector, development organisations, and women farmers attended the event. In collaboration with Partnership for Indonesia’s Sustainable Agriculture (PISAgro), the seminar focused on addressing the pivotal role of women in agriculture, both as customers and as staff.

#### Keynote presentations from the National Research and Innovation Agency (BRIN) and PRISMA highlighted the critical role of women in agriculture and business growth through adopting women-inclusive business practices. The event was also enriched with a panel discussion with 5 panellists from PRISMA’s partners and a farmer, Ibu Lasmi, representing her farmer's group, which had benefited from a loan from PRISMA partner and finance institution, Pemodalan Nasional Madani (PNM). PISAgro’s members and farmer representatives also shared their experiences in implementing women-inclusive activities. In addition, 2 women farmers shared their journey in agriculture and how they have been empowered through women-inclusive activities implemented by the private sector.

#### PRISMA organised for agribusiness journalists to attend the event to cover and promote inclusive business practices. The event was profiled in 4 media outlets. Palladium’s Co-CEOs also attended the event, which was profiled on Palladium’s social media channels, promoting PRISMA’s inclusive business practices to a global development audience.

Research for mungbean seed producers to increase their business performance by reaching more women farmers

PRISMA conducted a survey to explore women's participation in mungbean cultivation, the barriers they face in accessing information on mungbean seed, and their preferences for attending educational or promotional activities. Based on the findings, PRISMA developed a market brief with recommendations for mungbean seed companies on how to effectively engage women farmers in marketing and educational activities. PRISMA presented the findings and shared the market brief during a discussion forum organised jointly by PRISMA’s mungbean team and the Directorate of Food Crop under the MoA in Semarang, Central Java.

Study on a direct sales agent model using a gender lens in the crop protection sector

PRISMA conducted another study in the crop protection sector with the objective of improving the direct sales agent model using a gender-based approach. The initial findings suggest that the sales agent model could be more effective by considering the different needs and strengths of women and men field agents. Further insights and recommendations will be made, and the results will be disseminated to crop protection companies during a workshop in July.

## Progress towards WEE mainstreaming

# PRISMA measures progress towards WEE mainstreaming in 3 levels: (a) the pre-implementation stage, which demonstrates the willingness of the partners to embed and mainstream WEE within their business activities; (b) the implementation stage with PRISMA, which shows the commitment of the partners; and (c) the sustainability/continuity stage, where partners continue the WEE inclusive activities independent of PRISMA’s support. As PRISMA completed its ‘business as usual’ interventions with its partners by December 2023 and focused only on resilience activities, the previous process of measuring progress towards WEE mainstreaming was not applicable this semester.

# However, PRISMA is conducting a lean survey with a number of previous partners to assess whether they continue WEE inclusive activities promoted by PRISMA and explore the reasons why they continue or not. The study will give further insights into the business viability and continuity of WEE inclusive practices. By the end of the first semester, among the 11 companies interviewed, PRISMA found that 8 of them continued the practices while 3 decided to discontinue. The findings will be presented in the project completion report due in September.

4.2.2 Disability inclusion

## Analysis of disability prevalence

This semester, 17 farmers with disabilities were identified as having benefitted through PRISMA’s interventions. This comparatively low number is due to a low number of field impact assessments conducted during the semester (7 impact assessments and 12 extrapolations). Eleven of the 17 farmers are visually impaired, 2 have hearing impairments, 2 have mobility impairments, and 2 have communication difficulties.

## Progress on disability inclusion

## PRISMA’s disability inclusion strategy is based on 2 strands: (a) accessibility improvement and (b) participation improvement. The emphasis on accessibility improvement is centred on applying universal design (UD) principles across the business activities of PRISMA’s private sector partners. Participation improvement aims to enhance the involvement of farmers with disabilities as a target demographic in partners’ in-person marketing and educational events in the field.

## Progress towards accessibility improvements

Following the previous work with PRISMA in improving accessibility (readability) of its information posters, PT E-Tong Chemical Indonesia, a crop protection products company, has continued applying UD principles. The company has adjusted the display and messaging of its newly developed flipcharts to make them more readable and understandable. Field agronomists use the flipcharts to promote good agricultural practices (GAP) and proper use of agro-chemical products.

In the ICT sector, PRISMA supported 2 partners - Yayasan Bina Tani Sejahtera (YBTS), a foundation under PT East West Seed Indonesia, and PT Mitra Sejahtera Membangun Bangsa (MSMB), an agricultural startup that operates across the entire agricultural supply chain. PRISMA helped them develop a promotional video that incorporates UD principles, including a sign language translator (only for YBTS), embedded subtitles, appropriate size and colour contrast of graphics, and clear narration sound. The partners will disseminate the videos through their respective social media accounts.

## Progress towards increasing participation

PT NuFeed and KJUB Puspetasari, 2 cattle feed companies in the dairy and beef sectors, continued their inclusive business initiatives through commercial collaborations with farmers with disabilities who previously led their demonstration plots. Two dairy farmers with mobility and vision impairments started selling NuFeed feed products. NuFeed also supported them in distribution channel development to enhance their commercial activities. Similarly, KJUB Puspetasari also supported a farmer with a disability to become its field sales agent.

In the maize sector, CV Tani Jaya Sehati, a seed nursery in Manggarai, NTT, piloted its disability-inclusive business model through a partnership with a special school, namely SLB N 1 Borong. The seed nursery was inspired to do so after participating in PRISMA’s disability inclusion workshop in NTT last semester. Supported by PRISMA and its disability inclusion advisor, YAKKUM Rehabilitation Center (PR YAKKUM), the nursery conducted training for the special school teachers on maize seed sortation. The teachers then trained 6 selected students over 18 years with cognitive impairments to learn how to undertake quality maize seed sortation. The success of the pilot encouraged the nursery to continue the partnership with the school and develop a plan to replicate similar initiatives with nearby churches.

Knowledge harvesting and dissemination

#### Disability inclusion workshop – From Awareness to Action: Disability Inclusion in Agribusiness

Following the disability inclusion workshop for NTT-based partners in Kupang last semester, PRISMA organised a second workshop in Jakarta in May. The event targeted agribusinesses, including several members of PISAgro and local organisations of persons with disabilities (OPD). PR YAKKUM facilitated the event, with 58 participants from the private sector, OPDs, NGOs (Mercy Corps, Save The Children, and IBU Foundation), and farmers with disabilities. Personnel from the Australian Embassy’s development program (KATALIS) also attended to learn more about inclusive business practices.

The event started with a panel discussion to provide practical insights and examples of disability-inclusive business approaches in agriculture drawn from PRISMA and its partners' experiences. Following the panel discussion, PR YAKKUM continued with sessions on disability inclusion in agriculture, the opportunities and challenges in implementing disability-inclusive initiatives, the way forward, and networking discussions amongst private sectors and local OPDs. The event promoted PRISMA’s Accessibility Guidelines, created specifically for agribusinesses by PRISMA and PR YAKKUM, with input from farmers with disabilities.

PRISMA partnered with agri-media agency, Agrina, to promote the event and the Accessibity Guidelines to its Indonesian agribusiness audience. Journalists from Agrina attended the event and interviewed animal feed producer and PRISMA partner, Nufeed Director Pak Totok and farmer, Ibu Martini. The story was published in Agrina Magazine. PRISMA shared its own story of the event on the PRISMA News Page. An excerpt of the Nufeed story is below.

#### Sharing PRISMA’s experience with DFAT’s program - Market Development Facility (MDF)

PRISMA participated as a facilitator in an online disability inclusion workshop organised by the Market Development Facility (a multi-country program of DFAT). Nearly 60 staff from different MDF countries attended the workshop, which aimed to promote a better understanding of disability inclusion. PRISMA shared its approach, experience, and learning on disability-inclusive practices in agriculture within the MSD context. This includes improving accessibility and participation of people with disabilities, designing a disability-inclusive business model, and collaborating with disability organisations. The sessions sparked the participants' interest and curiosity, as reflected in their thoughtful questions.

GEDSI spotlight Half of Indonesians with a Disability Work in Agriculture. Here’s What They Need Farmers in Indonesia are ageing. This means the prevalence of disabilities, especially those related to mobility and sensory functions, is increasing. Routine tasks for farmers, such as gathering green fodder to feed their dairy cows in a backyard pen or reading the label on the back of a fertiliser bottle at their local agri-kiosks, become difficult. Martini, one of the participants of Disability Inclusion Workshop, conducted by PRISMA and YAKKUM in Jakarta. This highlights the need for agribusinesses to consider how farmers engage with their products to ensure that farmers with disabilities can continue contributing effectively and maintaining their livelihoods. It also presents an opportunity to consider how all farmers with disabilities, not just ageing farmers, engage with agribusinesses to create more inclusive markets in which everyone can participate. Earlier this year, PRISMA hosted a Petani Maju (Future Farmer) event called "Disability Inclusion in Agribusiness: From Awareness to Action" in Jakarta. The full day of activities gave agribusinesses the opportunity to learn from farmers with disabilities and share best practices for reaching farmers with a disability with products, services, and innovations that can increase their incomes. PRISMA, a partnership between the Government of Indonesia and the Government of Australia which boosts the incomes of smallholder farmers by increasing farm productivity, recently launched the Petani Maju campaign to support productive farmers and strong communities. Farmers with disability often miss out as consumers on products and services that could improve their productivity. This is partly due to agribusiness outreach and product design not being designed with farmers with disabilities in mind and field staff not being aware of the barriers farmers with various disabilities face in accessing product information and services. The campaign helps agribusinesses bridge this gap by researching and targeting different customer segments to support inclusivity. The event, facilitated by Pusat Rehabilitasi YAKKUM, a humanitarian organisation advocating for the rights of people with disabilities, drew participation from a wide group of agribusinesses, including animal feed and fertiliser companies, farmers with disabilities, and organisations for people with disabilities (OPD). Pak Eko Harsono, Director of YAKKUM, emphasised the community's desire for actionable steps guided by their input, following the principle of "nothing about us without us." “The importance of integrating disability inclusion in the agricultural sector cannot be overstated, especially considering that close to 50% of persons with disabilities rely on agriculture for their livelihood,” explains PRISMA Team Leader, Mohasin Kabir. Today, 64% of farmers are over the age of 45 and 39% of farmers over 55 encounter vision, hearing, and mobility impairments. Some challenges are more easily solved, such as applying “universal design principles” to product packaging and marketing. Universal design uses high-contrast colours and clear and large fonts to help farmers with vision impairment to read the product information. This is especially important for getting dosage right for pesticides and fertilisers on critical crops like rice and maize. Other examples include adapting sales outreach. Agribusinesses commonly use local sales agents and supporting agents to reach farmers who may not be able to physically attend farmers' meetings. Learning how to adapt their outreach is something many agribusinesses are keen to do. Some Guiding Principles At the event, agribusinesses were guided through a step-by-step process to involve farmers with disabilities found in their accessibility guidelines, which were developed specifically for Indonesian agribusinesses. The process includes gathering data on disability rates in a particular area and organising in-person activities for educating and marketing to farmers, with a focus on making sure farmers with disabilities were invited and could take part. The event also highlighted the important role of OPDs in breaking down barriers and connecting agribusinesses with farmers who have disabilities. Many OPDs have existing relationships with farmers with disabilities and can help connect companies with these farmers in a meaningful way. “We need to shift the common paradigm that people with disabilities are beneficiaries of assistance, but to see them as the subject of development. Involving our community in this process helps to do this,” said Bapak Nugroho, one of the panellists from the Association of People with Disabilities in Klaten. A Fresh Approach Yields Results Nufeed, an animal feed company and PRISMA partner, shared its approach to engaging dairy farmers with disabilities. “We must widen our horizons because opportunities are out there waiting for us,” said NuFeed Director, Pak Totok. NuFeed worked with farmers with a disability to create a demonstration plot for their animal feed product, DairyMix. The plot helps farmers see the product's benefits firsthand and in turn, set them up as local product champions. By involving farmers with disabilities, Nufeed’s goal was to introduce the product, boost farmers' confidence, and increase overall sales. These efforts have not only widened their market but fostered empathy and understanding within their teams. “When we did this project, we talked with our friends with disabilities about what they need and how it matches our needs,” said Totok. Their product, DairyMix, is designed to be affordable and suitable for smallholder farmers. It helps increase milk production and farmer incomes by providing a well-balanced nutrient mix, thus reducing the need for farmers to collect and cut grasses for fodder. This is especially beneficial for farmers with mobility issues. With the help of the OPD, Nufeed connected with 10 farmers, including 5 with disabilities, in Boyolali, Central Java, for the demo plot. Out of the 5 farmers with disabilities involved, 2 have gone on to become local sales agents for NuFeed, improving their incomes and sharing the feed innovation with their local community. Following the success of the demo plot, Nufeed held socialisation events to share the results widely and plans to continue the demo plot project. Again, this process engaged farmers with disabilities in attending. Champion Farmer Ibu Martini, a dairy farmer from Banyuanyar Village, participated in the NuFeed demo plot and is one of the farmers who has become a feed agent, selling the product locally to other farmers. Ibu Martini has had mobility issues since childhood, and using the animal feed, DairyMix reduces her family’s workload in collecting grasses for fodder while improving the productivity of her dairy cows. “The training and resources provided during the demo plot have transformed our dairy farming. With increased use of Nufeed, our cows are healthier, milk production has increased, and daily operations are more efficient,” she shared at the event. “As a feed agent, we can sell 6-7 tonnes of feed per month, which has greatly enhanced my family's income and proven that disability is not a barrier to success in farming.” What Next? Inspired by Ibu Martini and NuFeed's actions, agribusinesses shared their plans to develop more inclusive business practices at the event. “We are impressed by the commitment from agribusinesses to adapt and change their approach,” says Mohasin Kabir, PRISMA Team Leader, “Hearing from farmers today inspired us all to look more deeply at how we can connect and foster relationships with farmers.”. To date, thanks to PRISMA’s ongoing support, three agribusinesses have committed to developing more inclusive farmer outreach activities and eight agribusinesses have adopted universal design principles to improve the accessibility of their products. “By broadening our perspective and adapting our practices, we can support growth that benefits not only the individual farmers but the agriculture sector as a whole,” adds Kabir. “It's about building a more resilient and diverse agricultural community.” ‘The training and resources provided during the demo plot have transformed our dairy farming. With increased use of Nufeed, our cows are healthier, milk production has increased, and daily operations are more efficient. Martini, a dairy farmer from Banyuanyar Village.

4.2.3. Youth inclusion

## Study on regeneration in agriculture

This semester, PRISMA commissioned the Center for Population and Policy Studies of Gadjah Mada University (CPPS UGM) to conduct a study on youth and regeneration in agriculture. The study aims to comprehend the factors influencing farmers’ regeneration and youth involvement, which puts Indonesia's agricultural sustainability and food security at further risk. With a policy brief as its main output, the study will contribute to the initial draft of the 2025-2029 RPJMN and its indicators. The study is expected to be completed and disseminated by the end of October 2024.

4.2.4 Indigenous inclusion

## Collaboration with stakeholders for study on regeneration in agriculture

During this semester, PRISMA facilitated collaborations between different stakeholders in Tanah Papua to improve the inclusion of indigenous vegetable farmers. One such collaboration is with Anggi Mart, a local off-taker, PT Agrosid, a national seed company, and the Community and Village Empowerment Agency (DPMK) in Manokwari. This partnership aims to enhance indigenous farmers’ access to quality seeds, GAP assistance, and off-taking services in the vegetable sector.

  - Knowledge harvesting and dissemination

PRISMA has developed a learning brief based on its experience and lessons acquired working with indigenous people in Tanah Papua. The brief mainly targets development stakeholders, and PRISMA plans to share it during World Indigenous Day in August.

In addition, PRISMA co-hosted 2 events with the West Papua provincial government and PYCH to further promote indigenous-inclusive approaches and strengthen off-taking chains that involve indigenous farmers in Manokwari. Following the events, several participants expressed their interest in participating in or replicating the inclusive business model, i.e., the inclusion of indigenous people, developing offtaking channels, etc., promoted by PRISMA and its partners.

Strategic Communications

Project closure communications

PRISMA's strategic communications have focused on creating a strong program legacy this semester. This legacy is achieved through increased awareness of the program's impact, support for sustainability via market resilience activities, and enhanced government policy and planning processes. The Petani Maju campaign was developed to address each of these needs.

This proved to be an effective strategy. By the midway point of the campaign, PRISMA had surpassed its target of reaching 2 million people, reaching 2.68m, receiving over 129 media mentions, and engaging 2,578 people face to face.

Petani Maju / Future Farmer – PRISMA’s final year campaign

The campaign was launched in March and provided a cohesive brand and message for PRISMA’s surge in activities and events. The campaign leveraged PRISMA’s business and government networks across 6 provinces and 12 agricultural commodities to expand the reach of PRISMA communications. In the first semester, over 27 events were branded as "Petani Maju." The events aimed to influence market actors by disseminating knowledge, best practices, and field evidence. Media and social media supported the events, and the face-to-face engagement helped to build existing relationships between partners and forge new relationships for stronger market resilience and policy aims.

In addition to sector-specific market resilience events, PRISMA experts and partners in climate and GEDSI (Gender equality, disability and social inclusion) shared their insights at national-level events.

A key lesson from the campaign was the importance of decentralising PRISMA’s communications to enable sector teams to capitalise on opportunities for greater visibility. Templates were created for press releases, social media posts, market briefs, and policy briefs. Market briefs provided a concise template for summarizing.

What success looks like

In addition to the metrics on digital reach, event attendees and media mentions (shared in the Executive Summary), PRISMA gathered qualitative data to gauge the level of influence of PRISMA’s events and activities. Quotes from event participants can be found throughout this report, providing an insight into the relevance of the information shared to market actors.

“I think this event is excellent because it shows that women have a big opportunity in the agricultural industry. As a lecturer, I can tell my female students not to be pessimistic because agribusiness has initiated to provide designated space for women’s participation in the agricultural industry.” Puji Lestari – Lecturer from the Faculty of Agriculture, Universitas Lampung at PRISMA’s crop protection event on customer education and women sales agents excellence in Jakarta.

End-of-program package

PRISMA will create a comprehensive "end-of-program" package containing its key communication products to support its program legacy. This package will be shared at the closing event in September and made available on the PRISMA website. Nearly three-quarters of the communication products have been completed this semester. The package will include market briefs, GEDSI toolkits and studies, the business Q&A series, climate-smart agriculture case studies, the already published learning series, Indonesia Market Watch series, and legacy impact briefs derived from the program's completion report.

Market briefs

This semester, PRISMA produced 8 market briefs from 6 sectors. The briefs were distributed at events and sent directly to partners, academia, and relevant market actors. The briefs provided clear recommendations to businesses, drawing on PRISMA’s experiences. For example, one of the briefs focused on soil treatment and organic fertilizer, which was shared at PRISMA’s market resilience event. This event, titled "Education-Based Marketing to Support Sustainable Farming Practices in the Fertilizer Market," was held in Surabaya on July 23, 2024. The brief described effective marketing strategies for promoting organic fertilizer for business growth and sustainable agriculture. It addressed issues such as the national supply and demand gap of 53%, lack of company investment in developing the organic fertilizer business, and lack of farmer awareness about the use of organic fertilizer and balanced fertilization. The event participants responded positively to the shared market brief and the event, contributing to the strategizing of the marketing approach for organic fertilizer. PRISMA plans to continue developing and sharing market briefs into the second semester, with 12 events planned for disseminating the briefs and influencing market actors.

Monitoring for insights

PRISMA monitored its website traffic to determine which products attracted the most attention from visitors. The top three most visited pages were the Petani Maju campaign launch, the Climate Smart Agriculture Case Study on AgCoTech, and the news story on the disability inclusion national workshop. Each page held the reader's attention for between one and two minutes. Suggesting the topics that are most interesting to PRISMA readers.

Operations

Human Resources

During this semester, PRISMA has successfully filled the role of Chief Technical Officer (CTO). This became necessary when the former CTO was promoted to the CEO role in January 2024. The CTO position, which was previously held by an expatriate, has now been filled by a national candidate. While the recruitment process was open to the public, the chosen candidate was an internal talent. Additionally, two staff members were promoted from Principal Business Consultant to Head of Portfolio, and thirteen staff members resigned.

The number of resignations has slightly increased compared to the last semester, a trend commonly observed at this stage of a program. Most resignations were due to individuals seeking job security because the program is ending this year.

Operations

In this semester, the program activities focused on resilience and closing the PRISMA program, resulting in fewer collaboration agreements with partners. PRISMA processed 4 partnership agreements for implementation activities and one memorandum of understanding (MoU) for an activity in Papua.

For resilience activities, cooperation with partners involved partnerships and subcontract agreements. There are 12 partnerships for resilience activities, 13 new subcontract agreements, and 2 subcontract agreements extended from 2023. PRISMA also cooperated with 29 new local short-term advisors (STAs) and extended 12 STA local contracts and 2 international STA contracts to support program activities in this semester.

Operational cooperation with vendors supporting the program continued, with 59 agreements extended throughout the region to support operations in the field. The procurement process processed 846 procurements for operational and implementation activities. Operations also provided logistical support for 63 activities and 476 travel events this semester.

Another focus was on processing the closure of the PRISMA program, including completing the handover document for DFAT and ensuring that every detail of the operational process has commenced. This was repeatedly communicated to all staff in each town hall meeting.

During this period, the operations unit conducted internal spot checks under the guidance of the PRISMA Chief Operations Officer. The unit successfully completed 7 internal spot checks, addressing operational, financial, partner claim, assets, compliance, and safety standards. The findings mostly concerned incomplete administrative supporting documents during this reporting period, with no major findings leading to fraud.

The operations unit also prepared an accessible version of all operational guidelines for staff and began documenting the learning and best practices as a legacy for the end of the program, which will contribute to the lessons learned documentation for both DFAT and corporate Palladium.

Annexures

Annex 1: Sectors Progress

## Progress: Beef

## Vision

## Small-scale beef producers in East and Central Java and West Nusa Tenggara (NTB) increase cattle productivity through improved livestock management practices. This will be achieved by introducing good quality and affordable cattle feed and pharmaceutical services through feed and animal pharma companies. This will be supported by changes to Indonesian national feed standards (SNI) and overarching regulations; the development of new industry guidelines and a capacity-building program provided by the Government of Indonesia (GOI) for feed producers, local government, and the Ministry of Agriculture’s (MoA) feed auditors; and improvements in the trading system for live cattle.

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Strategies towards ensuring greater sustainability | ## Supporting partners to increase the participation of farmers with disabilities and promote climate-smart cattle feed in their business strategies | ## Promote the use of feed supplements to decrease methane emissions from beef cattle. | ## Molasses lick block (MLB) trials ## A raw material study report ## Publication on climate-smart livestock (CSL) trial result | ## The Australian technology company AgCoTech was supported by PRISMA through ongoing trial activities for its MLB in Central Java. AgCoTech named the MLB an “emission control block” and trialled it using raw materials readily available in Indonesia. The MLB was tested with the methane laser, and the trials produced qualitative insights that aligned with last year’s Central Java trial results. The study proved highly beneficial for AgCoTech, and the results will be used to develop its business in Indonesia. ## The raw material study was dropped as the trial required more resources and was a higher priority for catalyzing AgCoTech’s work in Indonesia. ## The publication on CSL will be finalised next semester. |
|  |  | ## Pilot and develop a scaling-up strategy for mainstreaming disability inclusion in the partners' business strategies. | ## Disability inclusion trials and reports on them The private sector adopts disability inclusion practices. | ## PRISMA assisted KJUB Puspetasari, an animal feed company, in conducting a pilot program for disability inclusion. This involved setting up a demonstration plot specifically designed for farmers with disabilities. The pilot program has been successfully completed, and now a farmer from the demonstration plot is selling the feed to other farmers. ## Obtaining data on farmers with disabilities, even from government sources such as the Department of Social Services, is quite challenging. Having more detailed information or a centralised database would be extremely beneficial for companies looking to enhance their inclusive practices. |
| ## Policy initiatives (which may include support to the National Development Planning Agency (Bappenas)/the MoA | ## Nudging companies to expand their distribution networks into NTB | ## Conduct policy dialogue on the cattle development sector in NTB to develop policy options and action plans. | ## Policy dialogue workshops ## Policy briefs and action plans | ## Progress on this activity, including new opportunities with universities (Nadhlatul Wathan University [UNW] and Brawijaya), is documented in Section 2.5.1: High-priority policy initiatives. |
|  | ## Supporting the East Nusa Tenggara (NTT) government in developing an enabling environment to induce private sector investment in the cattle sector | ## Organise workshops and coordination meetings with various stakeholders to translate the NTT 2021-2029 cattle sector development roadmap and grand design into practical policy options and action plans. | ## Workshops and coordination meetings ## Policy briefs and action plans | ## PRISMA supported the NTT government in organizing a study and focus group discussion (FGD) in Kupang with multiple stakeholders, including national, provincial, and district governments, as well as the private sector. Consultants are currently developing policy briefs and action plans to support evidence-based policy. ## The government faces a challenge in aligning its goals with the private sector. The private sector is seeking a more affordable buying price at the farmer level, while the local government aims to increase the buying price at the farmer level through a more regulated market for price and cattle minimum requirements. The policy is seeking a compromise that allows farmers to benefit while enabling the private sector to continue driving growth. |
|  | ## Improving feed producers’ capacity to comply with the SNI and good feed manufacturing practices (GFMP) | ## Develop operational guidelines and training modules on SNI and GFMP through collaborations with the MoA, industry associations and universities. | ## Workshops operational guidelines and training modules (booklet and video) | ## PRISMA assisted the Ministry of Agriculture in creating guidelines through a comprehensive process involving multiple teams within the ministry and feed industry representatives from October 2023 to February 2024. This effort resulted in the launch of the guidelines and training modules. It signifies PRISMA's continued commitment to promoting systemic change and sustainability in the production, sale, and use of high-quality feed in the beef sector. |
|  |  | ## Conduct capacity building through training of trainers (ToT) for the MoA, industry associations, and university master trainers, and auditor training for feed certification. | ## ToT and auditor training | ## PRISMA supported the Ministry of Agriculture (MoA) in conducting lead auditor training and certification for 12 master feed quality assessors from the MoA. In March, a hybrid Training of Trainers (ToT) for feed quality assessors (Wastukan) was held in Semarang and Surabaya, as well as online, allowing over 350 participants to join the training. The participants provided positive feedback, with approximately 94.2% stating that the training benefited their work, and 84.1% confirming that they are now more confident in guiding feed producers through the feed registration process. ## One of the challenges of this activity was to ensure the alignment on the needs, interest, and schedule of multiple stakeholders from various internal MoA divisions, as well as livestock agencies at provincial and district levels. PRISMA and the MoA Feed Directorate had to maintain close communication and coordination with all stakeholders to ensure mutual understanding regarding the training. |
|  |  | ## Pilot the training for technical guidance for feed producers in selected regions, including assessing non-protein nitrogen (NPN) compliance feasibility. | ## Technical guidance provided to feed producers |  |
|  |  | ## Continue influencing the MoA to roll out training on SNI for its staff. | ## A MoA training plan | ## The MoA has indicated that it already has plans to distribute the Operational Guidelines module to all wastukan. Many government agencies have shown full support and appreciation for the ToT (Training of Trainers) and technical guidance training series. This includes the head of the East Java Livestock Agency, who mentioned that the agency plans to improve support to the wastukan, including providing them with regular ToT. |
| ## Knowledge harvesting and dissemination | ## Harvesting and sharing good practices, learnings, and challenges in the beef cattle sector (CSL practices and disability inclusion initiatives) | ## Produce evidence-based knowledge on CSL practices (feed, tools, methodologies, and protocols) to measure and estimate beef cattle emissions and disability inclusion. | ## A CSL practices market brief ## A disability inclusion practices market brief – both for the beef and dairy sector |  |

## Progress: Crop Protection

## Vision

## Smallholder rice and maize farmers in East and Central Java reduce their harvest loss by appropriately using safer crop protection products. To ensure the promotion of safer crop protection products and good crop protection practices (GCP), PRISMA will improve the marketing and communication strategies of crop protection companies.

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Knowledge harvesting and dissemination | ## Improving the private sector’s (crop protection [CP] companies) delivery of educational messages | ## Conduct a comparison study to understand the difference between traditional and education-based marketing. | ## The comparison study report is delivered by Q1 and shows the commercial impact of education-based marketing. | ## PRISMA conducted a study to compare the commercial outcomes of education-based marketing and hard-selling strategies in crop protection. The study analysed the marketing approaches of 14 CP companies and their impact on farmers. Over 350 farmers from 7 provinces took part in the survey. The analysis showed that companies focusing on education-based marketing tend to achieve better commercial outcomes, including a higher revenue-per-field-staff ratio. The study also revealed that educating farmers increases their awareness and willingness to purchase. Education helps farmers better understand pests and diseases, leading to higher product satisfaction and loyalty, and positive word-of-mouth promotion among farmers. PRISMA plans to share the study results with CP companies and associations at a dissemination event scheduled for July in Jakarta. |
|  |  | ## Share study findings and support business-to-business (B2B) engagements between training providers and CP companies. | ## A dissemination workshop in Jakarta for CP companies (partners and non-partners) ## The comparison study results are shared with 6 CP companies. ## Training providers attend the dissemination workshop and engage with CP companies. | ## A dissemination workshop in Jakarta was held to encourage CP companies to adopt education-based marketing and optimise the potential of women sales agents. The event was co-hosted by CropLife, a pesticide association. ## The comparison study results were presented at the workshop with CP companies. ## Training providers attended the event and engaged with CP companies. |
|  |  | ## Harvest best practices for women sales agents and disseminate them to relevant companies. | ## A report on best practices for women sales agents is delivered by Q1. ## Dissemination events for CP companies (expected to be held in Jakarta) ## The report on best practices for women sales agents is shared with 5 CP companies. | ## A qualitative study to explore the potential of hiring women sales agents (WSAs) for CP companies was completed. The team conducted field observations and interviews with 23 field agents, 7 companies' representatives, 30 farmers, and 18 kiosk owners in East and Central Java. ## The study revealed that WSAs are perceived to have better negotiation skills than their male counterparts. Additionally, WSAs have a better reception among women kiosk owners, senior farmers, and women farmers. With the benefits that WSAs potentially bring to the CP companies, PRISMA shared these findings with CP companies at the dissemination event in Jakarta. |
| ## Strategies towards ensuring greater sustainability | ## Improving the private sector’s (CP companies) delivery of educational messages | ## Develop a monitoring tool framework for measuring the quality of education-based marketing activities and share it with training providers and CP companies. | ## A monitoring tool framework for CP companies ## A dissemination workshop in Jakarta ## The monitoring tool framework is disseminated to 3 CP companies. | ## PRISMA conducted a farmer survey to design a diagnostic tool for CP companies to monitor their field activities. The tool is a weighted questionnaire with a set of simple predictive questions that companies can use to check the effectiveness of marketing activities and their market positioning. ## PRISMA summarised the findings in a market brief that was shared at the event in Jakarta. |
|  |  | ## Support training providers in developing and promoting training services to CP companies. | ## Facilitation workshops for training providers and CP companies ## Promotional materials designed and tailored to the CP companies as a new market ## Marketing and promotional activities | ## The team faced challenges in engaging training providers, as the current market for training is underdeveloped. CP companies do not consider investment in training to be their top priority. PRISMA invited training providers to the dissemination event in to encourage engagement and highlight the importance of capacity development in improving marketing strategy effectiveness. |

## Progress: Dairy

## Vision

## Small-scale dairy farmers in East and Central Java improve milk quality and productivity as a result of adopting good practices in rearing, feeding, and health management and gaining access to good dairy breeds and more secure end markets where the milk price is based on quality. PRISMA will improve the management and business practices at the farm level by working with feed and pharma companies and enable access to good dairy breeds through its policy advocacy. In addition, PRISMA will work with dairy processors to improve milk handling at collection points and expand distribution networks. With better access to dairy processors, farmers will have increased incentives to improve their milk quality and yields.

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Strategies towards ensuring greater sustainability | ## Supporting partners to increase the participation of farmers with disabilities and promote CSL practices in their business strategies to increase resilience to climate change | ## Promote using climate-smart feed and pens to decrease the intensity of methane emissions from dairy cattle. | ## A molasses lick block trial and a report ## Climate-smart pen trials and a report ## CSL trial result publication | ## The MLB trial progress is reported in the beef section at the beginning of Annex 1. ## The climate-smart pen trials, known as "closed-house pens," have been successfully conducted, and the results have been shared with the industry. Closed-house pens have been shown to reduce heat stress and improve productivity. PRISMA has supported the agribusiness Medion and Nestle in disseminating the trial report, highlighting the benefits of the pens through the Union of Indonesian Dairy Cooperatives (GKSI’s networks). These trials have brought about a positive change in the industry and have helped build the resilience of animals and smallholder farmers. Nestle is actively promoting this innovation to its dairy farmers' network.. |
|  |  | ## Pilot and develop a scaling-up strategy for mainstreaming disability inclusion in the partners' business strategies. | ## Disability inclusion trials and reports ## The private sector is applying disability inclusion practices. | ## PRISMA assisted Nufeed in testing a disability inclusion strategy, including product trials and customer education for farmers with disabilities. ## The trial was completed in January 2024 and yielded positive results in terms of production. Farmers reported good outcomes from using the high-quality feed. Following the trial, two farmers with disabilities became sales agents for Nufeed. They were impressed by the positive impact of the product on their own dairy cows and are now earning additional income by selling to others. ## The pilot results were presented to various stakeholders, including partners, farmers, social agencies, livestock agencies, and organizations of persons with disabilities (OPD) in March 2024. The response from the local government, OPD, and the private sector was favorable. Furthermore, the pilot results were shared at the national disability inclusion workshop in Jakarta, titled "Disability Inclusion in Agribusiness: From Awareness to Action." ## One challenge encountered during this initiative was the difficulty in finding data on farmers with disabilities, even from government agencies. It was noted that more detailed information or a centralized database would be immensely beneficial for companies looking to expand their inclusive practices... |
| ## Policy initiatives (which may include support for Bappenas) | ## Supporting the MoA to implement the dairy cattle roadmap in collaboration with private sectors and industry associations | ## Conduct workshops and coordination meetings with multiple stakeholders to translate the roadmap into practical policy options and action plans (operational guidelines). | ## Workshops ## Operational guidelines | ## PRISMA assisted the MoA organising workshops to review and update the main regulations. The revised regulations were then submitted to the Ministry of Agriculture's Legal Bureau. ## Additionally, PRISMA helped the MoA develop guidelines for dairy farming practices and Jersey cow management through various workshops. These guidelines will be distributed in the form of pocketbooks next semester, providing practical information to enhance the productivity of Jersey cows.. |
|  |  | ## Link governments and private breeding farms with appropriate capacities to commercialise tropical dairy breeds. | ## Workshops and reports | ## PRISMA helped to bring together the MoA, Greenfields, cooperatives, and experts for the Jersey cow trial at the farmers' level. The trial was successfully completed with positive results. The guidelines for Jersey farming practices are now being developed based on the trial results. |
| ## Knowledge harvesting and dissemination | ## Harvesting and sharing good practices, learnings, and challenges in the dairy cattle sector (CSL practices and disability inclusion initiatives). | ## Producing evidence-based knowledge on CSL practices (feed, pens, tools, methodologies, and protocols) to measure and estimate emissions from dairy cattle and disability inclusion | ## A CSL practices market brief - for beef and dairy sectors | ## As reported in the beef sector progress update, the CSL case study was produced and disseminated this semester. |
|  |  | ## Organise a series of public-private discussion forums or policy dialogues to discuss policy options, public-private partnerships, and investments in CSL practices and disability inclusion in the dairy sector. | ## Sharing learning workshops | ## As reported above, NuFeed was supported to attend the national disability inclusion workshop. ## The Nufeed case study contributed to a market brief for disability inclusion (a joint document with the beef sector) and was disseminated at the event. |

## Progress: Finance

## Vision

## Smallholder farmers in Central and East Java can access quality inputs through better-financed agri-kiosks. PRISMA will achieve this by working with financial institutions to introduce flexible loans to agri-kiosks and by improving the enabling environment for agri-small and medium enterprise (SME) financing. By 2024, at least 3 banks will have increased their commercial interest in disbursing agricultural financing products to agri-kiosks in Central and East Java.

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Strategies towards ensuring greater sustainability | ## Supporting collaborations with other market actors for loan channelling | ## Facilitate a partnership between Bank Sinarmas Syariah and Semaai to enable a buy now pay later (BNPL) mechanism. | ## Semaai is promoting the Sinarmas Syariah BNPL facility to its agri-kiosks network. | ## A Buy Now, Pay Later (BNPL) service aims to provide financing for agri-kiosks, with the goal of expanding product lines and enhancing productivity for smallholder farmers. ## PRISMA recently organized a meeting to discuss a potential partnership between Bank Nano Syariah (formerly Bank Sinarmas Syariah), a private Sharia-compliant bank, and Semaai, an agri-e-commerce platform for agri-kiosks, to introduce BNPL service. ## This BNPL service is a new offering, and to minimize risk, Semaai plans to initially launch it with its current partner, Koinworks, a peer-to-peer lending company. The introduction to Bank Nano Syariah received positive feedback, and Semaai may consider expanding the BNPL facility to other partners after evaluating the pilot phase in the second half of 2024 |
|  |  | ## Facilitate a partnership between Bank Sinarmas Syariah and the Kubota machinery (mechanisation providers) network. | ## The mechanisation provider (the Kubota network) is accessing Bank Sinarmas Syariah’s loan facility. | ## The partnership facilitated by PRISMA between the mechanization provider Kubota and Bank Nano Syariah (formerly Bank Sinarmas Syariah), a private Sharia bank, has been successful. The bank has signed a partnership with Bina Pertiwi, an authorized distributor of Kubota Machinery Indonesia. Through this partnership, seven customers in Medan, North Sumatra, Makassar, and South Sulawesi have received a Sharia-compliant mechanization financing facility from Bank Nano Syariah. Mechanization can reduce harvest and labor costs and improve productivity for smallholder farmers. |
|  |  | ## Facilitate a partnership between Bank Mandiri and Saprotan Utama, an agri-input company, for financing agri-kiosks. | ## The Mandiri BNPL facility is promoted to Saprotan Utama’s agri-kiosk network. | ## Saprotan Utama has expanded the Mandiri BNPL (Buy Now, Pay Later) facility to 43 agricultural kiosks in Demak, Central Java. Bank Mandiri is currently evaluating the financing eligibility of the recommended kiosks and will offer loans to those that qualify. This initiative aims to enhance the sustainability of the BNPL loan product, potentially leading to significant improvements in the sustainability of agricultural kiosk businesses and the inventory available to smallholder farmers. |
|  |  | ## Facilitate a partnership between Bank Mandiri and Jiva, an agri-tech company, to provide kiosk financing. | ## The Mandiri loan facility is promoted to the Jiva agri-kiosk network. | ## PRISMA facilitated a business brokering meeting between Bank Mandiri and Jiva, a maize off-taker and supplier of agri-inputs to agri-kiosks. As a result, Bank Mandiri is conducting an institutional assessment before it can receive customer referrals from Jiva.. |
|  | ## Institutional strengthening for adapting business strategies | ## Agriculture financing training with Bank Mandiri to increase knowledge and capacity in developing and delivering suitable loan products in agriculture | ## Bank Mandiri’s staff knowledge of the agriculture sector has increased, and they are ensuring strategic alignment to improve their products. | ## To increase Bank Mandiri’s staff knowledge of the agriculture sector PRISMA organized an online agriculture financing training. Around 525 participants from all of Bank Mandiri’s branch offices in Central Java attended the training. The aim of the training was to help participants understand the characteristics of agri-SMEs and identify the market actors in the agriculture value chain who could potentially receive financing. ## The training strengthened Bank Mandiri’s institutional capacity for agri-financing. In the three months following the training, Bank Mandiri disbursed financing to 202 agri-SMEs, with a total of IDR30.7 billion of loans disbursed. |
|  |  | ## Support Bank Mandiri to develop market intelligence/market watch tools for better risk mitigation strategies in agriculture financing. | ## Bank Mandiri’s staff knowledge of the agriculture sector has increased, and they are ensuring strategic alignment to improve their products. | ## This initiative was dropped. Internal staff rotation within Bank Mandiri impacted management, who initially supported this initiative. |
|  |  | ## Support Bank Sinarmas in developing marketing strategies for Sharia product knowledge and awareness. | ## Bank Sinarmas Syariah has improved strategies for promoting Sharia products. | ## Bank Nano Syariah, formerly known as Bank Sinarmas Syariah, received support from PRISMA to develop marketing strategies. In order to raise awareness and knowledge about their Sharia products, they launched 17 promotional videos on social media. Additionally, 8 bank agents have partnered with Bank Nano Syariah to promote their Sharia financial services offline through the community banking system. |
| ## Policy initiatives | ## Developing a policy brief for improving agriculture financing | ## Socialise the draft policy brief for improving agriculture financing, including advisory and engagement services from the Financial Services Authority (OJK). | ## The OJK is aware of improvements that can be applied in agri-SME financing. | ## A FGD titled "Agri-SMEs Financing Policies Review" was conducted by PRISMA and the Institute for Development and Economics and Finance (INDEF), a public policy research organization. The FGD was attended by representatives from OJK, the Coordinating Ministry of Economic Affairs, Indonesia Guarantee company (Jamkrindo), University of Indonesia, and banks including Bank Rakyat Indonesia (BRI), Bank Mandiri, and Bank Nano Syariah. Feedback from the participants on the initial recommendations presented by INDEF and PRISMA has been collected. The recommendations showed the participants’ awareness of the issues concerning agri-SMEs financing, which helped INDEF and PRISMA to develop the policy brief. |
|  |  | ## Collaborate with the Australia-Indonesia Partnership for Economic Development (Prospera) think-tank organisation to raise OJK’s awareness of possible improvements in the agriculture financing sector. | ## The OJK is aware of improvements that can be applied to agri-SME financing. | ## PRISMA and Prospera are collaborating to exchange data and insights on financing for agricultural small and medium-sized enterprises (agri-SMEs). PRISMA is currently working on creating a policy brief and a market brief for agri-SMEs, which will be distributed through Prospera’s network at the Coordinating Ministry for Economic Affairs and the OJK. |
|  |  | ## Hold FGDs with the OJK to discuss potential policy improvements in agriculture financing. | ## The OJK is aware of improvements that can be applied to agri-SME financing. | ## PRISMA is currently preparing a policy brief and will request approval from DFAT. |
| ## Knowledge harvesting and dissemination | ## Extracting insights from studies and sharing them with relevant stakeholders to foster their adoption | ## Publish agri-kiosk landscaping insights through mass or digital media and financial institute associations. | ## Financial institutions, regulators, and governments are aware of the potential market and the characteristics of agri-SME financing. | ## PRISMA is currently finalising the dashboard containing information about 1.470 agri-kiosks, profiling data, and conducting further analysis. The analysis will be used to develop a market brief to be shared publicly in August. |
|  | ## Harvesting and sharing good practices, learnings, and challenges in the finance sector | ## Develop and share a market brief on agriculture financing with bank associations, financial technology (FinTech) associations and Bappenas. | ## Financial institutions, regulators and governments are aware of the potential market and the characteristics of agri-SME financing. | ## PRISMA insights will be shared through a market brief that will be disseminated in August. |

## Progress: ICT (Information and Communication Technology)

## Vision

## Smallholder farmers in Central and East Java have better access to GAP information, inputs, and agri-services through more tech-savvy and tech-enabled agri-kiosks. PRISMA will work with agri-kiosks to provide them better access to ICT solutions to ensure they are better managed and stocked appropriately with products in a timely fashion, offering an increased range of agricultural services, and relevant quality advice.

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Strategies towards ensuring greater sustainability | ## Developing support strategies for marketing | ## Facilitate meetings between Semaai and input companies for better product fulfilment (price, stock) and knowledge variety. | ## Semaai has an increased product line. | ## PRISMA has brokered business connections between PT Semaai, an agri e-commerce platform for agri-kiosks, and PT Botani Seed Indonesia (BOSI), a national rice seed producer for product fulfilment. Following the meetings, Semaai is now selling rice seed produced by PT Botani to agri-kiosks in Central Java. |
|  |  | ## Facilitate a partnership between Mitra Sejahtera Membangun Bangsa (MSMB), an ag-tech company, and Saprotan Utama and Agrotama Tunas Sarana (ATS) to promote the use of the fertiliser calculation app in product demonstrations (utilisation and efficacy). | ## An MSMB business model | PRISMA facilitated a meeting between Mitra Sejahtera Membangun Bangsa and 2 fertiliser companies, Saprotan Utama and ATS, to discuss trialling MSMB’s fertiliser calculator app. Saprotan Utama pulled out from the trial due to a change in its business priority. ATS tested the fertiliser calculator app with ATS farmers in Kediri district. The trial results showed that the app from MSMB increased the farmers’ profitability by 10% in maize and 3% in shallots, compared to the traditional fertilisation strategy followed by farmers. ATS plans to integrate MSMB’s fertiliser calculator app into its advisory service for farmers. |
|  |  | ## Facilitate a partnership between Sipindo, YARA, and Mutiara to promote the use of the fertiliser calculation app in product demonstrations (utilisation and efficacy). | ## Sipindo develops a new business model. | ## Due to staff resignations in Sipindo`s partnership, Sipindo/YBTS, an agri-tech company, decided not to prioritise this initiative. It plans to focus more on social media promotion to promote the fertiliser calculation app to farmers, agri-kiosks, and extension officers. |
|  |  | ## Facilitate showcasing the fertiliser calculation products and successful cases to relevant stakeholders, such as the MoA and PISAgro. | ## A workshop report | ## Successful trial plot harvesting using the fertiliser recommendation from SIPINDO/YBTS, an agri-tech company, has been exposed to the local Blitar government. The recommendation was proven to increase farmers’ revenue by up to 25%. This event was published in an e-newspaper. |
|  | ## Supporting collaborations with other market actors for alternative payment options for product stocking | ## Facilitate a partnership between NADI, an agri-tech company, Saprotan Utama, and an organic fertiliser producer, Rojokoyo Manunggal, to support better kiosk product stocking. | ## The NADI BNPL facility is promoted. | ## Following the launch of new supply-chain features in the apps, NADI has developed partnerships with 4 input companies: PT Berkat Mitra Makmur (BMM – organic fertiliser producer), Saprotan Utama (fertiliser producer), Rollimex (crop protection producer), and PT Tunas Widji Inti Nayottama (TWIN – seed producer). These partnerships will enable agri-kiosks to purchase agricultural inputs through their mobile app, which is embedded with a BNPL payment option. |
|  | ## Improving input procurement by enabling payment options | ## Support adjusting the NADI financing product feature to better suit agri-kiosks' cash flow. | ## Flexible financing/BNPL products are available and promoted | ## NADI has launched a new BNPL feature integrated with financing providers to ensure liquidity in providing BNPL and serve more agri-kiosks with various agri-input products and payment options. |
| ## Knowledge harvesting and dissemination | ## Assessing business feasibility and sharing it with relevant stakeholders | ## Study the technology investment feasibility in the agriculture sector, share the results through the media or PISAgro and involve impact investors or venture capital. | ## Awareness assessment report | PRISMA has interviewed 4 agri-tech and 5 investing companies to complete the research on the agri-tech investment study. The final report is planned to be finalised in August 2024 and will be disseminated through an Indonesia Entrepreneurs Association event. |
|  | ## Harvesting and sharing good practices, learnings, and challenges in the ICT sector | ## A workshop with the MoA to share PRISMA's experience in the digitalisation of agriculture. | ## A workshop report | ## DFAT has reviewed the report on the gender roles of women and men and it will be disseminated to market players in Q3 2024. ## A study on digital agriculture technology, which aims to support Bappenas in developing the National Medium-Term Development Plan (RPJMN), is ongoing. The result is scheduled to be disseminated in July. |

## Progress: Maize (Madura and NTT)

## Vision Maize Madura

- Smallholder maize farmers in Madura use quality hybrid seeds and GAP to increase production and productivity. PRISMA will achieve this by working with seed companies to improve private sector investment in the seed market and by facilitating public-private collaboration to improve the delivery of government subsidy programs. By the end of the program, PRISMA aims for more than 16% of smallholder maize farmers in Madura to increase production and productivity by adopting hybrid seeds and applying GAP.

## Vision Maize NTT

- Smallholder farmers in NTT use certified maize seeds and apply GAP properly. PRISMA will achieve this by (1) improving the capacity of open-pollinated variety (OPV) seed producers (nurseries) to produce quality seed and developing the commercial seed market, (2) facilitating local governments in the development and implementation of their maize sector strategy, and (3) promoting GAP information for farmers. Following the feasibility analysis of off-taking business opportunities, PRISMA dropped this function and focused on 3 market function areas around quality certified seed, market supporting policy, and information on GAP.

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Maize Madura |  |  |  |  |
| ## Strategies towards ensuring greater sustainability | ## Supporting the district office in Madura to disseminate market opportunities and sustainable, inclusive business strategies for Madura to more companies. | ## Capture the new market entry and expansion of companies in Madura. | ## List of new entries and expansions of private companies in Madura since September 2023 | ## As part of the follow-up to the socialisation event on market opportunities for seed companies conducted in August 2023, PRISMA continues to communicate with several seed companies to encourage them to carry out demo plots using a monoculture or intercropping method following the planting pattern in villages. ## Two new seed producers conducted demo plots in Madura, while 4 others expanded their seed distribution in the area. However, all of them focused on monocultures, and these new entries did not actively promote themselves to farmers. PRISMA will hold one more learning-sharing activity in August 2024. |
| ## Policy initiatives | ## Institutionalising the smart subsidy in Madura | ## Assist the district office in releasing official guidelines on the smart subsidy. | ## Official guidelines signed by the district office | ## In April 2024, PRISMA and the Sumenep Food and Agriculture Security Service (DKPP) held a FGD to discuss draft guidelines for determining prospective subsidy recipient candidates (Prospective Farmers and Location Candidates/CPCL) based on smart subsidy principles. This document aims to guide DKPP Sumenep in determining suitable areas for seed subsidy allocation to encourage wider adoption of high quality seeds. It includes guidelines for updating the database to periodically and continuously monitor developments in the commercial seed market so that DKPP Sumenep can prioritise subsidy allocation in new development areas. The final draft of the guidelines has been shared with the district office. PRISMA is following up on its official release. |
|  | ## Implementing the smart subsidy in Central Java | ## Assist provincial and district offices in implementing the technical guidelines on the smart subsidy in Central Java. | ## A report on data and progress of the implementation | ## Following the issue of the smart subsidy technical guidelines and the socialisation events in 2023, the provincial office encouraged district-level offices to complete the needed database. ## In March 2024, a joint visit was conducted to 3 districts to verify the data. Around 80% of districts have completed the database, which is the first crucial step in implementing the guidelines as this helps with the provincial office maps, as this area still needs further maize market development. |
| ## Knowledge harvesting and dissemination | ## Harvesting the lessons learned from the smart subsidy implementation in Madura and Central Java and sharing them with other relevant government institutions | ## Capture data and lessons learned from Madura and Central Java. | ## A report on data and lessons learned | ## PRISMA engaged the Centre for Indonesian Policy Studies (CIPS) to conduct a study to capture the lessons learned. CIPS has completed the literature review and interviews with relevant stakeholders and is currently conducting data analysis and summarising the findings. |
|  |  | ## National-level awareness event/FGD as evidence-based advocacy for the smart subsidy | ## FGD event | ## The research institute will present the results of the study and a summary of good practices for smart subsidies in a FGD. The FGD will invite representatives from government institutions and business associations related to maize seeds. PRISMA and CIPS are in progress finalising the concept of the FGD event. |
|  |  | ## Write a policy brief on the smart subsidy. | ## A policy brief | ## The policy brief will be finalised after the FGD event. |
|  |  | ## Publish and disseminate the smart subsidy policy brief. | ## Dissemination event for the policy brief | ## A dissemination event will be held after the policy brief is finalised. |
| ## Maize NTT |  |  |  |  |
| ## Strategies towards ensuring greater sustainability | ## Providing business advice and linkages for seed producers and more effective contract farming management | ## Connect seed producers with diverse intermediary service providers (ISPs). | ## A list of new ISPs linked to seed producers | ## Building a wider seed distribution channel is important to ensure more farmers have access to quality seeds and to ensure business continuity for the seed producers. Considering that the agri-input kiosks in NTT are mostly concentrated in urban areas, PRISMA advised seed producers to build their distribution networks by also involving other channels, such as village kiosks, mobile vendors, and extension services. ## As a result, the seed producers have engaged with a total of 28 ISPs, including 14 agri-input kiosks, 4 village kiosks, 6 extension services, and 2 mobile vendors. |
|  |  | ## Conduct sharing events on the best practices – including contract farming models | ## Sharing events on contract farming models | ## In February 2024, PRISMA facilitated benchmarking and sharing sessions for 3 local NTT seed producers (Sehati Toka, Sehati, and Dalla Sikka) with private seed companies and government seed production facilities in East Java. This activity aims to provide local NTT seed producers with new insights on how they can better manage seed production and post-harvest processes. As they actively promote their products and build product distribution networks, these local seed producers face the challenge of expanding production scale to meet increasing demand. ## During the 2024 dry season, 2 seed producers planned to expand their drying floors using the designs they learned during the visit. Meanwhile, another seed producer plans to implement a new contract system with plasma farmers, according to the example learned from the visit. |
|  | ## Providing business advice to the NTT Seed Producers Association on selling branded packaging to other (non-PRISMA partner) seed producers | ## Regular (quarterly) monitoring of the business model implementation | ## Progress report (quarterly) | ## Since the end of 2023, PRISMA piloted a business model to sell branded seed packaging to seed producers. Access to good seed packaging is a high entry barrier for local seed producers to enter the commercial market because of the high initial investment. The goal of the association’s business model is to have more local seed producers – beyond PRISMA’s partners – sell their products in the commercial market so that farmers can have more access to quality seeds. This semester, The NTT Seed Producers Association succeeded in selling small quantities of branded packaging to other seed producers. |
|  | ## Assisting the provincial government in improving the production planning of parent seed | ## Advocacy for the provincial agriculture office to allocate a budget for parent seed availability | ## Progress report (quarterly) | ## The provincial government office set aside a budget for parent seed production and communicated this with the NTT Association of Seed Producers. However, a fire incident in early May 2024 in the main office of the technical unit for seed production may cause operational challenges. ## To support the provincial office, PRISMA highlighted the importance of OPV seed production in NTT in an in-depth study (conducted by a research firm, Tulodo) for the Regional Development Planning, Research, and Innovation Agency (Bapperida), which will provide input for the NTT RPJMD. |
|  |  | ## Support the provincial government in developing a policy brief on the importance of breeder seed production of OPV by the national government (the Agriculture Instrumental Agency). | ## Published and disseminated policy brief and supporting study report | ## PRISMA engaged Tulodo as a research firm to conduct a study focusing on the business-enabling environment for seed producers—including OPV seeds—to develop their supply chains in NTT. Tulodo has conducted a literature review and interviewed key stakeholders. ## In May 2024, the findings were shared and discussed further in a FGD in Kupang. This event was attended by the NTT Agriculture and Food Security Service, several heads of agricultural services from maize-producing districts (including Southwest Sumba, East Manggarai, and South Central Timor), NTT seed producers, and farmer kiosks. The study’s results will be used to write a policy brief and provide inputs for the NTT RPJMD. |
| ## Knowledge harvesting and dissemination | ## Capturing and sharing NTT market characteristics and learnings with national seed companies | ## Share information and facilitate networking with national seed companies in the NTT context. | ## A list of national companies engaged and linkages made with local networks (semesterly) | ## National seed companies still have little interest in investing in NTT. PRISMA plans to hold a sharing and networking session in August 2024 between national companies and some local NTT players. The event will promote the market potential of Maize Madura and Maize NTT. |
|  | ## Capturing the learnings from the independent capacity-building modules for public extension services | ## Monitor the implementation of capacity building through independent learning run by the local district government. | ## A summary of implementation progress and lessons learned | ## Following up on the kick-off events for the independent training modules with 5 district governments in August-September 2023, 2 districts (Southwest Sumba and East Manggarai) with a total of 254 public extension services have completed the modules. In 3 other districts (Sikka, Belu, and Kupang), progress has stalled because (1) capacity building did not translate to the credit point of the public extension service, and (2) the extension workers considered the transportation and meal allowance as important incentives to conduct capacity-building. |
|  | ## Sharing the learnings on developing the maize market in NTT with other stakeholders (for example, local governments, NGOs, the private sector) | ## Publish the summary of learnings and conduct sharing events. | ## The summary of learnings is published and distributed during the sharing events. | ## PRISMA collaborated with the district agriculture offices to hold 2 sharing events – one in Southwest Sumba and the other in East Manggarai. The topic was on the learnings on developing the maize market in the area. It highlighted the important role of public extension services as the front liners of introducing agri-innovations and the need for their continuous capacity building. The event was attended by representatives from 3 other agriculture offices from neighbouring districts (West Sumba, Central Sumba, East Sumba, West Manggarai, Manggarai, and Ngada). ## In addition to the local government, representatives from the local private sector (including kiosks, off-takers, and seed producers) and local NGOs were also present. The goal was to facilitate interaction and linkages between stakeholders in advancing the development of the maize market. |

## Progress: Mechanisation

## Vision

## Smallholder farmers increasingly use agriculture machinery and tools (for example, maize combine harvesters and planters), resulting in reduced labour costs and improved yields. PRISMA will achieve this by supporting machinery companies to promote machine access to smallholder farmers and improve aftersales services.

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Strategies towards ensuring greater sustainability ## Knowledge harvesting and dissemination | ## Conducting a series of workshops to socialise information on market potential to attract more machinery companies to enter the NTT market | ## Collaborate with the government to socialise the information on market potential to attract more machinery entering the NTT market. | ## A workshop for disseminating the NTT market study report | ## PRISMA teamed up with NTT's Agriculture and Food Security Department to organize a workshop in Kupang, NTT. The participants included members of the Government Mechanisation Service Unit (UPJA) and Agriculture Department staff from key rice-producing districts in NTT. AGRINDO, an agricultural machinery company, shared best practices for the machinery rental business. ## Furthermore, recognizing the significant potential in NTT, AGRINDO proposed collaborating with the Agriculture and Food Security Department to support machinery operation. |
| ## Strategies towards ensuring greater sustainability | ## Improving the capacity of parent companies to expand machinery businesses without further PRISMA support | ## Explore collaborations with training providers to develop and promote modules for lean market research, aftersales operations, and digital marketing. | ## A new module for each of the functions (lean market research, aftersales operation, and digital marketing) developed by the training providers ## One promotion event to promote the training availability | ## PRISMA has collaborated with three training institutions to create courses on lean market research, aftersales management, and digital marketing. These training providers are now offering these courses as new training modules. ## Additionally, MRTKG, a training institute, has hosted a webinar to promote the market research module. |
|  |  | ## Partnerships with parent companies to build capacity for marketing and sales operations | ## A capacity-building workshop in sales and marketing for 2 parent companies | ## Plans to partner with parent agri-machinery companies were hindered by confidential business concerns. The activity was subsequently dropped. |
| ## Knowledge harvesting and dissemination | ## Conducting stakeholder consultations to stimulate market competition and disseminate information on market potential | ## Work with governments, associations, and the media to share the potential of the agricultural machinery market and its challenges. | ## Two seminars in collaboration with the media to disseminate information on the market potential of rice and maize machinery, including drones | ## In partnership with Agrina Magazine, an agribusiness magazine, PRISMA organised a seminar in March in Jakarta. Key representatives from the machinery industry participated in the event. The seminar outlined the challenges and opportunities in the agri-machinery industry and shared possible solutions available in the market. ## Agrina conducted a business forum in early June as follow up to the event. |
| ## Policy initiatives |  | ## Work with governments, associations, or training institutions to streamline agriculture drone operation processes and procedures for pilot certification. | ## A new drone spraying certification module is developed and implemented as an industry standard for drone pilots. | ## A new training module focused on drone spraying for pilot certification has been developed and socialised to market actors during the Agrina national seminar event. ## Furthermore, the Association of the Unmanned Systems and Technology Association will socialise the module at the Indonesian Drone Expo 2024 in August. |

## Progress: Mungbeans

## Vision

## Smallholder mungbean farmers in Central and East Java adopt quality seed and GAP and have increased access to improved off-taking services. This will be achieved by encouraging additional mungbean seed producers to enter the market and connecting relevant market players to improve the downstream mungbean market.

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Strategies towards ensuring greater sustainability | ## Supporting the commercialisation of parent seed | ## Support producers to promote parent seed to nurseries. | ## Parent seed producers conduct promotion activities with 3 nurseries by Q2 2024. | ## Following the completion and delivery of the parent seed business model to CV Luwes, a seed producer, the company then conducted 4 gathering events as promotional activities to traditional seed retailers and nurseries. ## However, CV Luwes has decided not to continue its promotional activities. This decision is due to a shift in strategic priorities to focus more on the extension seeds. |
| ## Knowledge harvesting and dissemination | ## Supporting the commercialisation of parent seed | ## Disseminate knowledge on parent seed business potential to other producers. | ## Three dissemination events for seed producers to be held in Jakarta (national), Central Java, and East Java | ## Given the scale and intricacy of each dissemination event, PRISMA strategically decided to consolidate the 3 dissemination events and business meetings into one. This unified event took place in Semarang on 12-13 June 2024. Semarang was a logical choice as it is a major hub for mungbean production. Semarang was a practical and efficient choice for the event rather than Jakarta or East Java, as many market actors are based there. ## More than 100 people attended the event, including upstream and downstream market actors - seed producers, nurseries, local off-takers, international traders and associations, and government officials. ## PRISMA collaborated with a key partner, the MoA, to host the event. The MoA, represented by the Seed Directorate, the Legume and Tuber Directorate, and the Processing and Marketing Directorate, played a crucial role. Their active involvement and support were instrumental to the success of the event. ## PRISMA shared the market briefs on the downstream market and women farmers' involvement during the event. |
|  | ## Inducing free market entry of other seed producers | ## Share lessons learned on marketing in the free market with entry-level producers. | ## Three dissemination events for seed producers to be held in Jakarta (national), Central Java, and East Java |  |
|  | ## Conducting stakeholder consultations to stimulate market competition and disseminate information on market potential | ## Disseminate knowledge on seed business potential to potential producers. | ## Three dissemination events for seed producers to be held in Jakarta (national), Central Java, and East Java |  |
|  |  | ## Harvest and disseminate learning on women farmers’ commercial involvement to relevant producers. | ## A report on women farmers' commercial involvement delivered by Q2 ## Three dissemination events for seed producers to be held in Jakarta (national), Central Java, and East Java |  |
|  |  | ## Share lessons on mungbean business potential and demand requirements. | ## Three dissemination and networking events for upstream, downstream, and public actors to be held in Jakarta (national), Central Java, and East Java |  |

## Progress: Pig

## Vision

## Smallholder farmers and market players in the pig industry benefit from increased availability and appropriate use of quality inputs and improved husbandry practices, supported by a conducive regulatory environment. PRISMA will work towards a 10% recovery of the pig sector in NTT. The focus is on detection, response, prevention, and recovery from African swine fever (ASF) by improving restocking, awareness, and information about animal husbandry practices. Sector resilience will focus on breed improvement by building the capacity of the key market actors and strengthening the regulatory environment, along with feed and pharma distribution networks.

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Strategies towards ensuring greater sustainability | ## Assisting the government to improve its pig breeding management system | ## Develop an accredited artificial insemination (AI) curriculum and module for pig AI training through a multistakeholder working group workshop and piloting the training. | ## Pig AI curriculum and module Pig AI training held by the Kupang Agricultural Training Center (BBPP) | ## PRISMA engaged experts to support the Kupang BPPP in establishing the AI curriculum, modules, and technical guidelines for pig inseminators to enhance the NTT pig breeding management system. Pig AI pilot training was conducted in Kupang (December 2023). |
| ## Policy initiatives (which may include support for Bappenas/MoA) | ## Supporting the commercialisation of parent seed | ## Institutionalise the AI curriculum and module as a standard for AI training in Indonesia at the national and provincial levels. | ## The curriculum is adopted by the NTT provincial government and the MoA and used as an official reference in pig AI training. | ## The Agricultural Extension and Human Resources Development Agency (BPPSDMP) under the MoA institutionalised the curriculum through the establishment of the Specific Work Competence Standard (SKK Khusus) for swine inseminators applicable to all professional certification institutions, and educational and training institutions under the MoA. The standard was endorsed by the head of BPPSDMP, MoA in May 2024. ## As a follow-up, ToT for pig AI assessors will be conducted in August 2024. |
| ## Strategies towards ensuring greater sustainability | ## Inducing free market entry of other seed producers | ## Workshop to develop the SNI procedures for pig semen (chilled) certification for breeding farms. | ## Pig semen SNI procedures for businesses are developed and implemented. | ## PRISMA engaged experts to support the development of the SNI chilled semen certification standard operational procedures (SOP). The SOP can be used widely by any semen producers in Indonesia to obtain the SNI certification. |
| ## Policy initiatives (which may include support for Bappenas/MoA) | ## Conducting stakeholder consultations to stimulate market competition and disseminate information on market potential | ## Workshop to develop a national standard for frozen pig semen and the relevant procedures. | ## A SNI for frozen pig semen and relevant procedures | ## PRISMA collaborated with the Center for Livestock and Animal Health Instrument Certification (PSIPKH) under the MoA to develop the draft SNI for frozen pig semen. This June, after completing 3 stages of conception, and technical and consensus meetings, the final draft was endorsed and submitted to the National Standards Agency (BSN). The SNI for the frozen pig semen is expected to be issued by the BSN this September 2024. |
|  |  | ## Institutionalise the pig semen procedures and frozen semen national standard to relevant stakeholders. | ## The Directorate of Animal Breeding and Production and the MoA adopt the frozen pig semen SNI as the official standard. |  |
| ## Policy initiatives (which may include support for Bappenas/MoA) | ## Assisting the provincial government in strengthening its procedure for livestock movement | ## A workshop for socialising the Disease Investigation Center (BBVet) recommendation for using the loop-mediated isothermal amplification (LAMP) diagnostic device as the official tool for ASF testing related to livestock movement | ## A BBVet recommendation on utilising the LAMP device as the official tool for ASF testing related to livestock movement --> leading to improving regulations | ## After a series of LAMP trials and comparison tests from March – November 2023 in Kupang, Sikka, East Sumba and Bali, which were overseen by BB-Vet Denpasar, it was recommended that LAMP be used for ASF testing. |
|  |  | ## Institutionalise the LAMP diagnostic testing as a standard regulation for livestock movement. | ## Regulation improvement - revision of NTT Governor Instruction No.003 of 2023 | ## In May 2024, PRISMA and the NTT Provincial Animal Husbandry Office conducted a workshop to discuss the use of LAMP as an official diagnostic tool for pigs and the movement of their derivative products in NTT. ## As a result, the NTT Provincial Animal Husbandry Office developed a policy brief by revising the current NTT governor instruction to include LAMP as an option for ASF testing for livestock movement. It is expected to be enforced by September 2024. ## Also, the NTT provincial government plans to amend the tariff regulation to include the LAMP. |
|  |  | ## A scenario and analysis of the impact of pig movement regulation | ## A policy recommendation document (policy brief) for the NTT province government and the national government ## An action plan document on increasing private investment in NTT province ## A provincial-level workshop to disseminate the study report, the policy brief, and the action plans |  |
| ## Strategies towards ensuring greater sustainability and knowledge harvesting and dissemination | ## Linking the potential ASF vaccine provider with the provincial and national governments | ## a. Assess risks associated with the vaccines | ## Understanding the risks and a mitigation plan to support the program in decision-making | During the feasibility assessment of this activity, PRISMA realised the stages of vaccine registration in Indonesia were beyond PRISMA’s timeline. The application for clinical trials submitted by PT Putra Perkasa Genetika (a vaccine distributor) to the MoA in December 2023 had not seen significant progress. ## Thus, PRISMA dropped this activity but is closely monitoring the development of vaccine registration. |
|  |  | ## b. Link the potential vaccine provider with the local government, the DFAT program (i.e., AIHSP-Australian Indonesia Health Security Partnership), the national government and the private sector. | ## The ASF vaccine is widely known, and distributors have potential agents in the regions, so farmers can easily access the vaccine. |  |
|  |  | ## c. Develop the vaccine registration steps for the vaccine provider with permission from the government. | ## A step-by-step vaccine registration procedure is developed to help distributor companies register products and obtain government permits to commercialise the vaccine. |  |
|  | ## Sharing sector lessons learned. | ## Share the NTT pig sector lessons learned through stakeholder engagement with private and public market actors from Papua, West Papua, Sulawesi, North Sumatra, Bali, and Kalimantan. | ## A workshop with pig sector market players in NTT and other provinces detailing the successful and unsuccessful experiences in the NTT pig sector, including educational materials on good rearing practices and disease prevention. ## Ongoing dissemination of the workshop information using the education materials developed by PRISMA and its partners | ## In June 2024, PRISMA, in collaboration with the NTT Provincial Animal Husbandry Office, held a sharing event in Kupang on lessons learned. The event targeted stakeholders at national and provincial levels (NTT and other provinces) to share the collective knowledge, learnings and efforts in the recovery and development of the pig sector in NTT. ## Based on this sharing event, policymakers, practitioners, academics, and other stakeholders are anticipated to apply the knowledge and learnings further in their respective areas. |

## Progress: Rice

## Vision

## Smallholder rice farmers in Central and East Java adopt high-yielding rice seeds and have increased productivity. To achieve this, PRISMA will work with key seed producers to produce, promote, and educate farmers on the benefits of using high-yielding varieties (HYV). In parallel, PRISMA will provide evidence and recommend concrete policy actions to encourage the government to boost HYV procurement in its seed subsidy programs.

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Strategies towards ensuring greater sustainability | ## Action research on climate-smart agriculture | ## Climate-smart agriculture products and practices exploration |  |  |
|  |  | ## Identify potential climate-related activities and amend contracts with rice seed partners. | ## A list of activities | ## PRISMA identified activities that supported climate resilience with high-yielding rice seed producers, PT Botani and CV Anisa. With PT Botani, PRISMA supported an event to launch its new climate-smart seed. At the event, PT Botani released its latest innovation, the IPB 9G climate-smart seed. The Minister of Agriculture attended and endorsed the event, highlighting this new seed variety’s importance and potential impact on sustainable agriculture practices. The IPB 9G is designed to be resilient in varying climate conditions, offering farmers a reliable option for enhancing crop yields and ensuring food security. Zero waste production efforts. CV Anisa, a rice seed partner, successfully completed a series of formulation trials for creating biofertiliser. Throughout 3 trials, CV Anisa refined its process, culminating in a successful final trial. The trials mark a milestone for the company, bringing it one step closer to its goal of zero net production. |
|  |  | ## Harvest lessons and conduct an impact assessment, incorporating climate-related measurements. | ## An assessment report | ## An impact assessment for PT Botani’s partnership is currently underway. The field activities were completed and data collection was conducted across Central Java and East Java, encompassing 220 respondents. The data collected is now being analysed, and a comprehensive report is being developed. |
| ## Knowledge harvesting and dissemination | ## Learning exchange events to disseminate the importance of HYV to rice seed producers and the government | ## HYV learning exchange events; |  |  |
|  |  | ## Roundtable discussions with rice seed partners to collect learnings on HYV | ## Discussion reports | ## PRISMA held a discussion with rice seed partners (PT Agrosid, PT Botani, CV Anisa, CV JTM, CV Fiona). The discussion gathered learnings and encouraged the exchange of knowledge amongst the partners. The companies’ owners and directors attended the event. ## Several collaboration opportunities between the partners were identified. Going forward, the partners will take up the discussion directly. ## Following the discussion, the team has developed a report that includes learnings from each partner as well as highlights and recommendations. |
|  |  | ## Develop a collaboration strategy document from the roundtable discussions. | ## A collaboration strategy document | ## The activity report has been developed, which includes the collaboration strategy. |
|  |  | ## Induce a response from the government by conducting information sharing sessions or workshops with relevant stakeholders. | ## The event is conducted for seed producers, the National Research and Innovation Agency (BRIN), and the government. | ## Through a rice consultant, PRISMA conducted direct discussions with seed producer, BRIN, and government representatives. ## The purpose of these discussions was to circulate the results of the partner’s roundtable discussion on promoting the importance of adopting HYV rice seed and paving the way for PRISMA’s rice seed partner in the future. |
|  |  | ## Develop a learning paper. | ## Learning paper on the efforts in expanding the HYV market | ## The learning paper was developed and will be disseminated in several forms, including roundtable reports, a case study, and a market brief. |

## Progress: Soil Treatment (Fertiliser)

## Vision

## Staple, horticulture, and estate crop farmers in Central and East Java, and NTB have access to and safely use quality fertiliser. To increase the availability and use of high-quality commercial fertilisers, PRISMA will work through private and state-owned fertiliser producers. Fertiliser producers and retailers will offer a variety of fertilisers (both organic and chemical) through innovative marketing and promotional strategies, which incorporate accessible information on good fertiliser practices (GFP).

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Strategies towards ensuring greater sustainability | ## Institutionalising education-based marketing and other soft-selling techniques | ## Improve the institutional capacity of fertiliser companies through tailored capacity development programs for embedding education-based marketing and soft-selling to smallholders. | ## Tailored capacity development workshops for fertiliser companies on strategic business issues | ## ATS conducted capacity building for its 25 staff on strategic marketing in Yogyakarta, facilitated by an agriculture business expert. PRISMA also supported ATS with a women’s inclusive business workshop on the commercial impact of inclusive strategies in business. ## BOSI conducted a series of training sessions for its staff on product knowledge, marketing, communication, and digital marketing for the fertiliser business portfolio. |
|  |  | ## Support collaborations between fertiliser companies and other market actors, such as seed producers, off-takers, and agri-tech companies, to develop enhanced offers to smallholders in under-served areas. | ## Joint activities | ## PRISMA supported PT ATS, a soil treatment company, in collaborating with an agri-tech company, PT MSMB, for soil testing and financial institutions (Bank Mandiri in East Java and BRI in Central Java) for kiosk financing. PT ATS also collaborated with the local government of Madura to enhance the organic fertiliser market in under-served areas in 3 districts of Madura. ## PRISMA supported BOSI in conducting a joint event with the local government of Sukoharjo, Central Java, to introduce organic fertiliser and enhance its use to support sustainable farming in Central Java. ## Facilitated by PRISMA, PT Saprotan Utama Nusantara (SUN), a fertiliser producer, together with PT Seger Agro Nusantara (a maize off-taker) and Syngenta (a seed producer), conducted joint training on GAP and good handling processes and established a demo plot for maize farmers in Southwest Sumba, NTT. This joint activity aims to support the growth of the maize sector in underserved areas, such as NTT. |
|  |  | ## Explore opportunities to crowd in marketing companies and others as long-term advisors in education-based marketing. | ## A workshop by a research and training (marketing) company for fertiliser and other input companies | ## The team faced challenges in engaging training providers, as the current market for training is underdeveloped. Fertiliser companies do not consider investment in training as a priority. PRISMA aims to invite training providers to the dissemination event in July and highlight the importance of capacity development in improving marketing strategy effectiveness. |
|  | ## Embedding innovative, sustainable, and environmentally friendly soil fertility management models | ## Support local governments in developing social marketing campaigns to enhance organic fertiliser uptake and collaborations between fertiliser companies and local governments to introduce innovative products (for example, mineral-organic fertilisers). | ## Social marketing campaigns on promoting sustainable farming practices and using organic fertiliser | ## Following the reprioritisation of PRISMA’s soil treatment strategy, the program decided not to continue this initiative, considering its early stage and the program’s timeframe. |
| ## Knowledge harvesting and dissemination | ## Institutionalising education-based marketing and other soft-selling techniques | ## Produce comprehensive learning on PRISMA’s education-based marketing approach (in conjunction with the crop protection team) to help inform the market of the validity and viability of the approach. | ## A market brief on best practices applying GFP | ## PRISMA is conducting a GFP study to assess the effectiveness of disseminating GFP information and the degree to which these promotional messages have been taken on by smallholder farmers and how they have changed their practices towards GFP. PRISMA will summarise the study into a market brief based on the learning of the study. ## Study analysis is currently underway. In July, a market brief will be disseminated at the event. |
|  |  | ## Partner with business enablers (PISAgro/universities/associations) to organise a learning workshop on education-based marketing. | ## A dissemination event or workshop for fertiliser and input companies | ## A dissemination event was held in July 2024. The event discussed 2 main topics: (1) the effectiveness of the education-based marketing approach in fertiliser markets and (2) a strategy to develop organic fertiliser markets. |
|  | ## Embedding innovative, sustainable, environmentally friendly soil fertility management models | ## Partner with business enablers (governments/universities/associations) to organise a learning workshop on PRISMA’s experience and market insights pertaining to organic fertiliser. | ## A dissemination event or workshop for fertiliser companies | ## In July, a market brief on the organic fertiliser study was presented at a dissemination event. The study itself is based on PRISMA’s learning and experience in developing the organic market. |
|  |  | ## The private sector and the NTB provincial government conduct joint research to test novel organic fertiliser products. | ## A report on the organic fertiliser market in NTB | ## Report completed for BOSI. One finding refers to how the marketing and promotion of liquid biofertiliser is generally related to government, and that PT Botani could benefit from involving local governments to disseminate information, educate farmers, and provide training and demo plots. ## BOSI, together with the governments of Central Lombok and East Lombok and the NTB provincial government, will conduct a mini workshop to share the learning and findings. |

## Progress: Vegetables and Regional Economic Development (RED) – Tanah Papua

## Vision

## Smallholder farmers in Tanah Papua use quality seeds, apply GAP, and have access to the downstream market. This will be achieved by working with seed companies and off-takers and will include implementing indigenous-inclusive strategies. By the end of the program, PRISMA aims for more than 12,000 seasonal vegetable farmers to experience an increase in productivity due to better seeds, agricultural practices, and off-taking services.

| ## Exit strategies | ## Focus areas | ## Planned initiatives |  | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- | --- |
| ## Regional Economic Development (RED) |  |  |  |  |  |
| ## Policy initiatives (which may include support for Bappenas/MoA) | ## Disseminating a formulated strategy document to all Tanah Papua provinces | ## Develop a province-level report outlining and analysing the agriculture market potential. |  | ## A provincial-based report highlighting the market potential | ## Six provincial-level reports were developed for Papua, Central Papua, Highland Papua, West Papua, Southwest Papua, and South Papua. ## The draft report was shared during the workshop to receive feedback from participants. |
|  |  | ## Workshops with stakeholders from the government and customary and religious networks to disseminate findings |  | ## Workshops across all Tanah Papua provinces | ## Three workshops were conducted in Jayapura, Merauke, and Manokwari to discuss insights and ways forward based on the provincial report. ## Various representatives from government, academia, civil society organisations, and private sector participants attended, including the head of the House of Representatives in Papua province and the head of the People’s Consultative Assembly in Papua province. |
|  |  | ## Follow up and observe responses from stakeholders |  | ## Follow-up plans collected from stakeholders | ## Ongoing facilitation between market actors to take up results from the workshop on a selected commodity as a trial. ## Each province identified a potential collaboration model involving government, civil society organisations, and agribusinesses for specific commodities that have high indigenous Papuan involvement in their respective provinces. ## The participants will follow up accordingly; however, implementation might be delayed due to ongoing preparation for the head of district elections. |
| ## Vegetable Sector |  |  |  |  |  |
| ## Strategies towards ensuring greater sustainability | ## Assisting vegetable seed partners to succeed in marketing their quality products to indigenous farmers | ## Seed Access across Tanah Papua |  |  |  |
|  |  | ## Link partners for locally-led development and indigenous-inclusive promotion activities. |  | ## A list of linkages between seed partners and local institutions/agencies ## Minutes of the agreements on promoting quality seed and providing GAP assistance to indigenous farmers | ## PRISMA facilitated a public-private partnership between PT Agrosid and the Manokwari District Community and Village Empowerment Agency (DPMK), formalised by signing the minutes as an agreement between both parties. ## The multiparty collaboration aims to enhance indigenous farmers' access to quality seeds, GAP assistance, and off-taking services in Manokwari district through 2 government aid programs: TEKAD and the Village Fund (Dana Desa). ## The collaboration includes establishing demo plots and organising farmers' meetings to promote quality seeds and provide GAP assistance to indigenous farmers in Kwau village as a pilot. ## Moving forward, PT Agrosid and Manokwari DPMK have agreed to continue this thriving collaboration by replicating similar activities in other Indigenous villages, demonstrating their long-term commitment to the betterment of the community. |
| ## Knowledge harvesting and dissemination | ## Embedding innovative, sustainable, environmentally friendly soil fertility management models | ## Institutionalise the learnings in local universities/agencies and offer business development services. |  | ## Market assessment reports for 4 new market expansion areas ## A list of potential new distributors | ## Due to budget concerns, the market assessment was only completed for one area. ## PRISMA has linked Ottow Geissler University in Jayapura to PRISMA’s seed partners and supported the university in showcasing its business development and consultancy services. ## Ottow Geissler University, with PRISMA support, conducted a market survey in South Sorong, identifying 3 agri kiosks as potential distributors. ## The university presented the market survey report to PRISMA’s partners and received a positive response from seed partner, PT Agrosid, which has expressed interest in exploring collaboration with the university to expand its commercial seed distribution and GAP assistance to indigenous farmers. |
| ## Strategies towards ensuring greater sustainability | ## Engaging local off-takers to enhance local produce absorption | ## Supply Chain Enhancement |  |  |  |
|  |  | ## Link the off-takers’ suppliers (farmers) with seed companies for farming assistance. | ## A list of linkages established between seed partners and local off-takers ## Minutes of the agreements on promoting quality seed, providing GAP assistance and off-taking services to indigenous farmers |  | ## Three collaborations were established between seed partners and local off-takers, one each in Sorong, Manokwari, and Merauke. ## PRISMA took the success of the multistakeholder collaboration in Sorong (Southwest Papua) from last semester and set the stage for a similar approach in Manokwari (West Papua) and Merauke (South Papua). ## In Manokwari, PRISMA facilitated tripartite collaboration between DPMK through the village-owned enterprise (BUMDES), Anggi Mart and PT Agrosid to provide GAP assistance and off-taking services to indigenous farmers in Kwau village. ## In Merauke, PRISMA facilitated a collaboration between vegetable seed partner PT Agrosid and Ibu Wiwin, a local female vegetable off-taker, to promote commercial seed and off-taking services to both indigenous and transmigrant farmers. |
|  |  | ## Roundtable discussions to endorse B2B engagement to increase the uptake of locally produced vegetables |  | ## Roundtable discussions in 5 provinces in Tanah Papua ## Purchase orders from hotels, restaurants and cafés and big industry consumers to local off-takers | ## Due to budget concerns and travel to the locations, the roundtable discussion was eventually held at one location, Manokwari. ## PRISMA, together with the West Papua provincial government, hosted a multistakeholder event to promote indigenous-inclusive approaches. Private and public sectors, including hotel, restaurant, and café reps, also attended. The half-day event consisted of a panel discussion, a joint commitment ceremony, and a mini-exhibition, showcasing products and innovations from partners, including Anggi Mart. ## The mini-exhibition successfully triggered interest from notable supermarket and restaurant chains, which requested Anggi Mart to submit a sales offer, which is the step required prior to becoming a supplier. |
| ## Knowledge harvesting and dissemination | ## Endorsing successful indigenous-inclusive approaches and learnings to stakeholders that will foster replication across Tanah Papua | ## Dissemination of Indigenous-inclusive best practices |  | ## One network facilitation conducted in West Papua | ## PRISMA collaborated with Papua Youth Creative Hub (PYCH), an organisation of young indigenous Papuan entrepreneurs, to hold the Youthpreneur Summit in Manokwari. ## The event provided a platform for participants from 4 provinces in Tanah Papua to exchange ideas and foster creativity in replicating the inclusive off-taking model aimed at enhancing the economy of indigenous communities. ## Following the event, 5 out of 6 participants immediately replicated the inclusive business model, and 3 participants from Biak, Jayawijaya, and Teluk Wondama kick-started their vegetable businesses. |
|  |  | ## Share learnings from off-taking models to encourage replication. |  |  |  |
|  |  | ## Conduct workshops in partnership with local governments and seed companies to share best practices from the indigenous targeted activities. |  | ## Workshops in 5 provinces in Tanah Papua ## A market brief | ## Considering the program’s budget and travel to the locations, the workshop was held in conjunction with the stakeholder meeting in Manokwari. ## The stakeholder meeting was attended by 70 people, mostly government reps from 4 districts. The event was acknowledged and opened by the second highest person in command, the Acting Regional Secretary of West Papua Province. ## The participants expressed their appreciation for the event and interest in taking up the model in their respective areas. ## Going forward, PRISMA’s private sector partners will follow up directly with interested district-level governments. |

## CROSS-CUTTING AREAS

## Progress: Gender Equality, Disability and Social Inclusion (GEDSI)

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Strategies towards ensuring greater sustainability | ## Strategic disability inclusion to establish good practice examples and learnings on disability-inclusive business models | ## Support the private sector in adopting inclusive business practices to include farmers with disabilities in their field marketing and educational activities. | ## Farmers with disabilities are participating in several partners' activities (for example, socialisation events and market engagement) | ## Cattle farmers with disabilities continued to participate in socialisation events conducted by cattle feed producers - KJUB Puspetasari and Nufeed. Two farmers with disabilities who participated in demo plots and the socialisation events became feed sales agents for Nufeed. In the maize sector, CV Tani Sehati Jaya, a seed nursery in NTT, conducted a trial on seed sortation involving people with disabilities through a partnership with a special school of students with disabilities. ## At the disability inclusion workshop in Jakarta, PRISMA’s private sector partners shared their experience on participation and accessibility improvement with a broader audience, including agribusiness, organisations of persons with disabilities (OPDs), and development programs. A market brief, “Inclusive strategy for agribusinesses to involve farmers with disabilities”, was also disseminated at the event. |
|  |  | ## Support the private sector in adopting universal design (UD) principles to improve accessibility for farmers with disabilities. | ## Improved accessibility to private sector partners' information and promotional materials | ## PRISMA supported 3 partners in developing inclusive promotional tools using UD principles. The improvements included: (1) an accessible promotional video with subtitles, appropriately sized with contrasting graphics for MSMB, an agricultural startup company, and YBTS, a foundation under PT East West Seed Indonesia; (2) sign language interpretation on the YBTS video; (3) accessible printed promotional tools with better readability for Etong, a crop protection company. ## PRISMA also shared the Accessibility Guidelines for agriculture with the private sector during the disability inclusion workshop. |
| ## Knowledge harvesting and dissemination | ## Women's economic empowerment (WEE) ## Harvesting knowledge and sharing it with the private and development sectors on women’s inclusion and empowerment | ## Develop learning materials - case studies, guidelines, and learning, which include: - Creating business opportunities through women sales agents - Measuring WEE in private sector development programs - Guidelines for the private sector on women-inclusive business strategies - Practitioner's guidelines for the development sector on women-inclusive business strategies - Learning on the agency dimension of WEE | ## WEE learning materials | - PRISMA is developing a market brief on opportunities for engaging women sales agents for crop protection companies. - PRISMA has commissioned Daya Makara, University of Indonesia, to conduct a study on Return on Investment (ROI) for women-inclusive businesses. The study is currently in the data collection stage and is expected to be completed by August. - PRISMA developed and disseminated the following documents: (a) a guideline on reaching more women farmers in promotional activities and for agribusinesses and field staff; (2) a revised version of a guideline on gender-based violence in agriculture (3) a market brief on boosting mungbean seed sales through reaching more women; and (4) learning on gender roles in kiosk management. - PRISMA is currently developing the practitioners guidelines and will finalise them by early August. - Given the private sector’s low traction on agency, PRISMA will focus on developing other knowledge products that are more focused on the needs of the private sector. |
|  |  | ## Disseminate learning products through webinars and workshops. | ## Webinars/workshops on WEE attended by relevant stakeholders. The WEE learning materials are shared with relevant stakeholders through different communication mediums. | ## PRISMA, in collaboration with PISAgro, conducted a workshop on WEE in Jakarta to celebrate International Women’s Day. Eighty-seven participants from various agribusinesses attended the workshop, where keynote speakers and panellists shared their experiences on promoting and conducting women-inclusive businesses. ## Several WEE-related learning documents were shared at the workshop, including: (1) Guidebook for Marketing Teams, Agronomists, and Field Staff; (2) PRISMA Direct Sales Agent Research; (3) Reaching Women Farmers: Tips for Indonesian Agribusinesses; and (4) Women Farmers Stories. ## PRISMA developed a market brief on how to increase mungbean seed sales by reaching more women farmers. The market brief was disseminated and presented during the mungbean discussion forum event organised by the mungbean sector team. ## PRISMA also presented learning on mainstreaming GEDSI through the MSD approach in an MSD training for government and academia in Surabaya 2024. |
|  | ## Disability inclusion ## Supporting a deepening understanding of disability inclusion in agriculture | ## Conduct a disability study to deepen understanding of the challenges in agricultural practices. | ## A study and report on the disability inclusion status quo and challenges in the agricultural context | ## PRISMA decided to cancel the study and focus on intensifying efforts to support interested partners in disability-inclusive business practices. |
|  |  | ## Develop and share learnings, findings, and experiences regarding PRISMA's disability inclusion approach with the private and development sectors. | ## Learning briefs are shared with the private and development sectors. | ## PRISMA developed a market brief with recommendations for implementing inclusive business models in the cattle sector. PRISMA also conducted a one-day workshop on disability inclusion for the private sector. As an outcome, several private sectors expressed their interest in learning more about the concept from PRISMA. PRISMA also developed a guideline for making events and information more accessible for people with disabilities, which was shared during the workshop. ## PRISMA participated as a facilitator, sharing its experience, in an online disability inclusion workshop organised by the Market Development Facility (a multi-country program of DFAT) for its staff. |
|  | ## Youth inclusion ## Regeneration of young farmers | ## A study on the opportunities and challenges of engaging more young farmers | ## Study findings are disseminated to targeted stakeholders. | ## PRISMA commissioned the Center for Population and Policy Studies of Gadjah Mada University (CPPS UGM) to conduct a study on youth and regeneration in agriculture. The study aims to comprehensively understand the factors influencing farmers’ regeneration and youth involvement, with a policy brief as its main output. |
|  | ## Youth inclusion ## Providing insights and learnings to the private and development sectors to trigger more youth initiatives | ## Conduct sharing sessions to gather insights and learnings from development programs, agri-companies, the MoA, and other stakeholders on the potential of youth in agriculture. | ## Sharing sessions on youth with relevant stakeholders | ## The plan was moved to the next semester as the study will be finalised in early August. |
|  | ## Youth inclusion ## Shaping youth readiness in agricultural markets | ## Assess potential business incubator models to identify and develop more youth entrepreneurs in agribusiness. | ## The assessment findings are shared with relevant stakeholders. | ## Dairy feed partner, Cipta Ternak Sehat Indonesia (CTSI), presented a business incubator model to the students of Nusantara PGRI University. This followed a successful application of a similar model at Nahdlatul Wathan University in NTB. However, no assessment had been undertaken prior to the sharing event. |
|  | ## Indigenous inclusion ## Enhancing the private and development sectors’ knowledge and capacity in indigenous inclusion | ## Develop a learning brief on applying indigenous inclusive business models. | ## The indigenous inclusion learning brief is shared with the private and development sectors. | ## A brief detailing the lessons learned from working with the indigenous people of Tanah Papua was developed. The brief is scheduled to be shared publicly on World Indigenous Day in August. |

## Progress: Policy Engagement (PE)

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Strategies towards ensuring greater sustainability | ## Utilising the learnings and insights from the RPJMN workshops to continue supporting Bappenas | ## Comprehensive strategic policy evidence to support the green economy and food security in Indonesia: 1. Data and benchmarking 2. Improve the bridge and delivery system from innovation to end users 3. Regeneration of youth farmers for food security | ## The study is accepted and delivered to Bappenas. | ## Delivered: background study on agriculture modernisation and resilience in Indonesia. ## Ongoing: Indicators on the modernisation of agriculture for the 2025-2029 RPJMN. ## Ongoing: Comprehensive policy studies in key thematic areas (i.e. availability of quality food crop seeds, young farmer regeneration, agriculture digitalisation, and climate-smart agriculture). |
| ## Policy initiatives (which may include support for Bappenas/MoA) | ## Strategic policy engagement at the national level | ## Strategic policy engagement at the national level: 1. National standard feed operational guidelines and Jersey cattle road map follow-up 2. A seed system | ## Policy change in specific sectors (policy brief delivered) | ## Delivered: National standard feed and operational guidelines and the Jersey cattle road map have been translated into Good Farming and Breeding Practices that will be incorporated into the national policy system as the Agricultural Minister Draft Regulation (Rapermentan). ## Ongoing: The seed system initiative has been incorporated into one of the policy studies. |
| ## Policy initiatives (which may include support for Bappenas/MoA) | ## Close collaboration at the provincial and district levels | ## Close collaboration at the provincial and district levels: 1. Maize – Central Java and NTT, 2. Vegetables - Papua 3. Pigs - NTT | ## Policy change in specific sectors (policy brief delivered) | ## Delivered: This semester, PRISMA conducted a final workshop related to vegetable Papua and pig NTT. ## Ongoing: The PRISMA team and consultants are finalising the Maize Central Java Road Map and study for maize, pig, and beef NTT. The reports are expected to be delivered by July 2024. |

## Progress: Strategic Communications

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Expected outputs | ## Progress update |
| --- | --- | --- | --- | --- |
| ## Strategies towards ensuring greater sustainability | ## Supporting sectors’ exit strategies | ## Provide ongoing support to sector teams to develop learning briefs, media releases, and events. | ## Templates for briefs and media releases and support for sector activities and events | ## To support increased communications in PRISMA’s final year, PRISMA developed tools for teams to communicate key information for sustainability. PRISMA developed templates for market briefs, policy briefs, media releases and social media content. This enabled teams to share sector market resilience activities and insights more widely. This semester’s total reach, measured across event, media, social media and partner channels reach is 2.68m, a significant growth from 806,000 last semester indicating the impact of this approach. ## The communications team also developed campaign materials for the Petani Maju campaign, including branding for banners, event invitations and publications and provided design, editing, media, and logistics support for events across all sectors this semester, aiming to engage a wider audience with creative and clear communications. |
| ## Policy initiatives (which may include support for Bappenas/MoA) | ## Anchoring knowledge | ## Support for the policy team's anchoring agenda and the Bappenas National Medium-Term Development Plan | ## Media releases and final products | ## The policy team is developing 4 studies, which will be completed in Q3. Should Bappenas request wider dissemination of the studies (beyond Bappenas), communications will support the dissemination. |
|  |  | ## National-level events to discuss and share knowledge about key program areas | ## 1-2 events | ## This semester, PRISMA held 3 national-level events sharing insights from its GEDSI and climate-smart agriculture cross-cutting areas. The events garnered attention from business and government and were shared in the media and on social media. Details can be found in the Petani Maju update in the PRIP. |
| ## Knowledge harvesting and dissemination - PRISMA's "end-of-program package" | ## Media | ## Ongoing public relations and media to disseminate PRISMA's end-of-program- package and learnings | ## 30+ news articles | ## PRISMA achieved 129 media mentions this semester, reaching an estimated 319,662 people with market resilience messages. Last semester PRISMA had 37 media mentions, demonstrating the impact the scale-up in communications had this semester. |
|  | ## Developing an end-of-program package | ## Develop learning and knowledge series, briefs and interviews with partners. | ## An end-of-program package | ## PRISMA’s end-of-program package is in development (70% complete) and will be completed in Q3. |
| ## Partnership closure | ## GOI completion report | ## Research, plan and publish. | ## A completion report | ## The completion report will be delivered to Bappenas on 31 December 2024. |
|  | ## DFAT completion report | ## Research, plan and publish. | ## A completion report | ## The completion report will be delivered to DFAT on 30 September 2024. |
|  | ## Closing event | ## Organise a Future Farmer event showcasing the business models and innovations that have proven successful. | ## A closing event with speakers, panels and displays in Jakarta | ## The closing event is planned for 30 September 2024. The event will bring the government, private sector, academia and farmers together to celebrate PRISMA's impact and communicate key program learnings through a talkshow and exhibition. The event has been shortened to 3 hours to ensure a more effective communication of PRISMA’s key messages, in a brief and clear format. |

## Progress: Results Measurement and Learning (RML)

| ## Exit strategies | ## Focus areas | ## Planned initiatives | ## Progress update |
| --- | --- | --- | --- |
| ## Measuring key performance indicators (KPI) | ## Impact assessment | ## Conduct impact assessments in the beef, mechanisation, dairy, fertiliser, crop protection, rice, and mungbean sectors. | ## PRISMA has completed seven impact assessments in the first half of this year for four sectors: beef, mechanisation, dairy, and rice. The findings have been reported in the latest PRIP edition. |
|  | ## Extrapolation | ## Report new beneficiaries and income increases using relevant assumptions based on new partner sales. | ## PRISMA has conducted 12 extrapolations this semester from 7 sectors: - Mechanization: Pillar Agri, Argo Jaya, and Galaxy PM - Soil Treatment: Agrotama TS - Dairy: Nufeed - Rice: Agrosid - Mungbean: Semi Purwodadi, Ewindo and Luwes Tani - Pig: Disnak Rote Ndao, Disnak Sumba Barat, Disnak TTS, Flobamora, Lolipop, Mario Putra, Pemkab Lembata, Pemkab Manggarai, Seminari Yohanes, Maju Jaya, Sreeya, Aroma, Mesang Nalley, and Kame Adonara ## Vegetable: Agrosid and Matahari |
|  | ## Evidence collection | ## Collect evidence that supports the claims made in the KPI and the impacts beyond the KPI. ## Collect multiple lines of evidence that support claims. | ## 298 media events have been documented as evidence of program achievement via mass and social media. |
| ## Measuring impacts beyond the KPI | ## Climate change climate-smart agriculture | ## Measure the relative emission reduction derived from using nitrogen-based fertiliser (maize, rice, and fertiliser sector) and concentrate feed (beef sector). | ## Relative emission reduction measurements have been conducted for the four sectors from Year 23 Semester 1 to Year 24 Semester 1. The reports are submitted in each semester's PRIP. |
|  |  | ## Conduct climate-smart agriculture development in Indonesia with Brawijaya University. | ## In-depth interviews have been conducted, and preliminary findings have been reported. FGDs with stakeholders in 3 provinces are planned for July, and the final report is expected to be delivered at the beginning of August. |
|  | ## GEDSI | ## Support the GEDSI team in research design, projects, and producing learning. | ## Women's Inclusive Return on Investment (WROI) research has been conducted. PRISMA collaborated with the consultant (DMUI) to conduct the research. The findings will be reported in August '24. |
|  | ## Food security | ## Measure the significant impacts of long-term interventions in other sectors and areas. ## Focus on areas with high levels of food insecurity (NTT) have the lowest food security scoring). ## Future research: beef Central Java, mung bean Central Java, maize NTT, and pig NTT. All research will be completed by August 2024. | ## The assessment was carried out on Madura Island for beneficiaries of the maize intervention. Findings have been reviewed by food security consultants. Food security studies in NTT are integrated with nutrition studies. |
|  | ## Nutrition | ## Nutrition study ## Investigate the impact of increased income in improving farming household food intake. | ## The Dakra consultant is still finalizing the report for nutrition studies in Central Java (mungbean, beef) and NTT (pig, maize), expected to be submitted in August. |
|  | ## Social Impact | ## Social impact study ## Investigate the impact of increased income on farmer efficacy in adopting more profitable innovations (with higher complexity or investment). ## Investigate the impact of increased income on farmers’ well-being (for example, their children’s education, debt-free status, financial security, etc.). | ## The 1st study: ## - The study covered 4 sectors and 10 districts across 2 provinces (Central Java and East Java). ## - It investigated farmer spending with 166 respondents. ## - The findings from the 1st study have been reported in the PRIP 23s2 edition. ## The 2nd study: ## - The study covered 10 sectors and 17 districts across 4 provinces (Central Java, East Java, NTB, and NTT). ## - It targeted locations where farmers benefited from multiple innovations introduced by PRISMA, with 392 respondents. ## - The survey also measured how households spent income from adopting innovations introduced by PRISMA interventions from 2019 to 2023. ## - Impact beyond income, such as additional free time, was also measured in the survey. ## - The findings from the 2nd study will be reported in August '24. |
| ## Supporting the sector exit strategy | ## All sectors | ## Conduct research to support the sector exit strategy. ## Conduct research or analyse the market system changes in the strategy table. ## Support market system resilience by supporting the sector, especially through knowledge-sharing activities. ## Support the sector team in producing materials on lessons learned. | ## - Smart subsidy: The Central Java Agriculture and Plantation Office and Sumenep DKPP: RML have received support from the Central Java Provincial Agriculture and Plantation Office and the Sumenep DKPP to create an index for hybrid maize market strength and visualize this data through a PowerBI™ dashboard. These tools will aid in implementing smart subsidies in these areas. ## - Bappenas Training: PRISMA conducted an MSD training for participants from Bappenas, the Ministry of Agriculture, Bappeda in Central Java, NTT, and NTB provinces, the Sumenep District Food Security and Agriculture Service, the Manokwari District Village Community Empowerment Service, the Bogor Agricultural Institute, Gadjah Mada University, Brawijaya University, and Nahdlatul Wathan University. The training has been completed, and feedback on participation has been compiled. The participants are committed to developing a curriculum and learning materials based on the market systems development approach, which will be launched in the upcoming semester. ## - RPJMD NTT: PRISMA is supporting the NTT government in developing a background study on the agricultural sector to inform its upcoming RPJMD policy planning process. PRISMA's support includes an evidence-based approach to policymaking with focus group discussions and other evidence and data-gathering activities. |
| ## Completion report | ## Activity completion report | ## Support management to produce high-quality activity completion reports: ## Support in self-evaluation matrix. ## Support in collecting multiple lines of evidence | - PRISMA began self-evaluating the project completion report by mapping FIMR indicators with evidence quality. - PRISMA works with a consultant to evaluate the evidence against FIMR indicators and decide if program achievement needs stronger evidence. - PRISMA will collect more evidence if needed. |
| ## Information handover | ## All data and information collected by RML | ## Prepare a platform for data and information handover: ## Clean data and analysis ## Aggregation and number summary ## An evidence database ## Various documentation and reports | - Organizing evidence and files in the local PRISMA drive is still ongoing (50%) - The impact assessment database (unified) is still ongoing (20%) - PMT website handover - Business intelligence (number summary & PowerBI™) |

Annex 2: High-Priority Policy Initiatives

While the high priority policy initiatives (HPPI) summary status graph is based on deliverables, the following table is organised around PRISMA's key areas of support within each initiative. Each area of support may involve a single or multiple deliverables, and in some instances, deliverables may cut across support areas. The annex is organised around support areas to make it easier to understand each of the initiatives, while the summary graph in Chapter 2.5.2 High Priority Policy Initiatives is organised around deliverables as that provides a more accurate reflection of PRISMA's overall progress in a HPPI.

| Policy Initiative | Description | Key Partner(s) | Activity Status (based on support areas) | Additional Details/Related Results |
| --- | --- | --- | --- | --- |
| Sector-based Initiatives |  |  |  |  |
| Beef: The Ministry of Agriculture (MoA) reforms and implements the revised cattle feed standards (SNI). | Indonesia’s SNIs make it difficult for feed mills, particularly for micro, small, and medium-sized (MSME) mills, which account for the majority of feed producers, to legally sell more affordable, good-quality cattle feed. This policy bottleneck not only impedes the growth of feed companies but also undermines the potential for smallholder farmers to enhance cattle productivity and income. PRISMA supports the MoA in reforming the SNI and ensures that the MoA has the necessary resources to implement and revisit the new standards and regulations and that MSME feed mills have improved capacity to comply with the new SNI. PRISMA does this by: - developing policy briefs and holding policy dialogues to convince the MoA to review the cattle feed SNI and provide the MoA with technical recommendations - facilitating the development of MoA regulations (on feed registration and distribution, good feed manufacturing practice [GFMP], and mandatory implementation of SNI) and training guidelines through consultation with industry stakeholders and universities - socialising the revised SNI for beef and dairy and delivering training sessions and materials to support capacity building of feed mills and government feed supervisors based on the new training guidelines | Feed Directorate, MoA | (a) Completed: The MoA published new feed standards for beef and dairy in 2022 as a result of the policy briefs and policy dialogues supported by PRISMA. The implementation of the revised SNIs is expected to proceed in July 2024. | - The new cattle feed SNIs spurred the MoA to review the SNIs for other livestock feed (chickens, ducks, pigs, and quail). New SNIs for other livestock were published in December 2022, socialised with the feed industry, and are being implemented. |
|  |  |  | (b) Completed: - Drafts for the overarching MoA regulations (Rapermentan) have been completed and are currently under review by the MoA for release and is targeted to be passed by the end of 2024. - Training guidelines for government feed quality supervisors (Wastukan) and feed companies were completed. | - The cattle feed SNIs spurred the MoA to streamline all feed regulations. The MoA is in the process of finalising 3 overarching feed regulations. - The MoA used the training guidelines in its Wastukan training in March 2024 and feed company training in May 2024. |
|  |  |  | (c) Ongoing: - The training was conducted for the MoA's feed auditors at the national level and government Wastukan at the provincial and district levels across Indonesia. - Auditors and Wastukans provided training (technical guidance) to feed companies to comply with the new SNI and good feed manufacturing practices. - PRISMA is in the process of producing a video on GFMP for MSMEs, which will be released in July 2024. PRISMA also plans to support an event to socialise the revised feed SNI for beef and dairy, which is also scheduled for July 2024. | - In February 2024, 12 MoA auditors were trained and certified to perform auditing roles for feed companies and to train Wastukan at the provincial and district levels. - MoA's trainers have trained 350 Wastukans across Indonesia using the training guidelines on 27-28 March 2024. Approximately 84.1% of Wastukans felt more confident with guiding feed producers through the feed registration process, and 94.2% reported that they intend to apply the knowledge they gained to enhance their work. - After the initial training, Wastukans from Sumatra regions requested that the MoA deliver a follow-up offline training in their regions, scheduled for 2025. - A 2-day training was provided for MSME feed producers on 28-29 May 2024. Over 200 feed producers from across the country participated in the training. Approximately 83.3% found the training helpful for their work, and 70.2% felt more confident guiding their company through the feed registration process after the training. The technical guidance video was also on YouTube and had 897 views as of June 2024. |
| Dairy: The MoA develops and implements a dairy recovery strategy to accelerate sector recovery and build resilience. | With national milk production dropping by 29% and with mandatory slaughtering of over 10% of the cattle population to prevent the spread of disease, there was an urgent need to repopulate the sector with dairy cows and increase milk production as part of the recovery from the 2022 outbreaks of foot and mouth disease (FMD) and lumpy skin disease (LSD). However, as of 2022, the government had yet to develop a dairy recovery strategy. There were also no farm-level dairy guidelines and existing regulations on breeding policy, and dairy farming practices were outdated or impractical. Furthermore, there was a lack of data on the impact of FMD on the market and on alternative solutions to accelerate sector recovery. PRISMA supports the MoA’s Directorate of Livestock Breeding and Production (Bitpro) in developing and implementing a dairy recovery strategy to accelerate sector recovery and build resilience. PRISMA does this by: - assisting the MoA in conducting a study on cattle repopulation after the FMD outbreak and developing 2 resulting reports to provide recommendations for cattle repopulation and for introducing Jersey cows to Indonesia - reviewing and updating existing regulations, as well as developing guidelines for good dairy farming (GDF) practices for farmers | Bitpro, the MoA | (a) Completed: The cattle repopulation study was completed in 2022. Two reports resulting from the study were presented to the MoA in February 2023. | - The cattle repopulation study included an assessment of Bitpro’s breeding centre’s capacity to produce breeding materials and seedstock. - The two reports were titled (1) “Production Improvement Strategy of Livestock Breeding Materials and Seedstock for Dairy Cattle after FMD Outbreaks”, and (2) “Development Roadmap and Rearing Guidelines for Jersey Cows”. - Bitpro has shared both reports with various directorates within the MoA and utilised them to formulate policies, programs, and budgets for 2023 and 2024, including the dairy repopulation program. - Bitpro is now executing the dairy repopulation program, which aims to make 1,400 cows, including Jersey cows, available through Bitpro’s breeding centres. Based on another report recommendation, the program also set a new target for the Artificial Insemination Centre to achieve a 40% increase in dairy heifer production and to improve the quality of their semen production. - Another recommendation to streamline the importation process of dairy cows was also adopted, which led to Bitpro recommending that 4 breeding farms import 2,000 dairy cows. - The team from Indonesia’s newly elected vice president acknowledged that the reports were used as a reference for the free milk program and the dairy farming blueprint for 2025-2045. The team also approached PRISMA to support the new administration/government in realising its vision, mission, and programs for free milk. |
|  |  |  | (b) Ongoing: - The MoA's draft regulation on good dairy farming practices is complete. The regulation is currently under review by the MoA’s legal bureau and is expected to be released in 2024 after approval by the Minister. - The MoA expects to disseminate the guidelines in the form of pocketbooks to industry stakeholders in a socialisation event in August 2024. The pocketbook for GDF practices has been finalised, and the pocketbook for Jersey cows will be finalised in July 2024. | - The MoA has consolidated 3 existing regulations (Guidelines on Dairy Farming Practices, Guidelines on Dairy Breeding Practices, and Organic Farming) into one comprehensive regulation, namely Good Dairy Breeding and Farming Practices. - Based on the revised regulation, 2 farm-level guidelines are being developed and will be disseminated in the form of pocketbooks: (1) a pocketbook for GDF practices and (2) a pocketbook for Jersey cows. - The pocketbook for Jersey cows was also informed by the smallholder Jersey trial, which ran from October 2023 to March 2024 and was implemented by SGM-Danone with PRISMA’s support. |
| Maize: Central Java provincial government and the Sumenep Office improve their maize seed subsidy planning systems | While provincial and local governments have promoted hybrid seed through their seed subsidy programs, subsidy planning has been inefficient, often resulting in high overlaps between the subsidy recipients and existing commercial seed users. This is a disincentive for seed companies to add investment and continue serving or expanding into certain geographies. As a result, in Phase 1, PRISMA facilitated a proof of concept pilot in Sumenep from 2016-2018. This pilot significantly reduced the overlap of subsidy recipients and commercial farmers and proved that smart subsidy planning works. PRISMA now supports the Central Java provincial government and the Sumenep Food Security and Agriculture Agency to ensure the smart subsidy practice is institutionalised, thereby increasing their willingness and capacity to continue implementing smart subsidy planning. PRISMA does this by: - developing databases and analysis tools for Sumenep and Central Java to show the level of hybrid seed adoption in different areas and providing training and coaching for government staff to utilise and regularly update the database - establishing guidelines for Sumenep and Central Java on how to identify target areas for subsidies based on the analysis of database results and improve the delivery of seed subsidy programs - capturing and promoting the benefits of smart subsidy planning to the national government through a study and policy brief based on the practices adopted in Sumenep and Central Java | Food Security and Agriculture Office Sumenep Food and Agriculture/DKPP) Central Java Provincial Agriculture and Plantation Office | (a) Completed: PRISMA has developed databases and analysis tools for Sumenep and Central Java. Government staff have also been trained and coached on the database. | - The database and analysis tool uses Microsoft Excel and Microsoft PowerBI Desktop to consolidate field-level data from public extension workers into visual mappings. - The database in Sumenep captures up to the village level, while Central Java captures up to the sub-district level. The databases need to be updated annually to maintain their accuracy for planning. - In Sumenep, a training session was conducted in September 2023, followed by several coaching sessions. In December 2023, the head of Dinas Sumenep appointed a task force to complete the database and use the analysis result for subsidy allocations (Prospective Farmers and Location Candidates/CPCL mechanism) in 2024. The Sumenep database was completed by June 2024. - In Central Java, the district-level Dinas had completed around 80% of the database data collection by June 2024, and the provincial Dinas are following up on the remaining 20%. PRISMA provided several coaching sessions to the provincial Dinas throughout this period. |
|  |  |  | (b) Ongoing: - In Sumenep, DKPP Sumenep expects to publish the guideline in July 2024. - In Central Java, the guideline was released in April 2023 and socialised to 18 maize-producing districts in June 2023. | - The guidelines in Sumenep can be applied to seed subsidies from the provincial or national budgets. However, the delivery mechanism, seed varieties, requirements of assistance from seed companies, and program evaluation will need to follow the guidelines provided by the budget owner. - The guidelines in Central Java focus on the seed subsidy that uses the provincial government’s budget. It provides 3 options for the delivery mechanisms (free seeds, price discount, and grant) as well as the suitable conditions for each mechanism. The guideline also covers criteria for seed varieties, mandatory variety testing and information on its characteristics by seed companies in the subsidy target area, and program evaluation. - Provincial Dinas also independently socialised the guidelines to 12 more districts. |
|  |  |  | (c) Ongoing: PRISMA is in the process of developing the study and policy briefs. To gain additional insights, the initial study results will be shared in a multi-stakeholder policy dialogue planned for August 2024. The final study report and policy brief will be disseminated in a policy seminar by the end of August or early September 2024. | - In February 2024, PRISMA contracted a research institute (CIPS) to conduct the study. As of May 2024, CIPS has completed the literature review and interviews with market players, and is currently analysing the results. |
| Pigs: The MoA accelerates the adoption of artificial insemination (AI) in the pig sector by improving standards and operating procedures for pig semen and standardising AI training and certification for inseminators. | As Indonesia recovers from African swine fever (ASF), there is an urgent need to restock the pig population. AI, which offers several advantages over natural mating (including faster expansion of herds and minimal risk of disease transmission), can help accelerate repopulation. However, widespread adoption of AI faces a number of challenges in Indonesia, including the lack of skilled pig inseminators and the absence of regulatory standards or operating procedures for certain types of pig semen. PRISMA supports the MoA in improving farmers’ access to skilled inseminators and stimulating pig breeding companies to produce high-quality pig semen for farmers. PRISMA does this by facilitating the process of developing: - a national curriculum and modules for pig inseminator training, as well as operational guidelines for educational and training institutions - specific work competency standards for inseminators (SKK Khusus), which will be used to certify inseminators across Indonesia - the SNI for frozen pig semen and standard operating procedures (SOP) to certify chilled pig semen from semen producers. | The MoA (the Kupang Animal Husbandry Training Center [BBPP], the Livestock and Animal Health Instrument Certification Agency [PSIPKH], and the Agricultural Extension and Human Resources Development Agency [BPPSDMP]) NTT Provincial Animal Husbandry Office | (a) Completed: - The AI training curriculum and modules were developed and piloted with a cohort of inseminators in NTT. The final curriculum and modules have been presented to the technical committee as the basis for developing the work competency standards. Once the registration number for the work competency standards is issued, this will officially be recognised as a national curriculum. - The operational guidelines for educational and training institutions to use the AI training curriculum and modules were developed and approved in November 2023. The guidelines can now be used by BBPP, universities, and other training institutions to conduct the AI training. | - The BBPP piloted the AI training for 32 inseminators from 10 districts in NTT, a government-owned farm in Kupang, and the Regional Artificial Insemination Centre in Bali. The pilot results were used to improve the curriculum and modules. - On average, participants improved their knowledge (with their test scores increasing by 20 percentage points after the training). |
|  |  |  | (b) Ongoing: - The SKK Khusus was drafted and endorsed by the head of BPPSDMP in June 2024. BPPSDMP sent a letter to the Ministry of Manpower in June 2024 to register the standard. The registration number for the standard is expected to be issued in August 2024. - After the registration, PRISMA will support BPPSDMP to conduct a socialisation event in Jakarta. - PRISMA will also support training for pig assessors selected by BPPSDMP in August 2024. Through the training, the assessors will be qualified to certify inseminators. | - As the final stage for developing the SKK Khusus, the BPPSDMP sent a letter (No.18469/TU.020/I.4/06/2024) to the Directorate General of Vocational Training and Productivity Development, Ministry of Manpower to register the standard on 19 June 2024. |
|  |  |  | (c) Ongoing: - The SNI for frozen pig semen was developed in collaboration with the Livestock and Animal Health Instrument Certification Agency at MoA (PSIPKH). - PSIPKH sent a letter to the National Standards Agency (BSN) in June 2024 to register the SNI. The SNI for the frozen pig semen is expected to be issued by BSN in September 2024. - The draft SOP to certify chilled semen from semen producers is in progress and expected to be finalised in July 2024. Once finalised, the SOP will be handed over to the Product Certification Agency (LS-Pro) under the MoA and tested with 3 semen producers. - Once the SNI is issued and the SOP is finalised, they will also be part of the socialisation event in Jakarta (along with the SKK Khusus). | - The NTT Provincial Animal Husbandry Office provided a supporting letter (No. 524.250/10/Bitpro/IV/2024) on 3 Apr 2024 to PSIPKH to request the development of an SNI for frozen pig semen. - PSIPKH sent a letter (No:B-529/PK.020/H.5/06/ 2024) on 20 June 2024 to BSN to register the SNI for frozen pig semen. |
| Policy Planning Processes |  |  |  |  |
| National Policy Planning Process: The National Development Planning Agency (Bappenas) formulates the 2025-2029 National Medium-Term Development Plan’s (RPJMN) food and agriculture development agenda based on robust policy evidence. | Bappenas is currently formulating the food and agriculture development agenda for the 2025-2029 RPJMN, which begins with the development of a background study. In the past, due to limited budget and resources, background studies were developed mainly through discussions with public officials and a few experts, with limited input from the private sector and the broader academic sector and imperfect market insights and evidence. Another challenge for the RPJMN is the need to ensure more relevant indicators and better alignment between the RPJMN and the MoA’s Strategic Plan (Renstra) for 2025-2029. PRISMA supports Bappenas with robust policy evidence based on market insights and public policy dialogue to shape RPJMN’s food and agriculture development agenda, ensuring it effectively addresses Indonesia's diverse needs and challenges. PRISMA does this by: - supporting Bappenas with a background study on agriculture modernisation and resilience in Indonesia, which identifies key constraints and priority interventions to accelerate the modernisation of Indonesia’s agriculture sector - developing indicators on the modernisation of agriculture for the RPJMN and ensuring alignment between RPJMN and MoA Renstra indicators - developing comprehensive policy studies in key thematic areas | Food and Agriculture Directorate, Bappenas Directorate for System and Procedure on Monitoring, Evaluation, Control of Development, Bappenas Planning Directorate, MoA Indonesian Centre for Agriculture Socio-Economic and Policy Studies (ICASEPS) | (a) Completed: The background study on modernisation and resilience in agriculture for RPJMN development has been completed and presented to Bappenas. | - The final draft of the background study was completed in January 2024. - The background study prompted Bappenas to request additional support from PRISMA on developing agricultural modernisation indicators for RPJMN. |
|  |  |  | (b) Ongoing: Workshops have been held with Bappenas and the indicators are expected to be finalised in August 2024. | - Two workshops were held with Bappenas in February 2024 and March 2024 to develop the indicators. - The World Bank has also reached out to PRISMA for support in synchronising the MoA’s Strategic Plan indicators with the RPJMN. |
|  |  |  | (c) Ongoing: PRISMA is in the process of developing the in-depth policy studies, which will be completed in August 2024. | - Four in-depth policy studies are being developed in key thematic areas (i.e. availability of quality food crop seeds, young farmer regeneration, agriculture digitalisation, and climate-smart agriculture). - These studies involve multi-stakeholder workshops as an integral component of their methodology. The aim of the workshops is to strengthen and confirm initial findings from the literature reviews, field surveys, and interviews. The Young Farmers Study workshop was held in May 2024, and 8 other workshops are planned. |
| Regional Policy Planning Process: The NTT provincial government formulates the 2025-2029 RPJMD for the agriculture sector using improved policy insights and data, including PRISMA’s evidence and market insights. | In 2024, the NTT Regional Development Planning, Research, and Innovation Agency (Bapperida) started preparing the NTT Regional Medium-Term Development Plan (RPJMD) for 2025-2029. While the NTT government has significant experience promoting development through subsidy programs, it now recognises the need for a vibrant commercial market to reach its regional development goals. As this is a nascent space for Bapperida, it currently lacks sufficient insights from the private sector and the necessary data to prioritise target areas for growing the commercial market. There is also a need to advocate for support from the national government, as national rules and regulations also influence the growth of NTT’s commercial markets. PRISMA supports Bapperida in preparing the participatory and technocratic planning of RPJMD NTT 2025-2029 for the agriculture sector, with a focus on insights and recommendations for a supportive business-enabling environment to encourage private sector investments, market growth, and shifting from subsistence to commercial agriculture. PRISMA does this by: - developing a planning tool to support the identification of target geographies for growing the commercial market and the development of suitable strategies - conducting a study on how the agriculture sector can support medium-term regional goals and holding a multi-stakeholder policy dialogue to gather additional inputs and perspectives - formulating recommendations for strategies, programs, and activities for NTT’s agriculture market development from 2025 to 2029 - developing and disseminating policy briefs to advocate for the national government’s support for NTT’s priorities | NTT Bapperida | (a) Ongoing: - NTT Bapperida launched the innovative planning tool during the 15-16 May 2024 multi-stakeholder policy dialogue in Kupang. - Before the launch, PRISMA conducted a training to introduce Bapperida staff to the new tool. This was followed by several coaching sessions where staff learned to update and operationalise the tool using the most recent data. - Additional coaching sessions are scheduled for July/August 2024 to ensure that staff have the confidence and capabilities to independently update and use the tool. | - This innovative planning tool, developed with the support of PRISMA, uses Microsoft PowerBI Desktop to consolidate data from multiple government agencies into visual mappings. - Bapperida is excited that the planning tool will help it decide on the priority geographies and develop strategies for key agricultural commodities in NTT. It can also use this information, along with inputs from the multi-stakeholder policy dialogue, to advocate for the national government's support. This has encouraged Bapperida to take the lead in coordinating with related agencies, including the Central Bureau of Statistics (BPS), to provide the data required for analysis. |
|  |  |  | (b) Completed: The data collection process and interviews have been completed, and a summary of initial findings and potential recommendations were presented in a multi-stakeholder policy dialogue on 15-16 May 2024. The policy dialogue also gathered additional inputs and perspectives from public and private stakeholders to inform the agricultural agenda in the 2025-2029 RPJMD. | - The NTT government issued a decree in Dec 2023 assigning related provincial government personnel to work with PRISMA for the studies. - The study commenced on February 20, 2024, with a kick-off meeting involving all related provincial government institutions. - The study was conducted with the support of a research firm and 8 consultants with commodity-specific expertise. It covers 9 commodities with a deep dive into the beef, pig, and maize markets as key drivers of NTT agriculture. - The policy dialogue covered strengthening the agriculture input market, aligning forces to tackle endemic pests and diseases, and developing strategies to link the agriculture sector with industry. An in-depth discussion was also conducted for 3 key commodities (beef, pig, and maize). - It was attended by more than 100 participants, covering representatives from provincial and district-level government agencies, private sectors, associations, research agencies, academia, and experts, as well as national-level government (Bappenas and the MoA). |
|  |  |  | (c) Ongoing: - A table summarising the recommendations for strategies, programs, and activities was submitted to Bapperida at the end of June 2024. - The table will be complemented with a report, which provides further details around the recommendations. The report is being finalised, with a targeted handover of all documents to Bapperida in mid-July 2024. | - The recommendations were formulated based on PRISMA’s learnings from working in NTT over the last decade, the initial study findings, analysis of results from the planning tool, and inputs from the multi-stakeholder policy dialogue. |
|  |  |  | (d) Ongoing: - The briefs will be completed in July 2024, with dissemination events in NTT and the national level planned for the end of July/early August 2024. | - The policy brief topics are being discussed with Bapperida to match their priority advocacy agenda to the national government. |
| Knowledge Sharing and Embedding Market Systems Development (MSD) |  |  |  |  |
| Knowledge sharing/embedding MSD: Government and academia build capacity in MSD | The remarkable success story of PRISMA has not only attracted Bappenas’s interest in the MSD approach but also instilled confidence that the approach can help the government more effectively achieve its development goals and objectives. Recognising PRISMA's expertise and success in the MSD approach, Bappenas’s Directorate of Food and Agriculture has requested that PRISMA support it in building MSD capacity in both the government and academia. PRISMA is delivering on this request by: - developing the national guidelines and training materials for designing and implementing an MSD program as a potential aid modality - conducting MSD training for government officials and academia | Bappenas MoA Local government champions (East Java, Central Java, NTB, NTT, Papua) Academia (Institut Pertanian Bogor [IPB], Gadjah Mada University [UGM], Brawijaya University [UB], University of Nahdlatul Wathan Mataram [UNWM]) | (a) Completed: The national MSD guidelines and MSD training materials have been completed and were used in the MSD training for government officials and academia. | - The national MSD guideline, “Government and Business Entity Partnership Program in Agricultural Sector Development Based on a Market System Approach”, was completed in November 2023. - The MSD training materials, which were completed in June 2024, included guidance on the market assessment process, identifying the root constraints, developing interventions, defining suitable monitoring and evaluation methods, and assessing the signs of market sustainability. |
|  |  |  | (b) Completed: A 5-day MSD training was conducted for government officials, university lecturers, and a DFAT representative. | - The June 2024 MSD training involved 23 participants (18 government officials, 4 university lecturers, and 1 DFAT representative). - In the closing ceremony, Mr. Jarot Indarto, Head of the Food and Agriculture Directorate of the Ministry of National Planning/Bappenas, awarded participants training certificates and commended the outcome of PRISMA’s training. He also encouraged participants to work together to implement MSD principles in Indonesia. - Nearly all participants (95%) reported an improved understanding of the MSD approach, and all participants indicated that they understood the value of partnerships between the government and private sector. - Furthermore, 50% of the graduates have already developed post-training action plans and a third plan to share information about MSD with their office heads, managers, and colleagues. |
| Knowledge sharing/embedding MSD principles: Universities improve their offering by incorporating PRISMA’s experience into their academic programs and by serving as a repository for PRISMA’s knowledge and lessons | PRISMA identified academia as a key institution to independently promote PRISMA’s knowledge and lessons after the program ends. By incorporating learnings from industry, universities can provide students with tangible insights into real-world applications and challenges in agriculture while also addressing the pressing issue around the skills mismatch between university graduates and industry needs. There is also a need for more practical knowledge around inclusive businesses and climate-smart agricultural initiatives in academic programs, as these are emerging focus areas at universities. PRISMA capitalises on its existing relationships with UB and UNWM to archive and share its knowledge more widely and ensure that UB and UNWM enhance their educational materials and academic curricula by embedding PRISMA’s lessons on inclusive business and climate-smart agriculture. Also, they can continue developing and implementing improved academic programs by having additional resources. PRISMA does this by: - sharing its knowledge products (for example, learning briefs, market watch, market briefs) through the online UB library - assisting UB in developing and testing climate-smart livestock protocols, which will be used as a benchmark when university researchers or students conduct future climate-smart trials - assisting UNWM in revising its curriculum by enriching its entrepreneurship course with the MSD approach and insights from the inclusive business incubator program | UB UNWM | (a) Ongoing: UB is in the process of storing and uploading PRISMA’s knowledge products into the university’s repository. A launching event will be held after the approval from DFAT and Bappenas. | - In April 2024, UB proposed using its website to disseminate PRISMA's knowledge products for students and the general public. - The UB library team is now reviewing PRISMA’s knowledge products. It will generate metadata for these files to optimise accessibility for students from various courses/subjects. |
|  |  |  | (b) Ongoing: - The closed-house pen trial was completed while the emission control blocks (ECB) trials are ongoing. The results from both trials are feeding the development of protocols for climate-smart trials, which will be completed in July 2024. - UB is preparing a workshop for August 2024 where its lecturers and researchers will discuss how to integrate the protocols and climate-smart practices into UB’s classes and research. | - UB recognised the benefits of integrating PRISMA's lessons learned and knowledge products into its academic programs. - Professor Hendrawan from UB was hired to conduct the ECB trials with Agcotech. He is harvesting lessons learned from the ECB trials and the closed-house pen technology trial with PT Medion to finalise protocols for climate-smart trials by July 2024. |
|  |  |  | (c) Ongoing: - The revised curriculum will be completed in July 2024 through a series of workshops, focus group discussions, and a trial run with students. - The course will be officially launched in August 2024 and will take in its first cohort of students in the upcoming 2024/2025 academic year. | - UNWM has also recognised the benefits of integrating PRISMA's lessons learned and knowledge products into its academic programs. - UNWM has formed a team to extract insights from PRISMA (including the UNWM business incubator program, market assessments, and digital marketing) and utilise them to develop an agri-tech business course and ensure alignment with curriculum standards at the university. - UNWM conducted a curriculum workshop in June 2024 to inform the development of the curriculum and ensure alignment with the government’s Outcome Based Education (OBE) standards. The workshop involved perspectives from various stakeholders, including government and agribusinesses. |

Annex 3: Detailed Key Performance Indicators

KPI 1 - Outreach

The mechanisation, beef, mungbean, soil treatment, dairy, vegetable, rice, and pig sectors generated outreach benefits this semester. The following table highlights the most significant outreach contributions during the semester (all outreach figures here are overlapped and unadjusted):

| Mechanisation (East Java, East Nusa Tenggara [NTT] and Central Java) 18,467 | PRISMA partnered with agriculture machine service providers to promote the use of combine harvesters during the rice and maize harvesting process. Combine harvesters can lower farmers' production costs, especially labour costs for harvesting and transporting crops, and labour food consumption during harvest. Two impact assessments and 3 extrapolations were conducted for mechanisation interventions, which resulted in 18,467 outreach in East Java, NTT, and Central Java. |
| --- | --- |
| Mungbean (East Java and Central Java) 17,707 | PRISMA worked with 5 seed producers to promote the commercial production of a high-quality mungbean seed variant, namely VIMA. With PRISMA's assistance, seed producers significantly increased their sales by reaching smallholder farmers. This semester, PRISMA conducted extrapolations based on mungbean sales from the partners and ascertained that 17,707 mungbean farmers have benefitted through improved productivity. |
| Pig (NTT) 9,220 | PRISMA worked with various breed partners to improve pig farmers’ access to quality piglets and artificial insemination. Additionally, PRISMA partnered with PT Sreeya Sewu Indonesia to promote high-quality feed among farmers. As a result of these interventions, farmers have experienced shorter rearing periods, increased productivity, and higher incomes. This semester, PRISMA’s extrapolations from previous impact assessment data revealed that 9,206 pig farming households in NTT have benefitted due to PRISMA’s interventions. |

KPI 2 - Net attributable income change (NAIC)

This semester, incremental NAIC from all beneficiary farming households reached IDR253 billion, which brought the cumulative NAIC up to IDR9.27 trillion or approximately AUD927 million. This number equals an accumulated average income increase of IDR4.79 million per household.

The detailed incremental NAIC per household in each sector is as follows:

| dairy | IDR | 9,140,304 |
| --- | --- | --- |
| vegetable | IDR | 6,283,836 |
| fertiliser | IDR | 4,753,031 |
| mungbean | IDR | 4,726,234 |
| beef | IDR | 4,262,812 |
| pig | IDR | 2,606,400 |
| rice | IDR | 1,810,169 |
| mechanisation | IDR | 1,356,029 |

KPI 3 - Number of intermediary service providers (ISPs) providing additional or improved access to innovation to farming households

This semester, 95 new ISPs started providing improved services and delivering innovations from PRISMA’s partners to smallholder farmers, bringing the cumulative number of ISPs to 15,107. Pig sector partners added 32 intermediary providers for breeding interventions, and the remaining ISPs came from partners in the mechanisation, beef, rice, and vegetable sectors.

KPI 4 – Women’s economic empowerment (WEE) effectiveness within PRISMA innovations

KPI 4 represents the ratio between the proportion of women accessed (by PRISMA's partners) to the proportion of their participation in farming. The ideal ratio is 1.0, which means that agribusinesses provide information to the full proportion of women that match their farming participation.

The WEE effectiveness score increased significantly from 0.91 to 1.59. PRISMA partners have successfully engaged more women proportionally to the overall involvement of women in the sector. The cumulative WEE effectiveness now stands at 0.79, which is up from 0.75 in the previous semester. These results underscore PRISMA's commitment to promoting gender equality and inclusivity, showcasing the positive impact of its interventions in empowering women economically within the agricultural sector.

KPI 5 – Value of additional turnover of ISPs

PRISMA recorded an incremental IDR194 billion (equivalent to AUD19.4 million) turnover of its partners’ ISPs. The most significant contribution came from the ISPs in the beef sector, which brought the cumulative ISP turnover to IDR2.46 trillion (AUD246 million) and is proof of the sustainability and effectiveness of the business models introduced through PRISMA's partners.

KPI 6 - Number of intervention partners (private and public sector)

In this reporting period, PRISMA focused on conducting resilience activities with existing partners and did not record any new partnerships.

KPI 7 - Value of additional turnover of private sector partners (PSP)

This semester, PRISMA’s private sector partners' turnover reached IDR144 billion (AUD14.4 million), raising the cumulative amount to IDR1.46 trillion (AUD146 million). The beef, dairy, and pig sectors were significant contributors this semester (83% of the total additional PSP turnover amounts to IDR120 billion).

KPI 8 - Value of attributable additional and/or more inclusive investment by PSPs, ISPs, and farmers

The investment value committed by PRISMA's private and public partners, identifiable ISPs, and farmers this semester amounted to IDR246 billion (AUD24.6 million). Of this amount, IDR21.2 billion (8.6%) was invested by PRISMA's partners, IDR141 billion (57.3%) by the ISPs, and IDR83.4 billion (34.1%) by the smallholder farmers adopting innovations. Cumulatively, the total investment from PSPs, ISPs, and farmers attributable to PRISMA’s interventions reached IDR3.06 trillion (AUD306 million).

KPI 9 - Number of crowding-in businesses/institutions

During this reporting period, PRISMA successfully identified and confirmed 2 crowding-in businesses from the rice and vegetable sectors. In the rice sector, UD Arif Tani Mandiri in Karawang adopted PRISMA’s partner, CV Fiona Benih Mandiri's business model, focusing on producing and promoting high-yielding rice seed varieties (HYV).  In the vegetable sector, PT Benih Citra Asia, a national seed company in Indonesia, introduced its vegetable seeds under the brand name "Bintang Asia" and is using similar business strategies with PRISMA’s partner East West Indonesia (Ewindo) in marketing its quality seeds in Tanah Papua. The copying strategy includes starting business penetration from the cluster's entry point, setting up distribution channels through Ewindo's distributors, hiring local field staff, building relationships with Ewindo's key farmers and farmer group leaders, and conducting inclusive promotional activities.

KPI 10 - Number of responding businesses/institutions

PRISMA identified and facilitated the growth of 6 additional responding businesses in the soil treatment sector. PT Seger Agro Nusantara and PT Syngenta Seed Indonesia collaborated with PRISMA’s partner, PT Saprotan Utama Nusantara, to provide services to improve the maize sector in underserved areas in NTT. Bank Rakyat Indonesia (BRI) and Bank Mandiri offered financing programs to agri-kiosks/retailers during the collaboration event with PRISMA soil treatment partner, PT ATS. As a follow-up, BRI and Mandiri offered financing to 50 agri-kiosks in Central and East Java. Meanwhile, PT Terra Agro Digital has used the fertilizer recommendation tools from PT Mitra Sejahtera Membangun Bangsa, PRISMA’s partner in ICT sector, to provide their contract farmers with suitable fertilizer dosage. PT Bina Pertiwi, a agri-machinery company authorized dealer, has implemented machinery tools financing scheme for seven service providers  in collaboration with PT Bank Nano Syariah, PRISMA partner in finance sector.

KPI 11 - Number of policy engagement

During this semester, PRISMA undertook 48 policy engagement initiatives. These engagements derived from cross-sectoral initiatives, such as capacity development training for government and academics on market systems development (MSD) and supporting the development of the 2024-29 RPJMD in NTT province (14 policy engagements), and sector-specific strategies, including mechanisation (9 engagements), maize (7 engagements), soil treatment (6 engagements), dairy (4 engagements), beef (3 engagements), mungbean (3 engagements), and information and communications technology (ICT) (2 engagements). The notable engagements are as follows.

PRISMA conducted MSD training for participants from Bappenas, the MoA, province and district-level governments, and universities. The training aimed to introduce the MSD concept. The government is expected to adopt relevant MSD principles to deliver more sustainable impacts in its program planning. The participating universities are also anticipated to embed MSD principles in their learning curricula.

The maize, beef, and pig sectors worked with the NTT Research and Innovation Development Planning Agency (Bapperida) to support the development of the NTT 2025-2029 RPJMD. This aimed to provide evidence-based policy advocacy for vital commodities in NTT and stimulate private sector investment. PRISMA also supported the development of the commodity mapping instrument and the agriculture background study research with inputs from local and national government agencies and the private sector.

PRISMA also facilitated collaboration between the private sector and the government in resilience activities conducted by different sectors. In the mechanisation sector, PRISMA supported a series of workshops in East and Central Java with provincial-level agriculture training centres to increase the utilisation rate of agriculture mechanisation services and thereby sustain the business of the government mechanisation service units (UPJA). The dairy sector has continued developing the “Good Dairy Farming Practices Guidelines” that will be integrated into an Agriculture Minister Draft Regulation (Rapermentan) by conducting coordination meetings and workshops with the MoA’s Breed and Livestock Production Directorate. In Boyolali district, PRISMA facilitated joint activities between NuFeed, a concentrate feed producer, the District Livestock Agency, and the District Social Agency to conduct a socialisation event on disability inclusion.

PRISMA

Jl. Margorejo Indah I block A-535,

Surabaya 60238, Indonesia

info@aip-prisma.or.id

+62 31 8420473

www.linkedin.com/company/prisma-indonesia/

PRISMA is supported by the Governments of Australia and Indonesia and implemented by Palladium, with Technical Assistance from Swisscontact, Zurich.

The 8 HPPIs include: (1) Beef: The MoA reforms and implements the revised cattle feed standards (SNI); (2) Dairy: The MoA develops and implements a dairy recovery strategy to accelerate sector recovery and build resilience; (3) Maize: Central Java provincial government and the Sumenep District Office improve their maize seed subsidy planning systems; (4) Pigs: The MoA accelerates the adoption of AI in the pig sector by improving standards and operating procedures for pig semen and by standardising AI training and certification for inseminators; (5) National Policy Planning Process: Bappenas formulates the 2025-2029 RPJMN’s food and agriculture development agenda based on robust policy evidence; (6) Regional Policy Planning Process: The NTT provincial government formulates the 2025-2029 RPJMD for the agriculture sector using improved policy insights and data, including PRISMA’s evidence and market insights; (7) Knowledge sharing/embedding MSD: The government and academia build capacity in MSD; and (8) Knowledge sharing/embedding MSD principles: Universities improve their offering by incorporating PRISMA’s experience into their academic programs and by serving as a repository for PRISMA’s knowledge and lessons.

The 8 HPPIs include: (1) Beef: The MoA reforms and implements the revised cattle feed standards (SNI); (2) Dairy: The MoA develops and implements a dairy recovery strategy to accelerate sector recovery and build resilience; (3) Maize: Central Java provincial government and the Sumenep District Office improve their maize seed subsidy planning systems; (4) Pigs: The MoA accelerates the adoption of AI in the pig sector by improving standards and operating procedures for pig semen and by standardising AI training and certification for inseminators; (5) National Policy Planning Process: Bappenas formulates the 2025-2029 RPJMN’s food and agriculture development agenda based on robust policy evidence; (6) Regional Policy Planning Process: The NTT provincial government formulates the 2025-2029 RPJMD for the agriculture sector using improved policy insights and data, including PRISMA’s evidence and market insights; (7) Knowledge sharing/embedding MSD: The government and academia build capacity in MSD; and (8) Knowledge sharing/embedding MSD principles: Universities improve their offering by incorporating PRISMA’s experience into their academic programs and by serving as a repository for PRISMA’s knowledge and lessons.

The national sector-specific policies for beef, dairy and pigs target relevant directorates at the MoA, while the maize sector targets provincial and district agriculture agencies. The national and regional policy planning processes target the Food and Agriculture Directorate, Bappenas and the Provincial Planning Agency of NTT. The initiatives to embed MSD and share PRISMA’s knowledge target national and regional governments and universities (Institut Pertanian Bogor [IPB], Gadjah Mada University [UGM], Brawijaya University [UB], and University o Nahdlatul Wathan Mataram [UNWM]).

Examples: beef SNI socialisation events, dairy guidelines socialisation events, maize smart subsidy planning study and policy brief dissemination events, pig policy socialisation events, RPJMD-NTT policy brief dissemination events, climate-smart protocol and online data repository launch, and an agri-tech business course launch.

Overlap in this context is when a beneficiary household benefits from 2 or more PRISMA interventions. When a household has already been claimed it cannot be claimed again.

This semester, PRISMA started tracking its reach, looking back at the last 2 years when it increased its digital presence through the Economist Impact’s website and social media campaign and launched its LinkedIn page.

After PRISMA commenced, provinces in Tanah Papua (the ‘Land of Papua’) were split up. Papua and West Papua are still used in the main body of the report, but the vegetable progress report refers to the new provinces.

The majority (61.9%) of smallholder farming households reached by PRISMA are under the USD5.50 purchasing power parity (PPP) poverty line. In fact, a large cohort (36.7%) of smallholder farming households reached by PRISMA face extreme poverty with less than USD2.50 PPP per day.

See the infographic on page 62 with progress towards systemic change across 12 agricultural sectors.

PRISMA contributed AUD24.6 million in additional turnover for SMEs up to Dec 2023.

See Chapter 3 for progress in cross-cutting areas of gender equality, disability, and social inclusion.

See Annex 1 for more on PRISMA’s market resilience activities.

See Chapter 4 for progress in emission reductions and climate change adaptation.

Overlap in this context is when a beneficiary household benefits from 2 or more PRISMA interventions. When a household has already been claimed it cannot be claimed again.

For the investment leverage indicator, private sector investment corresponds to KPI8, which includes investment committed by PRISMA's public and private partners, intermediate service providers, and farmers. Although this technically includes investment from the government, these amounts are insignificant when compared to other market actors. For the sake of simplicity, this indicator is labelled as “investment leverage (private sector)”.

PRISMA’s total intervention cost includes implementation staff costs, travel costs, results, measurement and learning costs, co-facilitator costs, communication, and capacity building.

PRISMA also considered the increased number of cattle sold by each farmer, but data shows that the number of cattle sold by farmers after using concentrate feed is not vastly different. This semester, an impact assessment in NTB showed farmers sold 2.1 cattle per year, compared to 1.5 before PRISMA interventions. Increased emissions due to additional cattle sold was accounted for in the calculation.

Throughout this semester, PRISMA conducted 4 field impact assessments across 3 sectors, incorporating WEE questions. These 4 impact assessments involved 235 user respondents, comprising 104 women and 78 men who were asked about WEE.

The number of participants may vary across 6 WEE dimensions based on the impact of the interventions on women and the clear attribution from the partnership. For instance, a mechanisation intervention provided a combine harvester service to women farmers, but targeted promotional activities toward the machinery service provider only. As a result, women may experience increased access to valuable mechanisation services, economic advancement, and a more manageable workload, but may not necessarily experience increased access to information or knowledge.

To add context, PRISMA’s independent learning module was designed without a dedicated budget to address the frequent budget challenge for capacity building — thus, no allowances were provided. PRISMA developed the videos and e-books used in this module in collaboration with the Provincial Agriculture and Food Security Office and the Agency for Standardisation of Agriculture Instruments (BPSIP).

Bali, North Sulawesi, South Sulawesi, Central Kalimantan, Papua, Highland Papua, Central Papua and West Papua

Take, for example, the HPPI related to the beef sector. When looking at it through the lens of its support areas, the first 2 support areas have been completed while the 3rd support area is marked as ongoing (implying 60% completed and 30% ongoing). However, within the 3rd support area, PRISMA has already completed 2 of the deliverables (training for feed auditors, feed quality supervisors and training for feed companies) and is planning to complete the remaining deliverable (socialisation events for the national feed standard [SNI] and good feed manufacturing practices [GFMP] video) in July 2024. As a result, by organising the summary graph around deliverables, we have a more accurate reflection of PRISMA's overall progress in each HPPI (beef SNI: 90% completed, 10% ongoing).